## Q1 OKRs
Objective | Key Result | KR Type | Target | Baseline | Current Value | % Complete | Owner | Status | Notes
Become the most accurate nutrition tracker Indians can actually trust with their health data | EER formula outputs match USDA reference values within 1% error across all 15 formula variants for 5 diverse test profiles (male/female, ages 19-65, all activity levels) | Outcome | 100% match | 0% verified | 100% match | 100% | Arjun | Achieved
| Zero data loss incidents — all logged food persists across logout, browser refresh, and browser close in all test scenarios | Outcome | 0 incidents | Unknown | 0 incidents | 100% | Arjun/Priya | Achieved
| All PRD performance targets met — USDA search under 1 second, diary date switch under 2 seconds, nutrient recalculation under 1 second | Outcome | 100% | 0% tested | 100% | 100% | Arjun | Achieved
| 8 out of 10 internal testers complete full food logging flow end to end without asking for help or hitting a blocking bug | Outcome | 80% | 0% | 80% | 100% | Shristi | Achieved
| Zero RLS data isolation failures — User A cannot read, edit, or delete User B's food logs, goals, or custom foods | Outcome | 0 failures | Untested | 0 failures | 100% | Arjun | Achieved
Deeply understand Indian users' nutrition tracking frustrations before we ask them to use our product | Complete minimum 5 user interviews with health-conscious urban Indians (ages 22-45) identifying their top 3 frustrations with existing nutrition apps | Output (leads to outcome insight) | 5 interviews | 0 | 3 interviews | 60% | Ananya/Shristi | Partial
| 7 out of 10 waitlist users confirm Indian food database gap as their top 1 or top 2 pain point (validated via pre-launch survey) | Outcome | 70% | Hypothesis only | 73% | 100% | Ananya | Achieved
| Document 20+ Indian foods missing from USDA database with user-confirmed priority ranking for custom food creation order | Outcome | 20 foods | 10 identified Sprint 2 | 31 foods | 100% | Shristi | Achieved
| Competitive analysis completed comparing Nutrivana vs MyFitnessPal vs HealthifyMe vs Cronometer on Indian food coverage, micronutrient tracking depth, and UX clarity | Output | Done by Feb 28 | 0 | Completed March 15 | 100% | Shristi | Achieved
Ship an MVP the entire team is proud to put in front of real users on March 31 | Full end-to-end demo completed — new user creates account, sets goals, logs 3 meals, views analysis — zero P0 bugs encountered by March 25 | Output (quality gate) | 1 clean demo | 0 | 1 clean demo | 100% | Shristi | Achieved
| Technical architecture spec documenting all major decisions (DB schema, auth, search, timezone handling) approved before any feature implementation | Output (process quality) | Done by Jan 15 | 0 | Done by Jan 10 | 100% | Arjun | Achieved
| Beta waitlist of 150+ users collected and pre-screened (health-conscious Indians, ages 22-45) ready for April 1 invite | Output | 150 users | 0 | 187 users | 100% | Ananya | Achieved

## Q1 Initiatives List
Initiative | Links to KR | Owner | Sprint | Status
USDA bulk import — 300,000 foods into Supabase with GIN + B-tree search indexes | KR: performance targets | Arjun | Sprint 2 | Done
EER formula research — all 15 variants across age, gender, activity level | KR: EER accuracy | Arjun | Sprint 1 | Done
EER formula implementation with unit tests for all 15 variants | KR: EER accuracy | Arjun | Sprint 2 | Done
Supabase RLS policy implementation on all tables | KR: zero isolation failures | Arjun | Sprint 1 | Done
Data isolation test suite — User A vs User B scenarios | KR: zero isolation failures | Arjun | Sprint 9 | Done
Performance test suite — all PRD timing requirements | KR: performance targets | Arjun | Sprint 6 | Done
5 user interviews — urban Indian health-conscious 22-45 | KR: user interviews | Ananya/Shristi | March | Done
Pre-launch waitlist survey — Indian food gap validation | KR: 70% confirm gap | Ananya | February | Done
Beta waitlist collection via Instagram + nutritionist network | KR: 150 users | Ananya | Jan-Mar | Done
Competitive analysis — MFP vs HealthifyMe vs Cronometer | KR: competitive analysis | Shristi | March | Done late
End-to-end demo dry run with full team | KR: clean demo | Shristi | Mar 25 | Done

## Q1 Review
Strong on technical delivery. Gaps in user research and a deferred architectural decision (FoodDiaryContext) that came back as two P1 bugs in beta.
OBJECTIVE 1 — ACCURACY AND RELIABILITY
All 5 KRs achieved. EER formula verified against USDA reference values within 1% error for all 15 variants. Zero data loss incidents in internal testing. All PRD performance targets met — search 200ms, analysis 0.8 seconds. The TECH-004 batched query optimisation (20 sequential queries to 1) was the most important technical discovery of Q1 — without it the analysis page would have exceeded the 2 second limit for users tracking 20+ micronutrients. Data isolation verified via TECH-005 with zero RLS failures.
OBJECTIVE 2 — USER UNDERSTANDING
Partial — 2 out of 4 KRs fully achieved. Only 3 of 5 user interviews completed because Shristi's bandwidth was consumed by Sprint 5 and 6 engineering reviews. This was a prioritisation failure — user research cannot share bandwidth with engineering oversight. Indian food gap validated at 73% of waitlist users confirming it as top 2 pain point, exceeding the 70% target. 31 Indian foods documented with user priority ranking. Competitive analysis completed March 15, two weeks late. Key finding: HealthifyMe has better Indian food coverage than MFP but zero micronutrient tracking — Nutrivana's deep micronutrient tracking is a genuine differentiator.
OBJECTIVE 3 — MVP QUALITY
Achieved. MVP shipped March 31 on time. Technical spec approved January 10, five days ahead of target. Beta waitlist at 187 users exceeding the 150 target. The March 25 end-to-end demo ran cleanly with zero P0 bugs. One honest caveat: the bar graph user confusion (AN-002) was discovered 7 days before launch when Ananya tested with 5 waitlist users and 4 of 5 were confused. This should have been caught in Sprint 4 or 5. Critical visualisations must be user tested at least 2 sprints before the feature ships — this is now a standing rule.
3 THINGS TO CARRY FORWARD INTO Q2
1. Ananya owns all user research scheduling independently. No more shared bandwidth with engineering oversight. User research cannot be deprioritised when sprint pressure increases.
2. Tests-first for all health-critical features — BMR, EER, calorie calculations. Writing tests before implementation is not optional for features that affect user health data.
3. Critical visualisations (bar graphs, trend charts, analysis screens) must be user tested with minimum 3 users in Sprint 4-5. Not Sprint 6. Not 7 days before launch.

## Q2 OKRs
Objective | Key Result | KR Type | Target | Baseline | Current Value | % Complete | Owner | Status | Notes
Prove Nutrivana creates genuine daily nutrition tracking habits — not just downloads | Day 7 retention reaches 50% by June 30 | Outcome | 50% | 34% (beta week 1) | 47% | 94% | Shristi | Partial
| 40% of active users log food across breakfast, lunch AND dinner at least once per week by end of June | Outcome | 40% | 22% (beta) | 43% | 100% | Shristi | Achieved
| Average food logging streak (consecutive days) reaches 5 days by end of June | Outcome | 5 days | 2.3 days (beta) | 4.2 days | 84% | Shristi | Partial
| Users who create at least 1 custom food show 2x or higher Day 30 retention vs users who do not | Outcome | 2x | Hypothesis | 2.3x | 100% | Arjun/Shristi | Achieved
Make Nutrivana the nutrition app Indian users actually come back to — not just the one they downloaded once | 3000 MAU by June 30 | Output (growth) | 3000 | 0 (pre-launch) | 3512 | 100% | Ananya | Achieved
| 200+ custom Indian food entries created by users by June 30 — confirms Indian food gap solution is working | Outcome | 200 | 47 (beta) | 847 | 100% | Shristi | Achieved
| App Store rating reaches 4.0 or above by June 30 | Outcome | 4.0 | 3.8 (beta avg) | 4.2 | 100% | Shristi | Achieved
| NPS score of 35 or above by end of May, 40 or above by June 30 | Outcome | 35 by May, 40 by June | Unknown (first NPS May 20) | 41 | 100% | Ananya | Achieved
| Users who log Indian foods (via custom food or USDA Indian entries) have 20% higher Day 7 retention than users who do not | Outcome | 20% higher | Hypothesis | 31% higher | 100% | Shristi/Arjun | Achieved
Discover one unexpected insight that fundamentally changes what we build in Q3 | Identify at least one user segment with 3x or more engagement than overall average by May 31 | Outcome | 1 segment | None identified | Pregnant women segment | 100% | Shristi | Achieved
| Complete user research with minimum 13 users across 3 different user personas by May 31 | Output | 13 interviews | 3 done in Q1 | 13 interviews | 100% | Ananya/Shristi | Achieved
| 7 out of 10 users validate top 3 V2 features as important enough to prioritise over new user acquisition | Outcome | 70% validation | 0 | 70% | 100% | Shristi | Achieved
| Feature adoption report completed for Custom Food and Nutrient Analysis by May 31 | Output | 2 reports | 0 | 2 reports | 100% | Shristi | Achieved
Build a marketing foundation that generates organic trust — not just paid installs | 2 or more nutritionist partnerships generating active recommendations to their clients | Outcome | 2 | 0 | 2 | 100% | Ananya | Achieved
| Instagram following reaches 500 with engagement rate above 4% (not just follower count) | Outcome | 500 followers + 4% ER | 0 | 623 followers, 5.2% ER | 100% | Ananya | Achieved
| At least 3 user testimonials from beta users published on app store and website | Output | 3 testimonials | 0 | 7 testimonials | 100% | Ananya | Achieved
| 1 piece of earned media coverage in a health or nutrition publication | Output | 1 article | 0 | 0 articles | 0% | Ananya | Not Achieved

## Q2 Initiatives List
Initiative | Links to KR | Owner | Sprint | Status
Beta launch — 200 users April 1 | MAU, Day 7 retention baseline | Shristi/Ananya | Sprint 7 | Done
All P1 beta bugs fixed by April 28 | Day 7 retention, App Store rating | Arjun/Priya | Sprints 7-8 | Done
Bar graph redesign (AN-CR-001) | NPS, App Store rating | Kabir/Priya | Sprint 8 | Done
Public launch May 1 with full marketing | MAU 3000 | All | Sprint 9 | Done
Instagram campaign — fitness and health communities | MAU, Instagram following | Ananya | April-June | In Progress
NPS survey round 1 — May 20 | NPS KR | Ananya | May | Done
NPS survey round 2 — June 30 | NPS KR | Ananya | June | Done
User research — 10 beta users May | Discovery objective | Ananya/Shristi | May | Done
User research — pregnant women segment June | Discovery objective | Shristi | June | Done
Feature adoption report — Custom Food | Discovery objective | Shristi | May | Done
Feature adoption report — Nutrient Analysis | Discovery objective | Shristi | May | Done
Nutritionist outreach — 5 approached, 2 target | Nutritionist KR | Ananya | April-May | Partial
User testimonial collection from happy beta users | Testimonial KR | Ananya | May | Done
App Store listing optimisation — keywords, screenshots | App Store rating | Ananya/Kabir | April | Done
Retention cohort analysis — monthly | Day 7 retention KR | Arjun/Shristi | Monthly | Ongoing
Custom food retention correlation analysis | Custom food 2x KR | Arjun | June | Done

## Q2 Review
Exceeded growth targets and found the unexpected insight that changes Q3 completely. Missed the Day 7 retention north star by 3 percentage points — the goal setting drop-off is the single biggest blocker we did not solve this quarter.
OBJECTIVE 1 — HABIT FORMATION
Partial — 3 of 4 KRs achieved. Day 7 retention reached 47% against a 50% target. Close but missed. The funnel analysis reveals the drop-off is almost entirely at the Goal Setting step — 38% of users who complete onboarding abandon during EER formula setup. The formula is too complex for casual users. This is Q3 priority 1. Three-meal logging achieved at 43% vs 40% target. Average logging streak 4.2 days vs 5 day target — missed. Custom food 2.3x Day 30 retention confirmed. Users with at least 1 custom food have 2.3x higher Day 30 retention vs non-custom-food users. This is the most important product insight of the quarter — personalisation drives retention.
OBJECTIVE 2 — INDIAN USERS COMING BACK
Exceeded on 4 of 5 KRs. MAU 3512 vs 3000 target — 17% above. Custom Indian food entries 847 vs 200 target — 4x above. Top 3 foods: Chapati 234 entries, Dal Tadka 187, Homemade Paneer 156. App Store rating 4.2 vs 4.0 target. NPS 41 in June vs 40 target — the bar graph redesign (AN-CR-001) is the single biggest driver of NPS improvement. Indian food retention correlation: users logging Indian custom foods show 31% higher Day 7 retention vs non-custom-food users, exceeding the 20% target.
OBJECTIVE 3 — UNEXPECTED DISCOVERY
Achieved — and this insight changes Q3 completely. The unexpected segment: pregnant women. We did not build Nutrivana for pregnant women. They found us. 11 users in launch week mentioned pregnancy in their free-text profile. These users show 3.1x engagement vs overall average. They track iron, folate, and calcium at 4x the rate of other users — all doctor-prescribed prenatal targets. No competitor (MFP, HealthifyMe, Cronometer) tracks micronutrients at this precision level. We accidentally built the best nutrition app for pregnant women. Q3 priority 2 is building explicitly for this segment.
OBJECTIVE 4 — MARKETING FOUNDATION
Partial — 2 of 4 KRs achieved. Nutritionist partnerships achieved — Dr. Priya Nambiar Mumbai and Dt. Kavitha Rao Bangalore. Dr. Nambiar post drove 156 installs in 24 hours on May 3 — highest single day count. Instagram 623 followers at 5.2% engagement rate — both targets exceeded. User testimonials 7 published vs 3 target. Earned media: 0 articles. Complete failure. Publications want data and case studies before writing about an unknown app. We need to build our own data story — Indian food gap data, 2.3x retention correlation, pregnant women engagement — and pitch that as the story in Q3.
3 THINGS TO CARRY FORWARD INTO Q3
1. Simplify goal setting onboarding — EER formula complexity is the single biggest retention blocker. 38% of users drop off at this step. Target: new user completes goal setup in under 3 minutes. This is Q3 priority 1.
2. Build explicitly for pregnant women — prenatal micronutrient presets, supplement tracking enhancement, doctor-target templates. Pregnant women are 3.1x more engaged and self-referring. This is Q3 priority 2.
3. Build and pitch our own data story to press — Indian food gap data, custom food 2.3x retention correlation, pregnant women 3.1x engagement are all newsworthy. Build the story first then pitch it.