## Sprint Summary
Ticket | Committed | Delivered | Notes
MON-001 | Yes | Yes | May 15 — custom foods per day metric added after Arjun's early retention observation
MON-002 | Yes | Yes | May 18 — 3.1x engagement confirmed, survivorship bias ruled out, iodine finding noted
BUG-010 | Yes | Yes | May 15 — same clearSearchState pattern, fix applied to 2 additional places proactively
AN-CR-003 | Yes | Yes | May 19 — analysis load time 1.8s → 0.7s on mid-range Android
NPS-001 | Yes | Yes | May 21 — NPS 34, 187 responses, goal setup complexity as top complaint
RES-001 | Yes | Yes | May 22 — 5 interviews, WhatsApp group referral behaviour discovered
MKT-001 | Yes | Yes | May 22 — Kavitha Rao post live, 89 installs in 48 hours
BUG-011 | Yes | Yes | May 16 — iOS Safari onBlur fix applied to all 6 free-text fields
V2-PLAN-001 | Yes | Yes | May 25 — Q3 priorities documented, shared with Ravi

## Retrospective Narrative
Retrospective Narrative
Sprint Summary | Sprint 10 was a transformative sprint for Nutrivana, focusing on understanding user behavior rather than just building features. We successfully analyzed user feedback, identified critical areas for improvement, and confirmed the pregnant women's segment as a key focus for Q3.
What Went Well | 1. The pregnant women cohort analysis methodology was rigorous, as noted in ticket MON-002. Arjun conducted two bias checks before sharing any numbers, confirming a 3.1x engagement and 81.8% Day 7 retention, which we can confidently present to Ravi. 2. The iOS Safari bug fix (BUG-011) was crucial for our retention strategy. Custom food creation was failing for 15% of iOS users, and resolving this issue has now unblocked a significant portion of our highest-retention users, enhancing their experience with the app. 3. The NPS survey design (NPS-001) exceeded our expectations. By adding a follow-up question about the most desired feature, we gathered actionable insights that ranked the custom recipe builder, barcode scanner, and simplified goal setup as top priorities for Q3.
What Did Not Go Well | 1. The analysis for ticket MON-002 took longer than anticipated due to the comprehensive bias verification process Arjun implemented. While this was the right decision, it delayed the availability of critical cohort analysis results until May 18, impacting our overall sprint timeline. 2. Our NPS score of 34 (NPS-001) fell short of our Q2 target of 35. Although the difference is small, the feedback highlighted goal setup complexity as a major pain point. This is a recurring issue we've known about since March, and our delay in addressing it is a pattern we need to break.
Key Learnings | 1. Small samples can provide significant insights. The pregnant women user group, while only 11 individuals, demonstrated an 81.8% Day 7 retention rate, which is a strong directional signal that can influence our Q3 strategy. 2. Research tasks require more time than engineering tasks due to the need for thorough iteration and validation. We need to incorporate this understanding into our sprint planning to ensure realistic timelines. 3. Qualitative research, such as user interviews, reveals insights that quantitative data cannot. The WhatsApp referral behavior discovered during user interviews is an example of valuable information that would not have surfaced through analytics alone.
Decisions Made | 1. The pregnant women segment has been confirmed as a Q3 priority 2, following simplified onboarding, based on credible data and validated user interviews. 2. Q3 priorities have been locked in: simplified onboarding to address the 38% drop-off, prenatal presets for the pregnant women segment, and a custom recipe builder as the top NPS request. 3. We approved the update of App Store screenshots to include the Chapati search result image, as recommended by Ananya. 4. The tests-first standard has been extended to require explicit unit display test cases for any feature that touches both mg and mcg micronutrient displays.
Action Items
Action | Owner | Due Date
Share pregnant women cohort analysis with Ravi in investor update | Shristi | May 28
Update App Store screenshots with Chapati search result | Kabir/Ananya | June 5
Begin Sprint 11 research planning — funnel analysis and feature adoption reports | Shristi | May 27
Document Q3 priorities formally in roadmap document | Shristi | May 30
Schedule remaining pregnant women interviews for June | Ananya | May 28
Team Health | 4/5 | The transition from building to learning has been both energizing and slightly anxiety-inducing. While the insights gained are invaluable, the team is still adjusting to a new rhythm that feels less tangible but more impactful.

## Metrics This Sprint
Metric | Value
MAU end of sprint (May 26) | approximately 1,100
MAU end of May | 1,247
Day 7 retention end of May | 45%
NPS score May 20 | 34
NPS response count | 187
NPS response rate | 23%
Custom foods cumulative end of sprint | approximately 280
App Store rating end of sprint | 4.1
Pregnant women Day 7 retention | 81.8% (9 of 11 users)
Pregnant women sessions per day | 4.2 vs 1.8 overall average
Pregnant women session length | 6.3 min vs 2.8 min overall
Pregnant women engagement multiple | 3.1x
Dr. Kavitha Rao partnership installs | 89 in 48 hours
Analysis screen load time after optimisation | 0.7 seconds
iOS Safari bug: affected users | approximately 15% of iOS users
Bugs fixed this sprint | 2 (BUG-010, BUG-011)