## Sprint Summary
Ticket ID | Committed | Delivered | Notes
NUTR-BUG-002 | Yes | Yes | Apr 20 — source-type aware duplicate check
NUTR-BUG-007 | Yes | Yes | Apr 22 — frozen snapshot approach
NUTR-BUG-008 | Yes | Yes | Apr 21 — synchronous clear on source change
NUTR-BUG-009 | Yes | Yes | Apr 20 — two bugs found, both fixed
NUTR-BUG-010 | Yes | Yes | Apr 22 — in-place array update + alphabetical sort
GOAL-BUG-001 | Yes | Yes | Apr 21 — full cascade function refactor
GOAL-BUG-005 | Yes | Yes | Apr 22 — tests first, then fix
CF-BUG-003 | Yes | Yes | Apr 21 — is_mandatory flag in renderer
CF-BUG-004 | Yes | Yes | Apr 21 — ID extraction from API response
AN-CR-001 | Yes | Yes | Apr 26 — progress bar with thermometer overflow
AN-CR-002 | Yes | Yes | Apr 24 — remaining/over target copy
Overall delivery rate |  |  | 11 out of 11 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | Sprint 8 was a successful stabilisation sprint where we delivered all 11 committed tickets. By April 28, we achieved zero P1 bugs in production, positioning us well for our public launch on May 1. Notable moments included a proactive codebase audit and the implementation of a tests-first approach for health-critical features.
What went well | 1. The codebase audit triggered by Shristi (NUTR-BUG-008) was a significant success, as it not only identified the recurring 'fix not applied to related components' issue but also led to the proactive fixing of 2 additional instances. This demonstrates our commitment to mature engineering practices by addressing root causes rather than just symptoms. 2. Implementing a tests-first approach for GOAL-BUG-005 was a game changer for our team. By writing tests before the fix, we were able to uncover the full scope of the regression, ensuring that our health-critical features are robust and reliable. 3. The redesign of the progress bar in AN-CR-001, informed by real user testing, resulted in a genuinely improved user experience. The new thermometer overflow metaphor effectively communicates both achievement and excess, which aligns perfectly with our goal of making nutrition tracking intuitive.
What did not go well | 1. Despite our efforts, the 'fix not applied to related components' issue reappeared for the third time this sprint in NUTR-BUG-008. Identifying this pattern in previous sprints and adding it to our PR review checklist did not suffice, indicating that we need to focus on creating shared utility functions instead of relying solely on checklists. 2. NUTR-BUG-009 highlighted a significant USDA data normalization issue that had been present since Sprint 2 but went unnoticed until beta testing. This indicates a need for more systematic data quality validation on external sources to prevent such oversights in the future.
Key learnings | 1. Checklists do not prevent duplicate-function bugs. Shared utility functions do. Every repeated logic pattern must be a shared function. 2. External data quality issues (like the USDA column order) can only be identified by testing edge cases with real data. We need to increase our edge case coverage for external data sources. 3. The tests-first approach for health-critical features is now a non-negotiable team standard that we must adhere to.
Decisions made | 1. Tests-first for all health-critical features (GOAL-BUG-005). 2. Codebase audit as standard response when a pattern is found more than twice (NUTR-BUG-008). 3. Custom meal values frozen at creation time snapshot, not live-calculated (NUTR-BUG-007). 4. Progress bar design with thermometer overflow for over-target (AN-CR-001). Replaces original bar = target metaphor. 5. Remaining/over target as standard label copy across diary and analysis (AN-CR-002).
Action items
Action | Owner | Due date
Create shared formatNutrient utility function | Priya/Arjun | Sprint 9
Create shared color utility function | Priya/Arjun | Sprint 9
USDA data quality audit — all 40+ micronutrient columns | Arjun | Sprint 9
Shristi to draft public launch announcement email | Shristi | Apr 29
Ananya to prepare launch day social media posts | Ananya | Apr 30
Team health rating | 4 | Tired but proud. The product is genuinely ready for public launch. Bug count has dropped significantly from Sprint 7 (10 bugs) to Sprint 8 (11 but mostly P2). The bar graph redesign energized the team — shipping a real improvement based on user feedback is more satisfying than bug fixing.

## Metrics This Sprint
Metric | Value
Beta DAU | 67 (out of 200 users — 33.5% daily active)
Day 7 retention improvement | 34% → 41% (driven by bug fixes)
Custom foods created | 47 (up from 23 at Sprint 7 end)
App Store rating | 3.8 → 4.0 (after bug fixes and AN-CR-001)
Beta user NPS informal survey | estimated 28-32
Bug reports from users this sprint | 3 (all P2, all fixed)