## Sprint Summary
Ticket ID | Committed | Delivered | Notes
CF-BUG-001 | Yes | Yes | One-line fix with massive impact.
CF-BUG-002 | Yes | Yes | Snapshot approach implemented, migration needed.
AN-BUG-001 | Yes | Yes | Zero fill in application code resolved.
AN-BUG-004 | Yes | Yes | Shared color function created.
AN-BUG-005 | Yes | Yes | FormatNutrient shared utility developed.
TECH-005 | Yes | Yes | All isolation tests passed.
CF-EPIC-001 | Yes | Yes | Beta users created 47 custom Indian food entries.
Overall delivery rate |  |  | 7 out of 7 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | Sprint 9 was a pivotal moment for Nutrivana as we successfully launched the app to the public on May 1, 2025. The sprint focused on final bug fixes and enhancements, with AN-BUG-001 being a critical issue that we resolved just in time. We also celebrated the closure of CF-EPIC-001, showcasing the engagement of our beta users who created 47 custom Indian food entries. Overall, this sprint marked a significant milestone in our journey.
What went well | 1. The implementation of shared utility functions for AN-BUG-004 and AN-BUG-005 was a significant win this sprint. This approach not only resolved immediate bugs but also improved the maintainability of our codebase, aligning with our goal to 'fix the root cause, not the symptom'. 2. CF-BUG-001's one-line fix demonstrated the importance of thorough SQL query reviews. By changing NOW() to $diary_date, we preserved the integrity of our historical data, showcasing our commitment to data accuracy and user trust. 3. TECH-005's proactive security analysis by Arjun was commendable. He identified a potential vulnerability in the CF-BUG-002 snapshot approach and confirmed it was not exploitable, ensuring our app remains secure for users handling sensitive health data.
What did not go well | 1. AN-BUG-001, which addressed the missing skipped days in the 7-day trend, became a priority zero issue at launch. Despite being specified correctly, it was not implemented as intended, highlighting a recurring gap between specification and execution that we need to address. 2. CF-BUG-001 inadvertently changed historical data for 8 beta users, marking a serious data integrity failure. This incident underscores the necessity for rigorous reviews of date-parameterized queries to prevent similar issues in the future.
Key learnings | 1. We must close the gap between specification and implementation by developing test cases that directly mirror specifications before merging code. 2. Always review date-parameterized queries with the critical question: 'Am I using the correct date for the historical context?' to avoid issues like those seen with CF-BUG-001. 3. The creation of shared utility functions is a proven strategy to eliminate duplicate-function bugs, and we should continue to expand this practice across our codebase.
Decisions made | 1. Established a shared color utility function as a single source of truth for all nutrient color logic. 2. Created a shared formatNutrient utility to standardize numeric nutrient display rounding. 3. Decided that nutrient snapshots in food_logs will ensure past data remains immutable, even if food definitions change. 4. Implemented zero-fill for skipped days in the 7-day trend to always return exactly 7 data points.
Action items
Action | Owner | Due date
One-time migration to backfill food_log nutrient snapshots | Arjun | May 20
Conduct a review of all historical queries focusing on date-parameterized queries | Arjun | May 20
Create a specification-to-implementation test pairing process | Shristi | May 15
Begin user research with beta users to gather feedback | Shristi | May 15
Launch NPS survey to gather user satisfaction data | Ananya | May 20
Conduct a team retrospective on the full Jan-May journey | All | May 12
Team health rating | 4 | The public launch was a significant achievement, reflecting our hard work over the past months. While we faced some challenges, the overall growth and collaboration within the team have been commendable. As we move into the next phase, we need to focus on refining our processes.

## Metrics This Sprint
Metric | Value
Day 1 installs | 312 installs on May 1, 2025.
Week 1 MAU | 847 active users in the first week.
Day 7 retention | 43% retention rate for the May cohort.
App Store rating | 4.1 rating as of May 12, 2025.
Custom foods created since launch | 203 custom foods created since launch, totaling 847 including beta.
AN-BUG-001 reports resolved | 12 users notified about the resolution.
Launch NPS | Too early to assess NPS.
Ananya Instagram followers | 287 followers gained from 0 at launch.