## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
NUTR-TASK-001 | USDA database integration and API setup | Task | In Progress | P0 | Arjun Mehta | Sprint 2 | 5 | We need to integrate the USDA FoodData Central API to allow users to select food items from a comprehensive database when logging their meals. This integration must ensure that search results are displayed quickly and accurately, even with potential spelling errors. Additionally, we need to ensure that the nutrient breakdown is displayed correctly for each food item added to the food diary. | • User can select the Food Database as a source when adding a food item. • Search results are displayed within 1 second of user input. • System supports fuzzy matching for search queries. • Food database appears instantly as the user adds food in the food diary. • User is redirected to the adjust portion page upon selecting a food source. • All nutrients related to food or recipe are displayed in the nutrient breakdown. • Default unit associated with each nutrient is displayed. • DV% is calculated based on a 2000 calorie diet.
NUTR-TASK-002 | Fuzzy search implementation for USDA food database | Task | In Progress | P0 | Arjun Mehta, Priya Nair | Sprint 2 | 5 | We need to implement a fuzzy search feature for our USDA food database to enhance user experience. The goal is to allow users to find food items even if they misspell or partially type the name. This will involve using PostgreSQL's trigram similarity extension, which is supported by Supabase. The search results must be displayed quickly and clearly, ensuring users can easily navigate the food options. | • Search results must be displayed within 1 second of user input • Support fuzzy or partial matching for food item names • Display results in a scrollable list with clear labels • Clear previous input if the user changes the source or navigates away
GOAL-001 | Set calorie goal with EER calculation | Story | In Progress | P0 | Arjun Mehta | Sprint 2 | 8 | We need to implement a calorie goal setting feature that calculates the user's EER based on various inputs. This feature will gate access to the food diary, ensuring users can only log their meals after setting a valid calorie goal. The inputs must include age, height, weight, sex, goal weight, target date, and activity level, with real-time updates to the EER as changes are made. | • All mandatory fields are marked with an asterisk. • EER calculation is triggered upon completion of the form. • Users can only access the food diary after setting a valid calorie goal. • Real-time recalculation of EER and calorie budget as user changes inputs.
GOAL-002 | EER formula implementation per gender and activity level | Story | In Progress | P0 | Arjun Mehta | Sprint 2 | 8 | We need to implement the EER formula that varies based on gender, age group, and activity level. This will ensure that our users receive accurate calorie recommendations tailored to their specific profiles. The implementation must also handle real-time updates when users change their personal details such as weight, height, or activity level. | • EER formula correctly adjusts based on gender, age group, and activity level. • Real-time updates occur when user changes weight, height, or activity level. • Formula selection matrix is created and tested with various user profiles.
GOAL-003 | Required deficit and surplus calculation | Story | In Progress | P1 | Arjun Mehta | Sprint 2 | 5 | We need to implement the calculations for required deficit and surplus based on user inputs. This involves using the formula provided in the PRD to ensure that the app can dynamically calculate these values as users update their weight, target date, and other relevant metrics. The calculations should always yield positive values and be accurately reflected in the user's food diary. | • Required surplus and deficit calculations are implemented correctly based on user inputs. • Values are recalculated when any of the dependent variables change. • All edge cases are handled, ensuring positive values for deficit/surplus.
GOAL-004 | BMR validation with warning message | Story | Done | P1 | Arjun Mehta | Sprint 2 | 5 | This story implements BMR validation for both system-calculated and user-defined calorie goals. The validation ensures that if a user's calorie budget falls below their BMR, appropriate warnings and error messages are displayed. It is crucial to maintain user safety and prevent unhealthy weight loss practices. The implementation will also differentiate between system-calculated goals and user-defined inputs, ensuring a robust user experience. | • If calorie budget is less than BMR, show error message and do not set the calorie goal. • If user-defined target calorie is less than BMR, show warning but allow saving. • Remove goal weight and target date when system-calculated calorie goal is below BMR. • Preserve EER display even when goal weight is removed.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
NUTR-TASK-001 | 1 | Arjun Mehta | 2025-01-15 | I've started the integration with the USDA FoodData Central API. My plan is to call the API in real-time for every search query to ensure users get the most accurate results.
NUTR-TASK-001 | 2 | Arjun Mehta | 2025-01-17 | I encountered a critical issue. The USDA API has a rate limit of 1000 requests per hour per API key. This means that during peak usage, we could hit this limit quickly, making real-time calls impractical.
NUTR-TASK-001 | 3 | Shristi Sharmistha | 2025-01-18 | How does this rate limit affect our 1-second search performance requirement? If we are limited, searches could fail or be delayed, which would be a major issue for user experience.
NUTR-TASK-001 | 4 | Arjun Mehta | 2025-01-19 | To resolve this, I suggest we bulk download the entire USDA dataset and import it into our Supabase database. This way, all searches will hit our own database, eliminating rate limits and allowing for sub-100ms response times.
NUTR-TASK-001 | 5 | Shristi Sharmistha | 2025-01-20 | That sounds like a solid plan, but what about Indian foods? Are items like idli, dosa, and chapati available in the USDA database? If users can't find these, it could be a dealbreaker for our target market.
NUTR-TASK-001 | 6 | Arjun Mehta | 2025-01-21 | I checked the USDA dataset, and unfortunately, it has a significant gap for Indian foods. For example, chapati is listed as 'Bread, whole wheat' with incorrect nutrient values. This is a major risk for our product.
NUTR-TASK-001 | 7 | Shristi Sharmistha | 2025-01-22 | I acknowledge the Indian food gap is a known risk. Let's proceed with the USDA import as our primary database, but we should fast-track a Custom Food feature to allow users to add missing items. We can document this gap for beta testing feedback.
NUTR-TASK-001 | 8 | Arjun Mehta | 2025-01-24 | I've completed the bulk import of over 300,000 food items into Supabase, and all nutrient columns are mapped correctly. I've created a search index on the food name column, and initial tests show that searches for items like 'chicken' and 'apple' return results within 200ms. Closing this ticket now.
NUTR-TASK-002 | 1 | Arjun Mehta | 2025-01-16 | I've created this ticket to implement the fuzzy search now that we have the USDA data in Supabase. I propose we use the pg_trgm extension for this.
NUTR-TASK-002 | 2 | Priya Nair | 2025-01-17 | Can you explain how the trigram similarity works? I'm curious how it would match 'chiken' to 'chicken'. Also, should we trigger the search on every keystroke or wait for a pause?
NUTR-TASK-002 | 3 | Arjun Mehta | 2025-01-18 | Sure! The trigram similarity breaks words into sequences of three characters and compares them. 'Chiken' and 'chicken' share enough trigrams to score high. I recommend a 300ms debounce on the frontend for a balance between responsiveness and reducing unnecessary database calls.
NUTR-TASK-002 | 4 | Priya Nair | 2025-01-19 | I tested the trigram approach, but I ran into an issue. Searching for 'dal' returns 0 results because it's only 3 characters. It seems like the trigram similarity isn't effective for such short queries.
NUTR-TASK-002 | 5 | Arjun Mehta | 2025-01-20 | Good catch! I propose a hybrid approach: use ILIKE for short queries (under 4 characters) for faster exact matches, and switch to trigram for longer queries. This way, 'dal' will return results using ILIKE, while 'chiken' will use trigram.
NUTR-TASK-002 | 6 | Shristi Sharmistha | 2025-01-21 | The PRD states that search results must appear within 1 second. Has anyone tested performance with 300,000 rows? I’m concerned that a full table scan with ILIKE could be slow.
NUTR-TASK-002 | 7 | Arjun Mehta | 2025-01-22 | I ran some performance tests, and without an index, ILIKE on 300,000 rows took 800ms, which is too slow. I created a GIN index for trigram and a B-tree index for ILIKE. After re-testing, ILIKE with the index took 45ms and trigram took 120ms. Both are well under the 1 second requirement!
NUTR-TASK-002 | 8 | Priya Nair | 2025-01-23 | I've implemented the frontend search component with the 300ms debounce and the hybrid routing for queries. I tested searches for 'dal', 'chicken', 'chiken', and 'broc'. All returned relevant results within 200ms. I think we can close this ticket!
GOAL-001 | 1 | Shristi Sharmistha | 2025-01-15 | I've created this story to define the acceptance criteria for the calorie goal setting page. Let's ensure all mandatory fields are clearly marked.
GOAL-001 | 2 | Arjun Mehta | 2025-01-16 | I started the implementation but noticed a discrepancy. The PRD mentions 5 activity levels, but the USDA EER documentation only lists 4. Which levels should we use?
GOAL-001 | 3 | Shristi Sharmistha | 2025-01-17 | Good catch, Arjun! The PRD was based on an older source. Let's stick with the USDA's 4 activity levels for accuracy. I'll update the PRD accordingly.
GOAL-001 | 4 | Arjun Mehta | 2025-01-18 | Thanks, Shristi. Another question: should the EER recalculate in real-time as users change their gender or activity level, or only after they submit the form?
GOAL-001 | 5 | Shristi Sharmistha | 2025-01-19 | Let's go with real-time recalculation. The EER and calorie budget should update immediately as users make changes. No submit button needed for calculations.
GOAL-001 | 6 | Arjun Mehta | 2025-01-20 | I've implemented the backend for the calorie goal, including the EER formula logic and real-time calculation endpoints. I’ll also handle the weight goal type detection.
GOAL-001 | 7 | Arjun Mehta | 2025-01-22 | The backend is complete! Shristi, can you review the API response structure before Priya starts on the frontend? I’ve shared a sample response with all calculated fields.
GOAL-001 | 8 | Shristi Sharmistha | 2025-01-24 | I've reviewed the API response and everything looks good. The weight_goal_type field is crucial for our color coding and formula displays. I approve the backend implementation. Let's move forward with the frontend!
GOAL-002 | 1 | Shristi Sharmistha | 2025-01-15 | Arjun, please reference the findings from GOAL-SPIKE-001 as you implement the EER formulas. We need all 15+ variants to be included with the correct selection logic.
GOAL-002 | 2 | Arjun Mehta | 2025-01-16 | I've started the implementation and created a formula selection matrix. However, I've noticed that the age groups differ across genders, which complicates things. For example, the female formulas include a +20 constant that isn't present in the male formulas. Can you confirm if this is intentional?
GOAL-002 | 3 | Shristi Sharmistha | 2025-01-17 | Yes, the +20 thermic effect constant is correct according to USDA documentation. The different structures for age groups are also accurate. Please proceed with implementing all variants as per the research document.
GOAL-002 | 4 | Arjun Mehta | 2025-01-20 | I've implemented the formula selection logic and created a lookup table keyed by gender, age group, and activity level. I've tested it with 12 user profiles including edge cases. However, I found an issue regarding users who turn 19. The system currently only recalculates EER when a variable is manually changed. It doesn't auto-switch on their birthday.
GOAL-002 | 5 | Shristi Sharmistha | 2025-01-21 | Let's consider the auto age-group transition as a V2 feature. For V1, we will only update the formula when the user manually updates their age in their profile. Please document this as a known limitation.
GOAL-002 | 6 | Arjun Mehta | 2025-01-24 | I've completed the full implementation of all 15 formula variants and the real-time recalculation feature. I've also written unit tests for each variant to ensure accuracy. I’ll run the tests now.
GOAL-002 | 7 | Shristi Sharmistha | 2025-01-26 | Great work, Arjun! Once you finish testing, please share the results. I want to ensure that all EER values align with USDA reference values before we close this ticket.
GOAL-002 | 8 | Arjun Mehta | 2025-01-27 | All tests have passed successfully! The EER values for the profiles I tested match the USDA reference values perfectly. I’ll go ahead and close the ticket now.
GOAL-003 | 1 | Shristi Sharmistha | 2025-01-20 | Hey Arjun, can you please confirm that the 7700 constant we're using for the deficit calculation is accurate? I believe it represents the energy equivalent of 1 kg of body fat, but I want to double-check before we proceed.
GOAL-003 | 2 | Arjun Mehta | 2025-01-21 | Yes, you're correct! The 7700 kcal is indeed the approximate energy equivalent of 1 kg of body fat. I’ll implement the formula now, ensuring that it recalculates correctly when any of the dependent variables change, like the calorie goal or target date.
GOAL-003 | 3 | Arjun Mehta | 2025-01-24 | I've completed the implementation. The dependency matrix is quite complex since three different variables can trigger different updates. I've documented everything in the code comments for future reference. Can you review the edge cases to ensure we’re covered?
GOAL-003 | 4 | Shristi Sharmistha | 2025-01-25 | I’ve tested all scenarios, including weight loss, weight gain, and maintenance. The required deficit/surplus is always positive, and the calculations are accurate. Everything looks good, so I’ll go ahead and close this ticket!
GOAL-004 | 1 | Shristi Sharmistha | 2025-01-20 | Hey Arjun, just wanted to clarify the two scenarios we need to handle for BMR validation. The first one is when the system calculates a calorie goal below BMR, which should block the goal and show an error. The second is when users manually set a calorie goal below BMR, where we should show a warning but still allow them to save. Can you confirm you understand the distinction?
GOAL-004 | 2 | Arjun Mehta | 2025-01-21 | Got it, Shristi! I’ll implement both BMR formulas using the Mifflin-St Jeor equations as outlined in the PRD. I’ll ensure that the validation logic is distinct for system-calculated and user-defined goals. This is definitely a critical feature for user health, so I’ll make sure to get it right.
GOAL-004 | 3 | Arjun Mehta | 2025-01-25 | I’ve completed the implementation! Both BMR formulas are working as expected, and the validation paths are correctly set up. Shristi, could you please test the edge case where the system calculates a calorie goal below BMR due to an aggressive weight loss target? I want to ensure everything is functioning properly.
GOAL-004 | 4 | Shristi Sharmistha | 2025-01-26 | I tested the scenario with a test user: female, 60kg, aiming for 45kg in 30 days. The system calculated a negative calorie goal, which correctly blocked goal setting and displayed the error message with the exact BMR value. The goal weight and target date were removed, but EER was preserved. I also tested the manual override and confirmed that it allows saving with a warning. Everything looks good, so I’ll go ahead and close this ticket!