## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
GOAL-005 | Default macro distribution 40:30:30 of target calorie | Story | In Progress | P1 | Arjun Mehta | Sprint 3 | 5 | We need to implement a default macro distribution of 40:30:30 for carbohydrates, fats, and proteins based on the user's target calorie intake. This should be automatically calculated and displayed when the user navigates to the macro setting step. Additionally, the macro breakdown must be shown in both kcal and grams, and should update automatically if the target calorie changes. | • Default macro goal should auto-populate as 40:30:30 when user reaches macro setting step. • Macro breakdown must display both kcal and grams. • If a user changes their target calorie, the gram equivalents should auto-update. • Macros should remain hidden if no calorie goal is set.
GOAL-006 | Custom macro percentage input with real-time gram and kcal recalculation | Story | In Progress | P1 | Priya Nair | Sprint 3 | 8 | We need to implement a feature that allows users to set custom macro percentages for their calorie intake. The system should instantly recalculate the corresponding gram and kcal values as users adjust the percentages. This feature will enhance the user experience by providing real-time feedback and ensuring that users can easily track their nutritional goals. | • Users can input custom percentages for carbs, fats, and proteins. • The system recalculates and displays the corresponding gram and kcal values instantly. • Editable fields only accept numeric input between 0 and 100. • Changes to calorie goals automatically adjust macro values.
GOAL-007 | Validate macros sum to 100% with real-time error display | Story | Done | P1 | Priya Nair | Sprint 3 | 5 | This story focuses on implementing a real-time validation for the sum of custom macro percentages in the Nutrivana app. The total of carbs, protein, and fat must equal exactly 100%. If the sum is incorrect or any field is empty, appropriate error messages and visual cues will be displayed to guide the user. The validation must occur instantly after user input to enhance the user experience. | • Total of custom macro percentages must equal exactly 100% • All macro % fields must be filled to proceed • Display error messages in real-time if validation fails • Enable track macro checkboxes only when validation is successful • Persist macro values even after page refresh
GOAL-008 | Select macros to track after validation | Story | In Progress | P1 | Priya Nair | Sprint 3 | 5 | This story focuses on enabling users to select which macros they want to track in their food diary after validation. Users should have the flexibility to choose any combination of carbs, fats, and proteins, with the UI reflecting these choices immediately. The implementation must ensure that unselected macros do not disappear from the database but are simply hidden from the food diary until re-enabled. | • Users can select/deselect macros with checkboxes after validation. • Only selected macros appear in the food diary columns. • The UI updates within 1 second of selection changes. • Macro goals persist even if a macro is deselected.
GOAL-009 | View micronutrient list by category with tabs | Story | Done | P1 | Kabir Sharma, Priya Nair | Sprint 3 | 8 | This story focuses on organizing the micronutrient list into distinct categories such as vitamins, minerals, carbohydrates, and fats. Each category will be accessible via tabs, allowing users to select nutrients based on their dietary goals. A key requirement is that the micronutrient details will only be visible once the user has set their calorie budget. If no budget is set, users will be prompted to complete this step first. | • Micronutrients are categorized into vitamins, minerals, carbohydrates, and fats. • Each category is accessible via tabs that allow users to switch between them. • Nutrient details are displayed only after the user sets their calorie budget. • A message prompts users to set their calorie budget if it is not done. • Each nutrient displays a checkbox, name, RDA value, MAX value, and unit. • RDA and MAX values are adjusted based on user age and gender. • Users can select a maximum of 20 nutrients to track in their food diary.
GOAL-010 | Select micronutrients to track with RDA as daily target | Story | In Progress | P1 | Arjun Mehta | Sprint 3 | 5 | We need to implement a feature that allows users to select which micronutrients they want to track, with the RDA set automatically based on their age and gender. This feature should ensure that selected micronutrients persist across sessions and that only these appear in the food diary. Additionally, we need to consider how changes in user profile (age or gender) will affect the RDA values for these nutrients. | • Users can select/deselect micronutrients for tracking. • RDA values are automatically set based on age and gender. • Selected micronutrients persist after logout and page refresh. • Only selected micronutrients appear in the food diary. • A maximum of 20 nutrients can be tracked at once.
GOAL-011 | Edit custom micronutrient goal values | Story | In Progress | P2 | Arjun Mehta | Sprint 3 | 5 | We need to implement functionality that allows users to edit their custom micronutrient goal values. This feature should enable users to override the system-set RDA values with their own inputs, such as a doctor-prescribed intake. It's crucial that the custom values persist across sessions and that users can revert to the original RDA values if needed. | • Users can input and save custom micronutrient goal values. • Custom values should override the system-set RDA values. • The is_custom checkbox must be checked when a custom value is set. • Users can revert to the original RDA value by unchecking the is_custom checkbox.
GOAL-012 | RDA values by age and gender loaded from research data | Story | Done | P1 | Arjun Mehta | Sprint 3 | 5 | This story involves seeding the RDA and MAX values for various nutrients based on age and gender from our research data. The focus is on ensuring that all micronutrients are accurately stored and that discrepancies, such as the unit for Potassium, are handled correctly. This will enhance the accuracy of our food diary calculations and nutritional recommendations. | • RDA and MAX values for all specified nutrients are correctly seeded in Supabase. • Potassium values are stored in mg with appropriate conversion in the display layer.
NUTR-005 | Food diary view displaying only tracked nutrients as columns | Story | Done | P0 | Priya Nair | Sprint 3 | 8 | This story involves creating a food diary that dynamically displays only the nutrients selected by the user in their goal settings. The diary will present food items as rows and nutrients as columns, ensuring a maximum of 20 columns with a horizontal scroll feature. It is crucial that the nutrient values are non-editable and that the column order adheres to the specified guidelines. | • Only nutrients checked to track should be shown in the food diary. • Display a message if the user has not set goals. • Food diary must be in a tabular format with specified column order. • User can scroll left to right to view all nutrient columns. • Nutrient values in the food diary must be non-editable.
NUTR-006 | Select meal type — breakfast lunch dinner snacks supplement | Story | Done | P0 | Priya Nair | Sprint 3 | 5 | This story focuses on allowing users to select meal types when logging food in the Nutrivana app. Users should be able to choose from predefined categories such as Breakfast, Lunch, Dinner, Snacks, and Supplements. The implementation will ensure that the food diary is organized and intuitive, with a special emphasis on the conditional visibility of the supplement section based on user preferences. | • User can select from predefined meal types: Breakfast, Lunch, Snacks, Dinner, Supplement. • Food items added must be saved under the selected meal section in the food diary. • Supplement section appears only if enabled by the user. • Duplicate food entries are prevented within the same meal type.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
GOAL-005 | 1 | Shristi Sharmistha | 2025-01-29 | Hey Arjun, for the default 40:30:30 macro distribution, can you confirm the gram conversion formulas? I believe it's 4 kcal per gram for carbs and protein, and 9 kcal per gram for fats. Just want to make sure we're aligned on this.
GOAL-005 | 2 | Arjun Mehta | 2025-01-30 | Hi Shristi, yes, the 4/4/9 conversion rules are standard in nutritional science. I've started implementing the endpoint for the default distribution. When a user has a calorie goal, it will auto-calculate and save the 40:30:30 split in both kcal and grams without any user action needed.
GOAL-005 | 3 | Arjun Mehta | 2025-02-01 | I've completed the initial implementation. However, I need to clarify one behavior: if a user has a custom macro split saved from a previous session and returns to the goal setting page, should the default 40:30:30 override their custom split?
GOAL-005 | 4 | Shristi Sharmistha | 2025-02-02 | Good question, Arjun. The default 40:30:30 should only apply to first-time users. If a user has already set custom macros, those should be displayed instead. Let's make sure to add that first-time check to your implementation.
GOAL-006 | 1 | Shristi Sharmistha | 2025-01-29 | Hi Priya, for this story, we need three editable percentage input fields for carbs, fats, and proteins. Each field should show the live kcal and gram equivalents. Can you confirm if we will use a controlled React component for this? I want to ensure we have a solid component architecture.
GOAL-006 | 2 | Priya Nair | 2025-01-30 | Yes, Shristi, I plan to use a controlled component approach. Each input field will be managed by React state, and the onChange event will trigger the recalculation. However, I'm concerned about performance if users type quickly. Should we debounce the calculation, or calculate on every keystroke?
GOAL-006 | 3 | Priya Nair | 2025-01-31 | After considering the user experience, I've decided against debouncing. The PRD specifies instant calculations, so even partial inputs like '3' should show live feedback. This way, users will see immediate results as they type, which aligns with our UX goals. I'll implement it this way.
GOAL-006 | 4 | Shristi Sharmistha | 2025-02-04 | Great decision, Priya! I've tested the functionality, and it works perfectly. When I changed the carb percentage from 40 to 50, the fat and protein values updated correctly, even though their percentages didn't change. The auto-save feature is also functioning well. I think we can close this ticket now.
GOAL-007 | 1 | Shristi Sharmistha | 2025-01-30 | I've created this story to ensure the macro percentages sum to 100%. We need real-time validation and visual feedback for users. Priya, can you take the lead on implementing this?
GOAL-007 | 2 | Priya Nair | 2025-01-31 | I've started working on the validation logic using JavaScript. However, I encountered a floating-point arithmetic issue during testing. When I input 33.33 + 33.33 + 33.34, it calculates as 99.99999999999999 instead of 100. What should I do?
GOAL-007 | 3 | Arjun Mehta | 2025-01-31 | This is a common JavaScript floating-point precision problem. The IEEE 754 standard can't represent certain decimal values accurately. I suggest we round each input to two decimal places before summing them.
GOAL-007 | 4 | Priya Nair | 2025-01-31 | Should the rounding be applied only for display purposes, or should we also round the stored values? If we store 33.33333 but display 33.33, it might lead to discrepancies in calculations.
GOAL-007 | 5 | Arjun Mehta | 2025-01-31 | I recommend a clean solution: round the values at input time. Use parseFloat(value.toFixed(2)) for every input before storing it. This way, all values—displayed, stored, and validated—will remain consistent.
GOAL-007 | 6 | Shristi Sharmistha | 2025-01-31 | I agree that two decimal precision is sufficient for our macro tracking. Users expect to see their inputs accurately reflected. Priya, please implement the rounding fix as discussed.
GOAL-007 | 7 | Priya Nair | 2025-02-06 | I've implemented the rounding fix and tested various edge cases. For example, the input 33.33/33.33/33.34 now sums to 100.00 and displays green. However, 40/30/29 shows red with the appropriate error message. Also confirmed that values persist after refresh.
GOAL-007 | 8 | Shristi Sharmistha | 2025-02-07 | Great work, Priya! I've verified all scenarios, and everything looks perfect. The validation works as intended, and the persistence is confirmed. I will go ahead and close this ticket.
GOAL-008 | 1 | Shristi Sharmistha | 2025-01-30 | Hi Priya, just a heads up that the checkboxes for macros should only be visible after GOAL-007 validation passes. Can you confirm that when a user deselects a macro, it hides from the food diary immediately?
GOAL-008 | 2 | Priya Nair | 2025-01-31 | Yes, Shristi. Deselecting a macro will remove it from the food diary columns as per the PRD. However, the macro goal value will not be deleted, so users can re-select it later and the goal value will reappear. I’m currently working on tying the checkbox visibility to the validation state from GOAL-007.
GOAL-008 | 3 | Priya Nair | 2025-02-03 | I've implemented the checkbox visibility and macro selection persistence in the database. However, I need clarification on an edge case: if a user selects carbs and protein but not fat, and then changes their calorie goal, should the untracked fat macro goal still recalculate?
GOAL-008 | 4 | Shristi Sharmistha | 2025-02-04 | Absolutely, Priya. All macro goals should recalculate when the calorie goal changes, even for untracked macros. If the user later re-enables fat tracking, the correct gram value should be displayed. Please update the implementation accordingly. Thanks!
GOAL-009 | 1 | Shristi Sharmistha | 2025-01-29 | I've created this story to organize the micronutrient list into categories. Kabir, could you please start working on the design for the tab layout?
GOAL-009 | 2 | Kabir Sharma | 2025-01-30 | I've shared the Figma design with the tab navigation at the top. Each tab has a scrollable list of micronutrients. The desktop version looks clean, but I have concerns about mobile usability.
GOAL-009 | 3 | Kabir Sharma | 2025-01-31 | I ran a quick test on an iPhone, and with over 40 micronutrients, switching tabs feels fragmented. Users might struggle to find specific nutrients.
GOAL-009 | 4 | Ananya Iyer | 2025-02-01 | I've been onboarding beta users, and many expressed confusion with the tab layout. They prefer a single scrollable list where they can see all nutrients at once. It seems to create less friction during setup.
GOAL-009 | 5 | Shristi Sharmistha | 2025-02-02 | Kabir, can you propose three options for the layout? We need to consider tabs, an accordion style, and a single scrollable list. Each option should highlight trade-offs.
GOAL-009 | 6 | Kabir Sharma | 2025-02-03 | I've created three mockups: Tabs (as per the PRD), Accordion (compact but requires taps), and Single Scroll (most discoverable). I recommend the single scroll layout for better usability.
GOAL-009 | 7 | Shristi Sharmistha | 2025-02-04 | I've decided to go with the single scroll layout with sticky category headers. This change will enhance the mobile experience and is a better UX decision overall. Kabir, please update the Figma design accordingly.
GOAL-009 | 8 | Priya Nair | 2025-02-05 | I've implemented the new component based on Kabir's updated Figma design. The single scroll layout is working well on both mobile and desktop. I've also enforced the 20 nutrient limit correctly.
GOAL-010 | 1 | Shristi Sharmistha | 2025-01-30 | Hi Arjun, for this story, when a user selects a micronutrient checkbox, the RDA value for their age and gender should be automatically set as their daily target. Can you confirm that we will be using the RDA values from the GOAL-SPIKE-002 research table?
GOAL-010 | 2 | Arjun Mehta | 2025-01-31 | Yes, we will use the RDA values from GOAL-SPIKE-002. However, I have a question: what happens to the selected micro goals if the user updates their age or gender in their profile? For example, if a female user turns 31, the RDA for Vitamin A remains the same, but if she changes to male, it increases. Should we auto-update the selected micro goals?
GOAL-010 | 3 | Arjun Mehta | 2025-02-01 | I propose that we do auto-update the goals. When a user changes their age across an age group boundary or changes their gender, we should recalculate all selected micronutrient RDA goals. This aligns with how EER recalculates when similar profile changes occur. I can implement this auto-recalculation logic.
GOAL-010 | 4 | Shristi Sharmistha | 2025-02-02 | That sounds good, Arjun. Please ensure that the persistence requirements are tested thoroughly. Selected micros should survive logout, page refresh, and even browser restarts. Once that's confirmed, we can close this ticket.
GOAL-011 | 1 | Shristi Sharmistha | 2025-01-30 | Hi Arjun, I want to ensure that users can override RDA values with custom micronutrient goals. For example, if a doctor prescribes an iron intake of 30mg instead of the RDA of 18mg, we need to mark this custom value with an is_custom flag. Can you confirm if unchecking the is_custom box will revert to the RDA or clear the value entirely?
GOAL-011 | 2 | Arjun Mehta | 2025-01-31 | Great question, Shristi. When the user unchecks the is_custom box, it will revert to the RDA value stored in the background. The custom value acts as an override, so removing it will reveal the underlying RDA. I will implement the custom value storage with the is_custom flag for each nutrient per user.
GOAL-011 | 3 | Arjun Mehta | 2025-02-05 | I've made significant progress on the implementation. However, I need clarification on what happens if a user changes their age or gender after setting a custom micro goal. Should the custom value be overridden by the new RDA, or should it take precedence?
GOAL-011 | 4 | Shristi Sharmistha | 2025-02-06 | Thanks for the update, Arjun. The custom value should always take precedence over the RDA, even if the user updates their profile. The RDA in the background will update for non-custom nutrients, but we need to ensure that custom values remain untouched. This way, users have full ownership of their custom goals. Please proceed with the implementation.
GOAL-012 | 1 | Arjun Mehta | 2025-01-29 | I've seeded the RDA and MAX lookup table in Supabase using the data from GOAL-SPIKE-002. All micronutrients are now populated by age group and gender. I noticed that the Potassium target is supposed to be in grams, but the USDA data is in mg. I’ve stored it in mg for now and will handle the unit conversion in the display layer. Shristi, can you confirm that this approach is acceptable?
GOAL-012 | 2 | Shristi Sharmistha | 2025-01-30 | Thanks for the update, Arjun! Storing Potassium in mg and converting it at the display layer sounds like the right move to avoid any precision loss. I've double-checked the Vitamin A values for males and females aged 31-50, and they match the expected values. The RDA table looks correctly seeded. Let’s close this ticket once you finalize the display layer adjustments.
NUTR-005 | 1 | Shristi Sharmistha | 2025-02-03 | Hey Priya, for the food diary table structure, we need to ensure that the columns are determined by the nutrients selected in goal setting. Can you confirm if the component design will allow for dynamic columns based on user selections?
NUTR-005 | 2 | Priya Nair | 2025-02-04 | Yes, Shristi! The diary component will fetch the tracked nutrients from the goal settings and generate the column headers dynamically. However, I'm a bit concerned about the user experience with the horizontal scroll. Having 20 columns might make it cumbersome on mobile devices. Is this acceptable?
NUTR-005 | 3 | Shristi Sharmistha | 2025-02-05 | I understand your concern, but the PRD explicitly allows for a left to right scroll for nutrients. This is a deliberate design decision as Nutrivana aims to track more nutrients than other apps. The table format is a key differentiator for us. So, let's proceed with the horizontal scroll implementation.
NUTR-005 | 4 | Priya Nair | 2025-02-09 | I've implemented the dynamic column generation along with the horizontal scroll feature. I tested it with three tracked nutrients and also with the maximum of 20. The column order is correct, the scroll is smooth, and the empty diary displays the message properly when no goals are set. Everything is read-only as required. Ready for your review!
NUTR-006 | 1 | Shristi Sharmistha | 2025-02-01 | Hey Priya, just to clarify, the supplement toggle—should it be a global setting in the user profile or a per-day toggle in the food diary? I want to ensure we’re aligned on this before you start implementing.
NUTR-006 | 2 | Priya Nair | 2025-02-02 | I've checked the PRD, and it looks like the supplement toggle is meant to be a persistent setting in user preferences. Once enabled, it will stay active across all diary dates unless the user disables it. So, it’s not a per-day toggle.
NUTR-006 | 3 | Shristi Sharmistha | 2025-02-03 | Got it! That makes sense for users who take supplements regularly. Please go ahead and implement the meal section layout with the conditional supplement section. Also, remember this connects to NUTR-014 for the full supplement logging flow.
NUTR-006 | 4 | Priya Nair | 2025-02-10 | I've completed the implementation! The four meal sections are visible, and the supplement section is hidden by default. Switching between meal types is instant without any page reload. I’ll close this ticket now, but I’ll keep an eye on NUTR-014 for the toggle UI.