## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
NUTR-011 | Select custom recipe source and search saved recipes | Story | Done | P1 | Priya Nair | Sprint 5 | 5 | This story focuses on allowing users to select a Custom Recipe source from their saved recipes. The implementation will mirror the USDA food database functionality from NUTR-007, enabling users to search and select recipes seamlessly. We need to ensure the user experience is smooth and that the search results are accurate and quick. | • User can select Custom Recipe as a source from available food sources • User is redirected to the recipe menu page with all saved recipes • Search field is present to search and select recipes • Search results include recipe name — partial and full matches • Only one item can be selected at a time • If no matching recipe is found, a clear 'no results' message is displayed • If the user changes the source or navigates away mid-process, previous input is cleared
NUTR-012 | Select custom food source and search saved custom foods | Story | Done | P1 | Priya Nair | Sprint 5 | 5 | This story focuses on implementing the functionality for users to select custom food sources and search through their saved custom foods. Users can add custom foods via two entry points: the diary's Add Food button and the Custom Food tab. The main page should display a list of custom foods with both names and calorie values, and users should be able to search for foods efficiently. | • Custom food can be added from diary or Custom Food tab • Search field displays results matching search terms • Only one custom food can be selected at a time • No results message displayed if no matches found
NUTR-013 | Log custom meal directly without portion adjust step | Story | Done | P1 | Priya Nair | Sprint 5 | 5 | This story focuses on allowing users to log custom meals directly without going through the portion adjustment step. The goal is to streamline the process for users who frequently eat the same meals. Users will be able to select a custom meal from a list, and it will be logged with default nutrient values in one tap. This will enhance user experience by reducing the number of interactions required to log meals. | • User can connect to the custom meal database • User can search and select custom meals without portion adjustment
NUTR-014 | Supplement section toggle — persistent setting with discoverability | Story | Done | P1 | Kabir Sharma, Priya Nair | Sprint 5 | 8 | We need to implement a toggle for the supplement section that allows it to be enabled or disabled by the user. This section should be persistent across diary dates and should be discoverable for users who need it, such as pregnant women and biohackers. The design should ensure that the toggle is intuitive and does not clutter the UI unnecessarily. | • Supplement section appears only if enabled by the user • Users can add food under breakfast, lunch, dinner, and snacks, with supplements appearing under these sections when enabled • The toggle for the supplement section is easily accessible and intuitive • The supplement section remains persistent across diary dates unless explicitly disabled
NUTR-019 | Edit logged item portion size with pre-filled values | Story | Done | P1 | Priya Nair | Sprint 5 | 5 | This story focuses on allowing users to edit the portion size of logged food items in their diary. When a user clicks on a food item, the adjust portion page should open with the previously logged values pre-filled. Users can modify the serving amount and unit, and the updated nutrient values should reflect immediately in the food diary without a page reload. Additionally, we need to ensure that any changes apply only to the specific date and meal where the item was logged. | • User can click any logged food item to edit portion size • Previously logged portion size is pre-filled and visible • User can edit serving amount, serving unit, or both • Nutrient values update automatically after saving • Changes apply only to the specific date and meal section
NUTR-020 | Delete logged item with confirmation popup | Story | Done | P1 | Priya Nair | Sprint 5 | 5 | We need to implement a feature that allows users to delete logged food or recipe items from their diary with a confirmation popup. The deletion should be instant, and the diary must update without a page reload. Additionally, we need to ensure that if the user cancels the deletion, the item remains unchanged. This feature should enhance user experience by making it clear and efficient. | • User can select any logged item and delete it with confirmation. • Confirmation popup appears with the message: 'Are you sure you want to delete this item?' • Deletion completes within 1 second after confirmation. • Food diary updates instantly without page reload. • Delete icon is available next to each logged item. • If the user cancels, the item remains unchanged. • Deletion only affects the current user's diary for the selected date.
NUTR-021 | Recalculate totals instantly on add edit delete with debounce on slow devices | Story | Done | P0 | Priya Nair, Arjun Mehta | Sprint 5 | 8 | This story focuses on ensuring that the cumulative nutrient totals are recalculated immediately upon adding, editing, or deleting food items. The goal is to achieve this recalculation within one second, even on slower devices, without requiring any manual refresh from the user. We also need to ensure that the UI remains responsive and that all values maintain unit consistency. | • Cumulative total recalculates on food addition, deletion, or portion size change • Recalculated totals must reflect daily nutrient intake and goal comparison • Recalculation happens within 1 second after any action without manual refresh
NUTR-022 | Separate diary per date with date picker and timezone handling | Story | Done | P0 | Arjun Mehta, Priya Nair | Sprint 5 | 8 | This story focuses on implementing a date picker in the food diary header that allows users to switch between different diary dates. Each date should load the corresponding food diary, and the date picker must be synced with the analysis section. We also need to address timezone handling to ensure accurate logging of food items for Indian users. | • Food diary maintains a separate log for each calendar date • Date picker and analysis section are synced • Switching dates loads corresponding diary within 2 seconds • Logged food items are associated with exact date and meal section
NUTR-023 | Fresh empty diary on new day | Story | Done | P1 | Priya Nair | Sprint 5 | 3 | This story focuses on ensuring that the food diary resets correctly when a new day begins. The diary should display a fresh empty state with all target nutrient columns visible. We need to ensure that no food items from the previous day bleed into the current day's diary and that the transition between dates is seamless and efficient. | • When today's date is selected, the current day's food diary reflects all latest updates. • When a new day begins, the diary displays a fresh empty state with all target nutrient columns. • No food items from the previous day should appear in today's diary. • The empty diary must still show all selected nutrient columns. • Switching to a new date must occur within 2 seconds.
NUTR-024 | Auto-save all diary actions | Story | Done | P0 | Priya Nair | Sprint 5 | 5 | This story focuses on implementing an auto-save feature for the food diary entries in the app. Users should not have to worry about losing their entries when they log off, refresh, or navigate away from the diary. The system will automatically save entries as they are added, ensuring a seamless user experience. | • Food diary entries persist across log-offs and page refreshes • Nutrient settings remain intact even after navigating away
NUTR-025 | Edit food logs for past and future dates | Story | Done | P1 | Arjun Mehta, Priya Nair | Sprint 5 | 5 | This story allows users to log and edit their meals for past, current, and future dates. It ensures that the food diary displays accurate nutrient values and portion sizes for any selected date. The goal comparison feature will utilize the goal settings that were active on the specific date selected, ensuring accurate tracking of user progress. | • User can log meals for past, current, and future dates • Goal comparison reflects goals active on the selected date
NUTR-026 | Duplicate food warning for same meal same date | Story | Done | P2 | Priya Nair | Sprint 5 | 3 | We need to implement a duplicate food warning that prevents users from adding the same food to the same meal on the same date. This warning should be displayed in red and disappear after 3 seconds. It's crucial that the system allows the same food in different meals or on different dates, but blocks duplicates within the same meal on the same date. | • Warning shows in red when a duplicate food is detected in the same meal on the same date. • Warning disappears after 3 seconds. • Prevents duplicates only within the same meal on the same date.
CF-001 | Create custom food with name serving value and serving unit | Story | Done | P1 | Priya Nair, Arjun Mehta | Sprint 5 | 5 | This story involves creating a feature that allows users to add custom foods to their profiles. Users will be required to input a food name, serving value, and serving unit. All fields are mandatory, and the food name must adhere to specific character limits. The implementation will also ensure that each user can only access their own custom foods. | • Food name must be alphanumeric and a maximum of 30 characters. • Serving value must be an integer greater than 0. • Serving unit must be a free-text input.
CF-002 | Add macro and micronutrient values when creating custom food | Story | In Progress | P1 | Priya Nair, Arjun Mehta | Sprint 5 | 5 | This story aims to implement a nutrient entry step for users creating custom food items. Users will be able to fill in macro and micronutrient values, with calorie values being mandatory. The design will follow the accordion pattern established in GOAL-009 to enhance user experience and reduce overwhelm when entering multiple nutrients. | • Nutrient entry form includes three columns: Nutrient Category, Nutrient Name, Nutrient Value, and Default Unit. • Calorie value is mandatory and clearly marked with an asterisk. • Nutrient values must be in integer format and greater than 0. • Values persist across page refreshes and user sessions.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
NUTR-011 | 1 | Shristi Sharmistha | 2025-02-26 | The custom recipe source should work exactly like the USDA food database from NUTR-007, but it will pull from the user's saved custom recipes. Please reuse the search component pattern from NUTR-007 instead of building a new one.
NUTR-011 | 2 | Priya Nair | 2025-02-27 | I can confirm that I'll abstract the search component into a reusable component that accepts a data source prop. This way, custom recipe, custom food, and USDA can all utilize the same component. However, I want to note that the custom recipe database will be user-specific, while USDA is shared. The API endpoint for custom recipes will include a user_id filter.
NUTR-011 | 3 | Priya Nair | 2025-03-02 | I've completed the implementation. Just a heads up, custom recipes are not creatable in this sprint, so the recipe menu page will show an empty state with the message 'No custom recipes created yet' for now. Recipe creation is planned for V2.
NUTR-011 | 4 | Shristi Sharmistha | 2025-03-03 | I verified that the empty state shows correctly and the source switch clears the search results. The 'no results' message displays as expected, and the redirect to the adjust portion page is instant. Everything looks good, so I will close this ticket now.
NUTR-012 | 1 | Shristi Sharmistha | 2025-02-26 | Let's ensure that the Add button on the custom food main page links correctly to CF-001 for creating new custom foods. This is a key difference from the custom recipe flow.
NUTR-012 | 2 | Priya Nair | 2025-02-27 | The Add button linking to CF-001 is confirmed. Additionally, the custom food main page will display both food names and calorie values in a two-column format. Should we clarify how the calorie values are displayed? Should it be just the number or include units like '250 kcal'?
NUTR-012 | 3 | Shristi Sharmistha | 2025-02-28 | The calorie display format should be '250 kcal' for clarity. Also, remember that users cannot edit custom foods while adding them through the diary flow; they can only edit from the Custom Food tab.
NUTR-012 | 4 | Priya Nair | 2025-03-03 | I've implemented the two entry points and confirmed that the two-column list with names and calorie values is working correctly. The Add button links to CF-001, and editing is blocked during the diary add flow. One edge case to consider: if a user switches the source or navigates away, we need to ensure that the search input is cleared. This aligns with the PRD requirements. Closing the ticket now.
NUTR-013 | 1 | Shristi Sharmistha | 2025-02-26 | For this story, we need to ensure that when a user selects a custom meal from the breakfast section, it logs directly to breakfast without needing to select the meal type again. Can you confirm this behavior?
NUTR-013 | 2 | Priya Nair | 2025-02-27 | Yes, the meal type will be inherited from where the user initiates the add. If they tap 'Add' in the breakfast section, it will log to breakfast. However, if they navigate from the food database, they will need to select the meal type first. This two-path behavior is consistent with our other sources.
NUTR-013 | 3 | Priya Nair | 2025-03-01 | I've implemented the logging functionality. In the diary view, the custom meal shows as a single row with the meal name and combined nutrient totals. Individual ingredients are hidden as per the PRD. Users can view ingredients in the custom meal management section, which is a V2 feature. I also caught an edge case: if a user tries to log a custom meal that has been deleted, we need to handle that gracefully to prevent errors.
NUTR-013 | 4 | Shristi Sharmistha | 2025-03-04 | I verified the implementation. The custom meal logs instantly with the correct nutrient totals and appears as a single row in the diary. The nutrient values match those set during meal creation, and the entire process requires no more than 3 interactions. This meets the PRD requirements. Closing the ticket.
NUTR-014 | 1 | Shristi Sharmistha | 2025-02-26 | Let's start with the design for the supplement section toggle. It should be hidden by default and enabled via user settings or diary preferences. Once enabled, it should show as a 4th section in the diary. Kabir, can you work on the toggle placement and the visual treatment?
NUTR-014 | 2 | Kabir Sharma | 2025-02-27 | I've created an initial Figma design where the supplement toggle is in the diary settings, completely hidden when off. However, I’m concerned that if it's hidden, users who need it—like pregnant women tracking folate—won't discover it. This could lead to a significant usability issue.
NUTR-014 | 3 | Ananya Iyer | 2025-02-28 | I completely agree, Kabir. From my conversations with potential users, tracking supplements is a major reason they choose Nutrivana. If they can't find this feature, it undermines our marketing message. We should consider making it more visible even when it's off.
NUTR-014 | 4 | Shristi Sharmistha | 2025-03-01 | Kabir, can you design three options for us to evaluate? Option A: completely hidden, discovered only via settings. Option B: always visible in the diary as a greyed-out section with a message to enable tracking. Option C: a persistent prompt that appears until the user makes a choice.
NUTR-014 | 5 | Kabir Sharma | 2025-03-02 | I've mocked up the three options. Option A is clean but has no discoverability. Option B adds clutter for users who don't need supplements. Option C, the dismissible prompt, seems to balance discoverability and UI cleanliness. I recommend we go with Option C.
NUTR-014 | 6 | Shristi Sharmistha | 2025-03-03 | Let's proceed with Option C. This way, users who need supplements will see the prompt, while others can dismiss it permanently. I'll update the PRD to reflect this decision. Kabir, please update the Figma accordingly.
NUTR-014 | 7 | Kabir Sharma | 2025-03-05 | I've updated the Figma. The dismissible prompt now appears below the snacks section with a clear CTA to enable supplement tracking. When enabled, the supplement section will show as the 4th section. When dismissed, the diary will show a clean 3-section view.
NUTR-014 | 8 | Priya Nair | 2025-03-09 | I've implemented the toggle logic and confirmed that the supplement section appears as expected. The prompt is visible for new users and can be dismissed permanently. I also tested the logging functionality, and it works seamlessly across diary dates. Closing this ticket now, but we should note that the PRD will be updated to reflect the implementation of Option C.
NUTR-019 | 1 | Shristi Sharmistha | 2025-02-28 | When a user clicks a logged food item, the adjust portion page should reopen with pre-filled values. Can you confirm how we will preserve the original values for restoration on cancel?
NUTR-019 | 2 | Priya Nair | 2025-03-01 | I plan to use a separate React state variable called editingOriginalValues to store the original logged values when entering edit mode. This way, if the user cancels or navigates back, we can reset the form state from editingOriginalValues. On confirming, we'll update the food_log record using a PATCH API call.
NUTR-019 | 3 | Priya Nair | 2025-03-03 | One edge case to consider: if a user edits the portion size for January 15, does this change affect other dates where the same food is logged? We need to ensure that the edit only applies to that specific entry.
NUTR-019 | 4 | Shristi Sharmistha | 2025-03-05 | Yes, the edit should apply only to the specific food log entry on that date. Each entry is independent. The PATCH /food-logs/{id} endpoint will update only the record by ID, not others. This aligns with our PRD requirements, so we can close the ticket.
NUTR-020 | 1 | Shristi Sharmistha | 2025-02-28 | For the delete functionality, should we implement an optimistic UI update where the item is removed immediately from the diary upon confirmation? This would align with our goal of making the deletion feel instant as per the PRD.
NUTR-020 | 2 | Priya Nair | 2025-03-01 | I recommend we go with the optimistic deletion approach. We can remove the item from the UI immediately after the user confirms, and then send a DELETE request to the API. If the API fails, we can re-add the item to the UI and show an error toast. This ensures a smooth user experience and meets the PRD requirement for instant feedback.
NUTR-020 | 3 | Priya Nair | 2025-03-02 | I've confirmed that the deletion will only affect the specific food_log record by ID, ensuring user data isolation at the Supabase RLS level. This means other users won't be able to delete each other's entries, which is crucial for data integrity.
NUTR-020 | 4 | Shristi Sharmistha | 2025-03-04 | I tested the implementation, and the delete icon is visible next to each item. The confirmation popup appears as expected. When I confirm, the item is removed instantly from the UI, and the totals update correctly. I also tested rapid deletion of multiple items, and everything updates correctly. I think we can close this ticket.
NUTR-021 | 1 | Shristi Sharmistha | 2025-02-26 | Let's ensure the recalculation fires on every add, edit, and delete action. It should happen within 1 second and no manual refresh should be needed. Priya, can you test this on a low-end device to confirm performance?
NUTR-021 | 2 | Priya Nair | 2025-02-27 | I've implemented the recalculation using the client-side calculation engine from NUTR-TASK-004. It fires on every food log state change. However, I noticed a performance issue when rapidly adding multiple foods. If a user taps 'Add' 5 times in 3 seconds, it causes a lag of about 750ms due to multiple recalculations stacking. This could be problematic for users with many tracked nutrients.
NUTR-021 | 3 | Arjun Mehta | 2025-02-28 | The lag you mentioned is concerning. Debouncing the calculation could help by batching rapid additions into one calculation instead of multiple. However, does this approach violate the PRD requirement for instant recalculation?
NUTR-021 | 4 | Shristi Sharmistha | 2025-03-01 | The PRD states that nutrient recalculation must happen within 1 second after an action. A 200ms debounce means the calculation fires 200ms after the last action, which is compliant with the PRD since it still achieves the final state within 1 second. I think we can proceed with the debounce approach.
NUTR-021 | 5 | Arjun Mehta | 2025-03-02 | Great, but we need to decide on the debounce timing. If it's too short, rapid additions might still trigger multiple calculations. If it's too long, single actions could feel sluggish. What do you think about a 100ms debounce?
NUTR-021 | 6 | Priya Nair | 2025-03-03 | I implemented the 100ms debounce on the calculation engine. After testing on the mid-range device, 5 rapid additions now trigger only 2-3 calculations instead of 5, and the UI settles within 300ms. This feels responsive while still being compliant with the 1 second requirement.
NUTR-021 | 7 | Shristi Sharmistha | 2025-03-04 | I verified the implementation on both fast and slow interaction patterns. A single food addition is instant, and 5 rapid additions settle within 300ms. Edits and deletes also recalculate within 200ms. Everything is within the 1 second limit. Looks good to close!
NUTR-021 | 8 | Arjun Mehta | 2025-03-10 | All tests confirm that the recalculation meets the PRD requirements. The debounce implementation is working well, and the performance on both low-end and mid-range devices is satisfactory. Closing this ticket!
NUTR-022 | 1 | Shristi Sharmistha | 2025-02-26 | For the date picker implementation, can we confirm that the goal_snapshots approach from NUTR-TASK-003 will allow each diary date to fetch the correct goal settings active on that date?
NUTR-022 | 2 | Arjun Mehta | 2025-02-27 | We need to address a critical timezone issue. If a user in Mumbai logs food at 11:30pm IST, it gets stored as 'February 26' in UTC. However, after midnight IST, the local date changes to 'February 27' while UTC still shows 'February 26'. This could lead to confusion for users logging food after midnight.
NUTR-022 | 3 | Priya Nair | 2025-02-28 | This seems similar to the issue we flagged in NUTR-TASK-003. Should we store dates in UTC and calculate the offset on display, or is it better to store them in the user's local timezone?
NUTR-022 | 4 | Arjun Mehta | 2025-03-01 | I propose two options: Option A is to store in UTC and apply timezone offsets for every query, which requires storing the user's timezone. Option B is to store the date as a local date string (YYYY-MM-DD) in their timezone. This is simpler and avoids offset calculations.
NUTR-022 | 5 | Shristi Sharmistha | 2025-03-02 | If we expand internationally, would Option B lead to inconsistent date representations in the database? Is it future-proof?
NUTR-022 | 6 | Arjun Mehta | 2025-03-03 | I recommend Option B for V1 with a migration path. We can store both the local date_string and UTC timestamp. For V1, all queries will use the local date_string, and in V2, if we expand internationally, the UTC timestamp will be available for migration.
NUTR-022 | 7 | Priya Nair | 2025-03-04 | I will implement the date picker using the user's local date. I will also test the midnight edge case where food is logged at 11:55pm on February 26 and 12:05am on February 27 to ensure they appear on the correct diary dates.
NUTR-022 | 8 | Shristi Sharmistha | 2025-03-10 | I verified that switching between dates shows the correct history for past dates, an empty diary for future dates, and the current day's diary correctly. The date picker is synced with the analysis section and switching dates loads within 2 seconds. Closing this ticket.
NUTR-023 | 1 | Priya Nair | 2025-03-01 | I implemented the new-day reset logic, and it seems to be working as expected. The diary component reads the current local date from NUTR-022's date system. Each diary page load fetches food_logs for the current date_string, ensuring that the diary shows clean columns with no food items. However, I noticed that if the user switches back to the previous day too quickly, it might still show the previous day's food due to caching. We should consider adding a cache invalidation step to ensure data accuracy.
NUTR-023 | 2 | Shristi Sharmistha | 2025-03-02 | I verified the implementation by manually setting the device date forward. The diary correctly shows an empty state with all nutrient columns from current goals. However, I realized that the PRD states that the empty diary should reflect the selected nutrient columns, but we should clarify that it should also reflect the user's current goals. Let's update the PRD to specify that the nutrient columns should be based on the user's goals to avoid any confusion.
NUTR-024 | 1 | Priya Nair | 2025-02-28 | I've implemented the auto-save functionality using the optimistic update pattern from NUTR-010. Every action (add/edit/delete) now immediately calls the API endpoint '/api/diary/save' to persist data in Supabase. However, I noticed that if a user tries to add a food item while offline, it throws an error instead of queuing the action. We should handle this edge case by queuing the action and notifying the user once they're back online.
NUTR-024 | 2 | Priya Nair | 2025-03-02 | I also realized that the PRD states the nutrient should remain set when the user logs off, but it doesn't specify that this should apply to all diary entries. We need to clarify that the nutrient settings should be saved per entry, not just globally. This will ensure that users can have different nutrients for different diary entries, enhancing the app's flexibility.
NUTR-025 | 1 | Arjun Mehta | 2025-03-01 | The backend is set up to support any date editing. The food_logs queries filter by user_id and date_string, so both past and future dates will work with the same API endpoints. However, we should ensure that the date picker in the frontend doesn't allow users to select dates beyond a certain range, say 30 days into the future, to avoid confusion.
NUTR-025 | 2 | Priya Nair | 2025-03-02 | I tested logging meals for both past and future dates, and everything persisted correctly. However, I noticed that if a user tries to log a meal on a date that is more than 30 days in the future, it should display a warning message. Also, we need to clarify in the PRD that the goal comparison must use the goal settings active on that specific date, as this wasn't explicitly mentioned.
NUTR-026 | 1 | Priya Nair | 2025-03-01 | I've implemented the duplicate check on the adjust portion page. It checks the food_logs for the same food_id, meal_type, and date_string combination. If a duplicate is found, a red warning appears below the Add button stating, 'This food is already in your breakfast. Add again anyway?' However, I need clarification on whether to block the addition entirely or allow the user to override it. What do you think?
NUTR-026 | 2 | Shristi Sharmistha | 2025-03-02 | The PRD specifies that the same food cannot be part of the same meal again on the same date, so we should block the addition entirely with a warning. The warning should disappear after 3 seconds. I've verified that the warning shows correctly for duplicates and disappears as expected. However, we need to note that the current implementation only checks for USDA food_id and does not trigger for custom food sources. This will be addressed in NUTR-BUG-002 in Sprint 8.
CF-001 | 1 | Shristi Sharmistha | 2025-02-28 | We need to ensure that the custom_foods table in Supabase has a user_id foreign key to restrict access to the logged-in user. Can you confirm this design, Arjun?
CF-001 | 2 | Arjun Mehta | 2025-03-01 | The custom_foods table is designed with a user_id foreign key. Supabase RLS policy will restrict users to their own foods. The food name will be enforced as VARCHAR(30) at the database level, and the serving value will be stored as DECIMAL(10,2) to accommodate fractional servings.
CF-001 | 3 | Priya Nair | 2025-03-02 | I've implemented the create form with real-time validation. The food name input shows a character counter. However, I need clarification on the serving unit input — should it be a free-text field or a dropdown?
CF-001 | 4 | Shristi Sharmistha | 2025-03-03 | The serving unit should be a free-text field as per the PRD, allowing users to enter any unit they want. This is different from USDA foods, which use predefined units. Make sure to include a placeholder like 'e.g. cup, glass, gram' in the input.
CF-002 | 1 | Shristi Sharmistha | 2025-02-28 | For the nutrient entry, can we confirm if we're using the same nutrient list from GOAL-SPIKE-002? I want to ensure we're aligned on the source.
CF-002 | 2 | Arjun Mehta | 2025-03-01 | Yes, we're using the nutrient list from GOAL-SPIKE-002 along with the nutrient_list Excel file. All nutrients tracked by Nutrivana will be available for user input. However, we should ensure that the unit column is system-defined and not editable. Also, we need to consider the edge case where users might enter nutrient values in a non-integer format, which should trigger a validation error.
CF-002 | 3 | Priya Nair | 2025-03-03 | I've implemented the nutrient entry form with dynamic input fields based on the nutrient reference list. The calorie field is mandatory with validation in place. I'm concerned about UX, though; displaying all 30+ nutrients at once might overwhelm users. Should we group them by category (calories, macros, vitamins, minerals) using the accordion pattern from GOAL-009?
CF-002 | 4 | Shristi Sharmistha | 2025-03-05 | I approve the accordion grouping approach. It aligns well with the micro-selection pattern we established in GOAL-009. Also, let's ensure that values are saved incrementally as users enter each field to prevent data loss. This will help us address the potential issue of users navigating away from the form before completing it.