## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
CF-003 | Save custom food with mandatory field validation and zero calorie edge case | Story | Done | P0 | Priya Nair, Arjun Mehta | Sprint 6 | 8 | This story focuses on implementing the save functionality for custom food entries, ensuring all mandatory fields are validated before saving. A critical edge case regarding zero-calorie foods has been identified, which requires a review of the PRD specifications to ensure accuracy in the app's nutritional logging. | • Save button must be present to confirm food is saved • Once saved Add button appears to directly add from create page • Once saved no field can be edited • Food saved only if all mandatory fields filled — food name, serving size, AND calorie • Food once saved can only be accessed by the logged-in user who created it • If mandatory field not filled — show message 'please enter mandatory field' with field highlighted • If input not in correct format — do not allow save • Once saved: if user goes back or navigates away, refreshes or re-logs in, same value should be present • If NOT saved and user navigates away — input value is discarded • On going back after saving — navigate to custom food menu page • Once saved user stays on create custom food page (does not redirect away) • The input field should be a number format like 20.0 or 0.5 and ≥ 0 • Calorie value is mandatory to be filled
CF-004 | Search and select custom food from list on menu page | Story | Done | P1 | Priya Nair | Sprint 6 | 5 | The custom food menu page allows users to search and select from a list of saved custom foods. It includes a search field, a create button, and displays the calorie values of each food. The layout consists of two columns: Custom Food and Calorie, with an add icon next to each food item for easy selection. | • Custom food menu page displays a list of saved custom food names and their calorie values. • Search field allows for partial and full matches of custom food names.
CF-005 | Edit custom food — name serving size nutrients with retroactive date logic | Story | In Progress | P1 | Priya Nair, Arjun Mehta | Sprint 6 | 5 | This story focuses on allowing users to edit custom food entries in the app. Users should be able to click on a food item in the main menu to edit its name, serving size, and nutrient values. The changes made should only reflect from the day of the edit, ensuring that past entries remain unchanged. Additionally, we need to ensure that unsaved edits persist even if the user navigates away from the page. | • User can edit custom food name, serving size, and nutrient values. • Unsaved edits persist on navigation away from the edit page.
CF-006 | Delete custom food with confirmation popup | Story | Done | P2 | Priya Nair | Sprint 6 | 5 | We need to implement a feature that allows users to delete custom food entries with a confirmation popup. The delete icon should be present beside each custom food item on the menu page. The confirmation popup will ask users if they really want to delete the food, and if they confirm, the food record will be removed from their account. If they cancel, they should remain on the menu page. | • Delete icon present beside each custom food on menu page • Confirmation popup appears on delete action with delete and cancel options
CF-007 | Retroactive change reflects from edit date only — effective date versioning | Story | Done | P1 | Arjun Mehta | Sprint 6 | 5 | This story focuses on implementing effective date versioning for custom foods in our app. When users edit their custom food entries, the changes should only take effect from the date of the edit, while past entries should retain their original nutrient values. This ensures accurate tracking of dietary intake over time. | • Changes to custom food reflect from the date of edit. • Past diary entries retain original nutrient values.
AN-001 | Per nutrient analysis screen with ordered categories and separate screens | Story | Done | P1 | Kabir Sharma, Priya Nair | Sprint 6 | 5 | This story focuses on designing the nutrient analysis section of the app, where each tracked nutrient will have its own screen. The order of nutrients needs to follow a specific hierarchy: calories first, followed by macros and micros in alphabetical order. The navigation should feel intuitive and responsive, enhancing the user experience while analyzing their nutrient intake. | • Each nutrient has a dedicated screen with graphical analysis. • Nutrients are ordered: Calorie → Macros → Micros. • Category labels are clearly visible. • All sub-nutrients are displayed under their respective parent nutrient. • Analysis reflects only the current or selected date.
AN-002 | Daily bar graph actual vs target — user testing reveals fundamental label confusion | Story | Done | P0 | Kabir Sharma, Priya Nair, Ananya Iyer | Sprint 6 | 8 | User testing has revealed that the current bar graph design, which represents actual consumption as a percentage of the target, is fundamentally confusing. Users misinterpret the full bar as what they have consumed, leading to incorrect conclusions about their intake. We need to address this confusion urgently before the MVP launch. | • Bar graph displays actual nutrient consumed, target nutrient, and remaining amount clearly. • Percentage displayed inside the bar and in bold text below. • Label indicates 'left' or 'over' based on actual vs target.
AN-003 | Color coding yellow green red for all nutrients with weight goal type logic | Story | In Progress | P0 | Kabir Sharma, Priya Nair | Sprint 6 | 5 | This story focuses on implementing a color coding system for nutrients based on users' weight goals. The logic will apply different colors (yellow, green, red) depending on whether the actual intake meets, exceeds, or falls short of the target. It is crucial that this system is consistent with the existing food diary color coding to ensure a seamless user experience. | • Color coding must match the logic defined in the PRD for all nutrients. • Colors must update dynamically as users log their food.
AN-004 | 7-day trend graph showing adherence over last 7 days | Story | In Progress | P1 | Arjun Mehta, Priya Nair | Sprint 6 | 5 | We need to implement a 7-day trend graph that shows adherence over the last week based on user food logs. The PRD is incomplete, so we need to clarify the data to be displayed and the type of chart to use. This will help users visualize their adherence to nutritional goals effectively. | • Trend shows actual and target percentages for each of the last 7 days. • Days with no food logged are displayed as 0%.
AN-005 | Date picker synced between food diary and analysis section | Story | Done | P1 | Priya Nair | Sprint 6 | 5 | We need to implement a shared date picker that syncs between the food diary and analysis sections of the app. This will allow users to change the date in either section and have the other section update automatically. Additionally, the analysis section should show nutrient consumption for the selected date and a 7-day trend that includes the selected date and the six days prior. | • Same calendar picker used for both food diary and analysis • The analysis shows nutrient consumed for the selected date • 7-day trend shows selected date and 6 days before it • Changing date in food diary updates analysis view • Changing date in analysis updates food diary view
TECH-004 | Performance testing — all search and load operations under 1 second | Task | Done | P0 | Arjun Mehta | Sprint 6 | 5 | We need to ensure that all search and load operations meet the specified performance requirements outlined in the PRD. This includes testing the speed of search results, food database loading, and analysis rendering. The goal is to optimize our operations to provide a seamless user experience. | • Search results displayed within 1 second of user input • Food database appears instantly when user adds food in diary • Redirect to adjust portion page happens instantly after food selection • Bar graph loads within 2 seconds of navigating to analysis • Updates to analysis after food add/remove render within 1 second • Nutrient recalculation within 1 second • Meal type selection responds instantly • Switching diary dates loads within 2 seconds • Deletion completes within 1 second
TECH-006 | Auto-save implementation verification across all diary actions | Task | Done | P0 | Arjun Mehta, Priya Nair | Sprint 6 | 5 | We need to ensure that the auto-save functionality for the food diary is working seamlessly across all actions. This includes persisting entries across logouts, refreshes, and navigations. We must confirm that the cumulative total updates instantly and that no data is lost during any action. This verification is crucial for the MVP launch. | • Food diary entries persist across logout, refresh, and navigation. • All diary actions auto-save without a manual save button. • Cumulative total updates instantly without loading. • Nutrients remain set even after logout or refresh.
TECH-007 | Date-timezone handling — IST offset storage verification | Task | Done | P0 | Arjun Mehta | Sprint 6 | 5 | This task focuses on verifying the implementation of IST timezone handling for date-sensitive operations in the app. We need to ensure that food diary entries are accurately logged and displayed according to the local date, especially around the midnight edge case. It's crucial to confirm that switching between dates works seamlessly as per PRD requirements. | • Food diary maintains a separate log for each calendar date • Food items are associated with the exact date when saved • Date switching loads within 2 seconds • Same date picker is used for food diary and analysis

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
CF-003 | 1 | Shristi Sharmistha | 2025-03-12 | We need to ensure that the save button validates all mandatory fields (food name, serving size, calorie) before saving. After a successful save, the Add button should appear on the same page. Let's make sure all fields become read-only after saving.
CF-003 | 2 | Priya Nair | 2025-03-13 | I've implemented the save validation. The food name and serving size are required and must be > 0, and calorie is also required. I've tested these scenarios and they pass, but I encountered an edge case during internal testing.
CF-003 | 3 | Priya Nair | 2025-03-14 | When I tried entering 0 in the calorie field for black coffee, it was rejected. The PRD states calorie is mandatory and the input field description says '> 0'. However, black coffee has 0 calories, which raises a conflict. We need to address this.
CF-003 | 4 | Shristi Sharmistha | 2025-03-15 | The PRD states the input field format is '> 0', but zero-calorie foods like black coffee and plain water are real. If we block zero, the app becomes inaccurate. This needs to be clarified in the PRD as accuracy is crucial for a health app.
CF-003 | 5 | Arjun Mehta | 2025-03-16 | From a technical perspective, 0 is valid as a stored value in our DECIMAL(10,2) column. The '> 0' requirement was likely meant to prevent negative values and empty submissions. I propose we allow 0 as a valid calorie input.
CF-003 | 6 | Priya Nair | 2025-03-17 | If we allow 0 calories, should we consider other nutrient fields? The PRD states all nutrient input fields should be '> 0'. For example, some foods could have 0mg cholesterol or 0g fat. We need to decide on this.
CF-003 | 7 | Shristi Sharmistha | 2025-03-18 | Let's allow 0 for all nutrient fields, including calories. The '> 0' in the PRD was poorly worded and meant to prevent empty fields and negative values. I will update the PRD to '≥ 0 (empty is not valid, negative is not valid, zero is valid).' Arjun, can you confirm this won't break any downstream calculations?
CF-003 | 8 | Arjun Mehta | 2025-03-19 | The calculation engine handles 0 nutrient values correctly, treating them as 0 in sums. This aligns with how USDA data is managed, which includes many foods with 0 values for certain nutrients. I will update the validation logic to allow ≥ 0, and Priya, please adjust the frontend validation accordingly.
CF-003 | 9 | Shristi Sharmistha | 2025-03-20 | I verified the implementation by saving a custom food 'Black Coffee' with 0 calories, 0g fat, 0g carbs, and 0mg sodium. It saved successfully, the Add button appeared, and all fields became read-only. I checked navigation and values persisted correctly. Closing the ticket.
CF-004 | 1 | Shristi Sharmistha | 2025-03-12 | Let's ensure the search functionality uses the same reusable component from NUTR-011. The data source should be the custom_foods table, filtered by user_id for RLS. Can you confirm this?
CF-004 | 2 | Priya Nair | 2025-03-13 | I can confirm that we will reuse the search component from NUTR-011. The search will query the custom_foods table filtered by user_id. One difference is that we will display the calorie value in the second column. Also, I’ll ensure the Create button links to CF-001 for creating new custom foods.
CF-004 | 3 | Priya Nair | 2025-03-15 | I’ve implemented the add icon next to each food item, which provides an additional way to initiate logging. Both selecting from the search and clicking the add icon will redirect to the adjust portion page. The list is sorted alphabetically by food name by default for better usability.
CF-004 | 4 | Shristi Sharmistha | 2025-03-17 | I verified the implementation. The list shows names and calories correctly, and the search works with partial names. Both the add icon and the Create button function as intended. However, we need to ensure that if a user searches for a food that doesn’t exist, they receive a clear message instead of an empty list. Closing this ticket now.
CF-005 | 1 | Shristi Sharmistha | 2025-03-12 | The edit functionality should work similarly to the creation process, but with pre-filled values. We need to clarify how CF-007 connects to this ticket since both involve date-aware changes. Can you explain how the backend logic will support this?
CF-005 | 2 | Arjun Mehta | 2025-03-13 | CF-005 is focused on the user-facing edit flow, while CF-007 will handle the backend logic for retroactive changes. We can test CF-005 independently since the UI doesn't depend on the backend logic. The effective_date will be crucial for ensuring that changes only affect diary entries from the edit date onwards.
CF-005 | 3 | Priya Nair | 2025-03-15 | I've implemented the edit form that pre-fills all fields from the current custom food record. However, I need clarification on whether unsaved edits should persist if the user navigates away. The PRD states that this behavior is different from the creation flow where unsaved inputs are discarded.
CF-005 | 4 | Shristi Sharmistha | 2025-03-18 | Yes, the PRD explicitly states that unsaved edits should persist in edit mode. This is intentional to accommodate users who have already invested time in creating the food item. Please implement a way to auto-save the draft state of the edits. Also, we should ensure that the effective_date logic from CF-007 is working correctly to prevent any past entries from being affected.
CF-006 | 1 | Priya Nair | 2025-03-15 | I implemented the delete functionality with a confirmation popup as per the pattern from NUTR-020. The delete icon appears next to each custom food item. However, the PRD states that if the user cancels, they should be redirected to the create custom food page. This seems unusual to me since it deviates from the expected behavior. Can we confirm if this is indeed an error?
CF-006 | 2 | Shristi Sharmistha | 2025-03-16 | After reviewing the PRD, I agree that the redirect to the create custom food page on cancel is not consistent with user expectations. We should keep the user on the menu page instead. I will document this as an intentional deviation from the PRD. Also, regarding the soft delete, Arjun confirmed that the past diary entries should remain intact, which is crucial to avoid losing data. We need to ensure that the deleted_at timestamp is set correctly to filter out the deleted custom food from the menu.
CF-007 | 1 | Arjun Mehta | 2025-03-15 | I've implemented the effective_date versioning by creating a custom_food_versions table. Each time a user edits a custom food, a new row is inserted with the current date as effective_date. However, I noticed that if a user edits the same food multiple times on the same day, we need to ensure that only the latest edit is reflected. We might need to add a check to prevent duplicate entries for the same effective date.
CF-007 | 2 | Shristi Sharmistha | 2025-03-20 | I tested the changes with a custom food entry and confirmed that the versioning works as expected. However, I realized that the PRD states we should also consider how this affects users who might edit their entries at the end of the day. For instance, if a user logs an entry at 11:59 PM and edits it at 12:01 AM, the transition between days might cause confusion. We should clarify in the PRD that the effective date should always reflect the date of the edit, regardless of the time.
AN-001 | 1 | Shristi Sharmistha | 2025-03-12 | Let's structure the analysis section so that each nutrient has its own screen. The order should be calorie first, followed by macros and then micros. Kabir, can you design the navigation between these screens? Should we go for horizontal swipe, vertical scroll, or tab navigation?
AN-001 | 2 | Kabir Sharma | 2025-03-13 | I've created a Figma design proposing horizontal swipe navigation between nutrient screens. Each screen will have a nutrient name indicator at the top. This feels natural for mobile, allowing users to swipe left/right to browse nutrients. Priya, is this a single scrollable component or separate routes for each nutrient?
AN-001 | 3 | Priya Nair | 2025-03-15 | I think a single component with swipe gestures is the best approach. If we route to a new URL for each nutrient, it could slow down transitions and disrupt the swipe animation. We should pre-render all nutrients but only display the current one. Also, we need to ensure that the analysis reflects the selected date from the food diary. An edge case to consider is if a user tries to swipe when there are no nutrients logged for the selected date.
AN-001 | 4 | Kabir Sharma | 2025-03-18 | I agree with the carousel approach for performance. I've implemented the swipe navigation with category section headers. The order is calorie first, then macros alphabetically (carbohydrate, fat, protein), followed by micros. Also, we need to clarify in the PRD that the analysis cannot be changed manually and will only update based on food diary entries. Closing this ticket once we verify everything works as intended.
AN-002 | 1 | Shristi Sharmistha | 2025-03-12 | The bar graph design needs to clearly show the actual consumption versus the target. Kabir, can you ensure that the design includes all required display elements such as actual, target, percentage, and remaining amount?
AN-002 | 2 | Kabir Sharma | 2025-03-13 | I've implemented the bar graph design in Figma. The colored part represents actual consumption, while the whole bar is the target. I’ll share it with Ananya for feedback before we proceed.
AN-002 | 3 | Ananya Iyer | 2025-03-15 | After testing with 5 users, 4 misread the graph entirely. They think the full bar indicates what they have eaten, not what remains. One user even said they felt done for the day after consuming only 75% of their target. We need to address this confusion immediately.
AN-002 | 4 | Kabir Sharma | 2025-03-16 | This feedback is concerning. The design follows the PRD, but users expect a fill-up progress bar. I propose three options to fix this: A) Add clearer labels, B) Invert the visual, or C) Keep the current design but add explicit numbers. I recommend Option C for the MVP.
AN-002 | 5 | Shristi Sharmistha | 2025-03-17 | I agree that Option C is the best interim solution given our timeline. However, we need to ensure the text labels are bold and the percentage is clearly visible. Can we confirm the exact placement of these elements?
AN-002 | 6 | Priya Nair | 2025-03-19 | I’ll implement Option C changes with the percentage displayed inside the bar and bold text below showing 'Xg consumed / Xg target, Xg remaining.' This should clarify the confusion. We should also test this with users again.
AN-002 | 7 | Ananya Iyer | 2025-03-25 | I tested the updated graph with 3 users, and all understood it correctly with the new labels. This is a significant improvement. We should still document a follow-up for a more comprehensive redesign.
AN-002 | 8 | Shristi Sharmistha | 2025-03-28 | Great to hear the testing went well. I’ll close this ticket and create a follow-up (AN-CR-001) for the full redesign post-beta. Let's ensure the team is aware of the confusion around the bar direction for future iterations.
AN-003 | 1 | Shristi Sharmistha | 2025-03-14 | The color logic for the analysis bar should mirror the food diary's color coding from NUTR-017. Can you confirm that the same rules apply for consistency? Users should see identical colors for the same nutrient status.
AN-003 | 2 | Kabir Sharma | 2025-03-15 | Yes, the color rules are consistent with NUTR-017. One key detail is that the color of the bar segment is dynamic and changes as the user logs food. For example, it starts at yellow (0%), transitions to yellow at 50%, green at 100%, and red above MAX. Priya, ensure the color recalculates correctly on every diary update.
AN-003 | 3 | Priya Nair | 2025-03-16 | I've implemented the color logic by reusing the color calculation function from NUTR-017, which is a good architectural choice for maintaining a single source of truth. The analysis component will now subscribe to food log state changes to update colors automatically. However, I noticed that if a user logs food that exceeds the maximum target, we need to ensure it doesn't incorrectly revert to yellow at 100% due to rounding issues.
AN-003 | 4 | Shristi Sharmistha | 2025-03-17 | I verified the color cases: calorie under target (yellow), calorie at target (green), calorie over target for weight loss (red), and calorie over target for weight maintenance (yellow, not red). Also, for vitamins, if Vitamin C is under RDA, it should be yellow, at RDA green, and over MAX red. Please remember that AN-BUG-004 will affect this logic, so we need to keep that in mind as we close this ticket.
AN-004 | 1 | Shristi Sharmistha | 2025-03-14 | Arjun, the PRD is incomplete with the note to 'discuss with developer and then write.' Can we clarify what data the trend should show? Also, what chart type do you think would be best for this?
AN-004 | 2 | Arjun Mehta | 2025-03-15 | I suggest we use a line chart showing the actual and target percentages for each of the 7 days. The X-axis would represent the dates, while the Y-axis could range from 0% to 150% to accommodate over-target days. Each nutrient can have its own trend line. We should also ensure that days with no food logged show as 0% to avoid confusion.
AN-004 | 3 | Priya Nair | 2025-03-18 | I've started implementing the frontend for the trend graph using the charting library. The backend will need an endpoint that queries the food_logs for user_id and the 7-day date range. We should aggregate the nutrient totals per date and return an array of {date, actual, target, percentage}. Also, we should handle an edge case where users might select a date without any logs in the last week.
AN-004 | 4 | Shristi Sharmistha | 2025-03-20 | That sounds good, Priya. Just to clarify, we need to ensure that switching the selected date updates the trend correctly. For example, selecting March 31 should show data from March 25-31. I’ll update the PRD to reflect this behavior. Also, let’s keep in mind that AN-BUG-001 will affect how we display 0% for days with no logs, so we need to test that thoroughly.
AN-005 | 1 | Shristi Sharmistha | 2025-03-17 | For the shared date picker, should we use a React Context to manage the selected date state? This way, both the food diary and analysis can react to changes in the date seamlessly.
AN-005 | 2 | Priya Nair | 2025-03-18 | Yes, I suggest lifting the selected_date state up to the app-level Context, similar to the FoodDiaryContext from NUTR-BUG-001. This allows both components to subscribe to the same selected_date. When either component changes the date, it will update the Context and trigger a re-render.
AN-005 | 3 | Priya Nair | 2025-03-21 | I've implemented the shared date picker component. The date changes are propagating via Context as expected. However, I noticed that if the user selects a date that falls on a weekend, the 7-day trend doesn't display correctly. We need to ensure that the trend still shows the previous six days, even if they include weekends.
AN-005 | 4 | Shristi Sharmistha | 2025-03-22 | I tested the functionality and confirmed that changing the date in either the food diary or analysis updates the other section correctly. The 7-day trend also shifts as intended. Just a note: the PRD states that the analysis should show nutrient consumed for the selected date, but we also need to ensure that it handles edge cases like no data available for that date. Closing this ticket now.
TECH-004 | 1 | Arjun Mehta | 2025-03-17 | I've created a performance test suite that covers all the PRD-specified timing requirements. I'm using the browser performance API to measure response times for each operation, including the USDA search with 300,000 rows and the analysis bar graph with 20 nutrients.
TECH-004 | 2 | Arjun Mehta | 2025-03-20 | After running the tests on a production-equivalent Supabase instance, most operations pass. However, I've noticed that the analysis bar graph with 20 nutrients takes 2.1 seconds to load on the first navigation. This is due to 20 separate database queries firing in sequence. I propose we batch all 20 nutrient queries into a single call to optimize performance.
TECH-004 | 3 | Arjun Mehta | 2025-03-23 | I've optimized the analysis endpoint to use a single query that returns all nutrient totals for the selected date across all tracked nutrients. This reduces the database round trips from 20 to 1. After re-testing, the analysis now loads in 0.8 seconds, and all other operations are well under their limits. This should significantly enhance user experience.
TECH-004 | 4 | Shristi Sharmistha | 2025-03-26 | I've reviewed the test results, and all operations now pass the performance requirements. The optimization from 20 queries to 1 is crucial; without it, we would have failed the performance requirements for users tracking the maximum 20 nutrients. I’ll document the test suite for regression testing after each sprint. Closing the ticket now.
TECH-006 | 1 | Arjun Mehta | 2025-03-17 | Let's ensure we comprehensively verify that the auto-save works correctly across all diary actions before the MVP launch. I want to avoid any silent failures where the API save call fails but the UI shows success. Priya, can you review all places where API calls happen and confirm that error handling is in place?
TECH-006 | 2 | Priya Nair | 2025-03-19 | I've audited all diary API calls: add food (POST), edit portion (PATCH), delete food (DELETE), and add custom food (POST). They all use the optimistic updates from NUTR-010 pattern and have error handlers that revert the UI state if the API call fails. However, I found a gap: if the network is offline when a user adds food, the optimistic update shows success in the UI, but the food is lost upon refresh since it wasn't saved to Supabase. How should we handle this offline scenario?
TECH-006 | 3 | Arjun Mehta | 2025-03-21 | I think offline support should be a V2 feature since it requires service workers and a local-first architecture. For V1 MVP, we should assume online usage. I propose we document offline as a known limitation and add a network status indicator in the app header that shows an 'offline' warning when the network is unavailable. This way, we can prevent users from logging food while offline, avoiding silent data loss.
TECH-006 | 4 | Shristi Sharmistha | 2025-03-24 | I approve the offline warning approach. It's better to clearly inform users when they're offline rather than risk losing data silently. I've tested the scenarios: adding food, refreshing, logging out, and closing the browser tab — all passed and the diary remains intact. I will close this ticket now, and we can add offline support to the V2 backlog.
TECH-007 | 1 | Arjun Mehta | 2025-03-19 | I'm starting the verification process for the IST timezone handling from NUTR-022. Specifically, I’ll test the midnight edge case where food logged at 11:55 PM IST should still be on the same date as food logged at 1:00 AM the next day. This is critical to ensure we don't misrepresent logged data.
TECH-007 | 2 | Arjun Mehta | 2025-03-22 | I've run tests for the edge case and confirmed that food logged at 11:55 PM IST appears on the correct local date, while food logged at 12:05 AM IST correctly shows on the next local date. The dual storage method (date_string + UTC timestamp) from NUTR-022 is functioning as expected. However, I noticed that if the user logs food right at midnight UTC, it could lead to confusion in date representation. We should document this edge case.
TECH-007 | 3 | Arjun Mehta | 2025-03-25 | I tested the date switching functionality for the analysis section, and it correctly updates the 7-day trend window using local date_string arithmetic. No UTC offset errors were found. However, I realized we need to ensure that the date picker used in both the food diary and analysis sections is consistent, as per PRD requirements. Let's make sure this is addressed before the MVP launch.
TECH-007 | 4 | Arjun Mehta | 2025-03-26 | All date operations have been verified and are functioning correctly, including the midnight edge case. Since we are closing this ticket, I want to note that NUTR-BUG-006 might arise in future date handling due to a specific code path not covered by our tests. We should keep an eye on that. With the MVP launching in just a few days, it's crucial we ensure everything is solid.