## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
NUTR-BUG-002 | Duplicate food warning not showing when same food added from custom food source | Bug | Done | P2 | Priya Nair | Sprint 8 | 3 | During beta testing, it was found that the duplicate food warning only triggers for USDA foods and not for custom foods. This leads to the possibility of users accidentally adding the same custom food multiple times to the same meal, which distorts nutrient totals. We need to ensure that the duplicate check works for all food sources, including custom ones. | • Duplicate food or recipe cannot be part of the same meal again on the same date. • Warning must be shown in red when duplicate detected. • Warning disappears after 3 seconds.
NUTR-BUG-007 | Custom meal nutrient values in diary not matching values from creation | Bug | Done | P1 | Arjun Mehta, Priya Nair | Sprint 8 | 5 | We've received multiple reports from beta users regarding discrepancies in nutrient values for custom meals logged in the diary. The protein value, for example, shows differently than what was originally set during meal creation. This inconsistency suggests that the nutrient values are being recalculated rather than retrieved from stored values. We need to investigate and resolve this issue to ensure data integrity. | • Nutrient data in food diary matches values saved during custom meal creation. • Only meals created by the logged-in user should be accessible.
NUTR-BUG-008 | Search results from previous food source still showing when source changed | Bug | Done | P2 | Priya Nair | Sprint 8 | 3 | There's a bug where the search results from a previous food source remain visible for a few seconds after the user switches to a new source. This can lead to confusion as users might click on outdated results. The issue needs to be fixed to ensure that the results are cleared immediately when the source changes. | • Search results must be cleared instantly when the source changes. • User must re-search and re-select after changing the food source.
NUTR-BUG-009 | DV% showing decimal value instead of dash for nutrients less than 1% | Bug | Done | P2 | Priya Nair | Sprint 8 | 5 | During QA, it was discovered that the DV% column on the adjust portion page is displaying decimal values for some nutrients that should show a dash instead. This issue affects nutrients with values less than 1%, which contradicts the PRD requirements. We need to address both the display logic and the data alignment for these nutrients. | • DV% values less than 1% should display as '-' • All nutrient values must be displayed correctly in the nutrient breakdown table
NUTR-BUG-010 | Per-meal nutrient total row appearing after wrong food item | Bug | Done | P2 | Priya Nair | Sprint 8 | 5 | We've encountered a bug where the per-meal nutrient total row appears in the wrong position when foods are added in a non-sequential order. This issue arises specifically when editing a food's portion size, leading to confusion in the display of meal totals. We need to address this to ensure the total always appears after the last food item in that meal section. | • Total nutrient consumed per meal displayed at end of last food item in that meal • Total nutrient consumed per meal should be bold • No color coding for meal totals • Food items within a meal should be displayed in alphabetical order
GOAL-BUG-001 | Target date not recalculating when user manually changes calorie budget | Bug | Done | P2 | Arjun Mehta | Sprint 8 | 5 | A beta user reported that when they manually changed their calorie budget, the target date did not update accordingly. This is a critical bug as it affects user experience and goal tracking. The app should recalculate the target date based on the new calorie deficit when the user makes changes to their calorie budget. | • Target date updates correctly when calorie budget is manually changed. • Number of days left to reach the goal updates accordingly. • Weight maintenance calorie remains unchanged.
GOAL-BUG-005 | BMR warning shown for below-BMR calorie but goal saved incorrectly | Bug | Done | P1 | Arjun Mehta | Sprint 8 | 5 | We've encountered a bug related to the BMR validation for user-defined calorie goals. When a user sets a calorie goal below their BMR, a warning appears correctly, but upon saving, the goal weight and target date fields are cleared incorrectly. This should only happen for system-calculated cases. We need to address this regression from the refactoring done in Sprint 6. | • For system-calculated calorie below BMR: show error, DO NOT set calorie goal, remove goal weight and target date • For USER-DEFINED calorie below BMR: show warning but ALLOW user to save • Both cases show the message: 'Calorie budget below BMR [value]. Eating less than BMR calories could cause excessive loss of lean body mass'
CF-BUG-003 | Calorie field not marked as mandatory with asterisk in custom food create form | Bug | Done | P2 | Priya Nair, Kabir Sharma | Sprint 8 | 3 | During QA of the custom food create form, it was found that the calorie field does not display an asterisk to indicate it's mandatory, despite the PRD stating that it should. This could lead users to believe that entering a calorie value is optional. We need to ensure that the UI reflects the mandatory nature of this field correctly. | • Calorie field must show an asterisk (*) to indicate it is mandatory. • All mandatory fields should be clearly marked with an asterisk.
CF-BUG-004 | Add button not appearing on create custom food page after saving | Bug | Done | P2 | Priya Nair | Sprint 8 | 3 | There's a bug in the custom food creation flow where the Add button does not appear after saving a custom food item. This prevents users from adding the newly created food directly to their diary. The expected behavior is that the Add button should be visible after saving, allowing users to quickly add the food without extra navigation. This issue needs to be resolved to enhance user experience and align with the PRD requirements. | • Add button appears after saving a custom food item. • No fields can be edited once saved. • User navigates back to the custom food menu page after saving.
AN-CR-001 | Bar graph colors and design confusing — full redesign following user feedback | Story | Done | P1 | Kabir Sharma, Priya Nair | Sprint 8 | 8 | Following user feedback from beta testing, the bar graph design needs a complete overhaul to enhance clarity. Users find the current representation confusing, especially in distinguishing actual intake versus targets. This ticket aims to implement a redesign that aligns with user expectations and improves overall comprehension. | • Bar graph visual must clearly communicate actual vs target • All nutrient value and unit must be clearly visible • Bar graph loads within 2 seconds • Updates within 1 second after food changes
AN-CR-002 | Add clear remaining vs over target label below bar graph | Change request | Done | P2 | Kabir Sharma, Priya Nair | Sprint 8 | 5 | Beta users have expressed confusion regarding the text label under the bar graph indicating nutrient status. The current labels 'Xg left' and 'Xg over' are ambiguous. This ticket aims to clarify these labels to improve user understanding and ensure consistency across the app. | • Labels should read 'Xg remaining' for under-target and 'Xg over target' for over-target. • Ensure consistency in terminology across both the analysis section and the food diary comparison section.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
NUTR-BUG-002 | 1 | Priya Nair | 2025-04-15 | I've identified a bug where the duplicate detection from NUTR-026 only works for USDA foods. Custom foods, recipes, and meals bypass this check. Steps to reproduce: create a custom food 'Homemade Daal', add it to breakfast, then try to add it again — no warning appears.
NUTR-BUG-002 | 2 | Shristi Sharmistha | 2025-04-16 | How many beta users have actually double-logged a custom food? We need to understand the impact before prioritizing this fix.
NUTR-BUG-002 | 3 | Priya Nair | 2025-04-16 | Checked the database and found 7 users with duplicate custom food entries in the same meal. Most seem to be accidental double-taps. I suggest we keep this as P2 since users can manually delete duplicates.
NUTR-BUG-002 | 4 | Priya Nair | 2025-04-17 | I've traced the duplicate check code from NUTR-026. The check queries the food_logs table for existing entries matching food_id + meal_type + date_string. The issue is that for custom foods, we store custom_food_id in a separate column. The current check only looks at food_id.
NUTR-BUG-002 | 5 | Priya Nair | 2025-04-18 | Arjun, should we refactor the food_logs table schema to use a single food_id with a food_source_type column, or extend the duplicate check to consider the appropriate ID based on source_type?
NUTR-BUG-002 | 6 | Arjun | 2025-04-18 | Let's extend the duplicate check instead of refactoring the schema. Refactoring would require a migration on existing beta user data, which is risky. The extension can be done safely. We should check for duplicates based on (source_type + appropriate_id + meal_type + date_string).
NUTR-BUG-002 | 7 | Priya Nair | 2025-04-19 | I've implemented the extended duplicate check. Now, if source_type is 'usda', it checks food_id; if 'custom_food', it checks custom_food_id; and similarly for recipes and meals. All sources now trigger the red warning on duplicates.
NUTR-BUG-002 | 8 | Shristi Sharmistha | 2025-04-20 | I've verified the changes. I added the same USDA food twice to breakfast and got the warning, then did the same with a custom food and recipe — both worked. Also tested cross-meal behavior, and same food in breakfast and lunch is still allowed. Closing this ticket.
NUTR-BUG-007 | 1 | Shristi Sharmistha | 2025-04-15 | We've received reports from beta users that the nutrient values for custom meals in the diary do not match what they set during creation. For example, one user created a meal with 35g protein, but it shows 32g in the diary. This seems to be a recurring issue.
NUTR-BUG-007 | 2 | Arjun Mehta | 2025-04-16 | I've looked into the custom meal data model. It appears that when a custom meal is logged to the diary, the nutrient values are being recalculated from the current ingredient data, rather than using the values saved at creation. This is likely causing the discrepancies.
NUTR-BUG-007 | 3 | Arjun Mehta | 2025-04-17 | I've identified a specific edge case: if a user edits an ingredient in a custom meal after its creation, the recalculation at logging time uses the updated ingredient values. This means if a user created a meal with 'Protein Powder' at 35g but later edits it, the logged meal will reflect the new value, not the original.
NUTR-BUG-007 | 4 | Priya Nair | 2025-04-18 | Should we consider freezing the nutrient values at the time of meal creation to avoid these discrepancies? This would ensure that the diary always reflects what the user intended. However, we need to weigh the pros and cons of having live calculations versus frozen values.
NUTR-BUG-007 | 5 | Shristi Sharmistha | 2025-04-19 | After considering both options, I believe we should go with freezing the nutrient values at creation time. The PRD states that 'nutrient data added to diary must match values saved during custom meal creation.' This aligns with our goal of maintaining consistency for users.
NUTR-BUG-007 | 6 | Arjun Mehta | 2025-04-20 | I'll implement the fix to store the total nutrient values as a snapshot when a custom meal is created or edited. This way, when the meal is logged to the diary, it will use the snapshot values directly, avoiding recalculation.
NUTR-BUG-007 | 7 | Priya Nair | 2025-04-21 | I've updated the food diary logging flow to ensure that the POST /food-logs for custom meals now copies the snapshot_nutrients directly from the custom_meals table. I tested it with a meal created with 35g protein, and it still shows correctly in the diary after editing an ingredient.
NUTR-BUG-007 | 8 | Shristi Sharmistha | 2025-04-22 | I've verified the changes with the beta users. The nutrient values now match what they created. I also tested the edge case where a user edits the custom meal itself, and the snapshot updates correctly for future logs. Past logs remain unaffected. Closing the ticket.
NUTR-BUG-008 | 1 | Priya Nair | 2025-04-16 | I found a bug where switching from USDA to Custom Food still shows the USDA results for 1-3 seconds. Steps to reproduce: search 'chicken' in USDA, switch to Custom Food, and observe the results panel.
NUTR-BUG-008 | 2 | Arjun Mehta | 2025-04-17 | Looking into the reusable search component from NUTR-011. The source prop change triggers a re-render, but the results clearing happens after the render due to React's batching. We need to adjust the timing of the state updates.
NUTR-BUG-008 | 3 | Priya Nair | 2025-04-18 | Instead of clearing results in useEffect after render, we should clear them synchronously in the onChange handler before the state update. This should fix the issue.
NUTR-BUG-008 | 4 | Arjun Mehta | 2025-04-19 | The issue is deeper. The fix from NUTR-BUG-003 was for a different component. We need to apply a similar cleanup approach here, but it seems the search component wasn't updated when that fix was made.
NUTR-BUG-008 | 5 | Shristi Sharmistha | 2025-04-20 | This is the third time we’ve missed applying fixes across related components. We need to conduct a comprehensive audit of all components that share similar patterns to avoid this in the future.
NUTR-BUG-008 | 6 | Priya Nair | 2025-04-21 | I've implemented the fix by moving the results clearing to the synchronous event handler. Now, when the source dropdown changes, the results array clears immediately before any fetch starts.
NUTR-BUG-008 | 7 | Arjun Mehta | 2025-04-21 | I reviewed all useEffect cleanup patterns as requested. I found another instance in the date picker component that could cause a similar issue under certain conditions. I've fixed that as well.
NUTR-BUG-008 | 8 | Shristi Sharmistha | 2025-04-21 | I verified the fix by switching sources while results are showing. Everything clears instantly now, no flash of old results. I tested all source types and they all behave correctly. Closing the ticket.
NUTR-BUG-009 | 1 | Shristi Sharmistha | 2025-04-16 | I found an issue during QA on the adjust portion page. For example, selecting 100g of lettuce shows Zinc DV% as '0.47%' instead of '-'. This violates our PRD requirement that any DV% less than 1 should show '-'.
NUTR-BUG-009 | 2 | Priya Nair | 2025-04-17 | I've reviewed the DV% display logic in the code. It checks `if (dvPercent < 1) return '-'`, which should work. However, the 0.47% is actually the Zinc actual amount being displayed incorrectly. We need to investigate the column alignment issue.
NUTR-BUG-009 | 3 | Priya Nair | 2025-04-17 | I traced the issue further and found that the nutrient table renders columns dynamically. For some nutrients, the array order is incorrect, leading to actual mg values appearing in the DV% column. We need to fix this alignment issue.
NUTR-BUG-009 | 4 | Arjun | 2025-04-18 | I've checked the USDA database and found that 23 out of 40+ tracked micronutrients have an unusual data structure with reversed column order. This is a data normalization issue from NUTR-TASK-001. We need to address this in the import process.
NUTR-BUG-009 | 5 | Arjun | 2025-04-19 | I've fixed the USDA import normalization by adding explicit column mapping using nutrient_type_id instead of relying on array position. All affected nutrients should now return data in the correct order.
NUTR-BUG-009 | 6 | Priya Nair | 2025-04-19 | I also need to fix the < 1 dash rule. The original check `dvPercent < 1` works for most cases, but for very small numbers like 0.002%, we need to apply `parseFloat(toFixed(2))` before the comparison to ensure it displays correctly.
NUTR-BUG-009 | 7 | Shristi Sharmistha | 2025-04-20 | I've verified the changes across 20 different foods. All DV% values below 1% now show '-', and the column alignment is correct for all nutrients. We should close this ticket.
NUTR-BUG-009 | 8 | Priya Nair | 2025-04-20 | Agreed, the fixes are working as expected. I also tested extreme micro values like oysters for zinc and liver for vitamin A to ensure high values display correctly. Closing the ticket now.
NUTR-BUG-010 | 1 | Shristi Sharmistha | 2025-04-17 | I found a bug during QA. The per-meal total row is appearing after the second food item instead of the last one when foods are added in a non-sequential order. For example, if I add an Apple to Snacks, then an Egg to Breakfast, and finally a Banana to Snacks, the total for Snacks shows after Banana instead of after Apple and Banana.
NUTR-BUG-010 | 2 | Priya Nair | 2025-04-18 | I traced the meal grouping logic. The diary component uses the food_logs array ordered by created_at timestamp. When adding in the order mentioned, the array is [Apple, Egg, Banana]. The total is appended after the last item in the array that belongs to that meal, which is correct. However, I suspect the issue might be related to how we handle state updates.
NUTR-BUG-010 | 3 | Priya Nair | 2025-04-19 | Upon further testing, I found that the bug occurs when editing a food's portion size. The PATCH API returns the updated record, and the frontend optimistically updates the diary state. This moves the edited item to the end of the food_logs array, which disrupts the visual order. For example, editing Apple moves it to the end, resulting in [Banana, Apple(updated)]. The total still appears after Apple, but now it's not the last item visually.
NUTR-BUG-010 | 4 | Arjun | 2025-04-20 | The optimistic update bug is indeed the root cause. The edit state update removes the original item and appends the updated version, changing the visual order. We should implement an in-place update to preserve the item's position in the array instead of removing and appending it.
NUTR-BUG-010 | 5 | Priya Nair | 2025-04-21 | Will the in-place update also fix the meal total position? If we preserve array positions, the meal grouping should render in the original insertion order, ensuring the total appears after the last item in that order.
NUTR-BUG-010 | 6 | Shristi Sharmistha | 2025-04-21 | Should we also consider how food items are displayed within a meal? The PRD doesn't specify if they should be in insertion order or sorted. I suggest we implement an alphabetical sort for better UX so users can predict where a food will appear.
NUTR-BUG-010 | 7 | Priya Nair | 2025-04-22 | I've implemented both fixes: the in-place update for edits to preserve position and an alphabetical sort by food_name within each meal group. Now, the total row always renders after the last alphabetically sorted item in each meal. I will test this with various additions and edits.
NUTR-BUG-010 | 8 | Shristi Sharmistha | 2025-04-22 | I've verified the changes. Adding foods in random order shows each meal section is alphabetically sorted, and the total appears after the last food in each meal. I also tested editing a food's portion, and it stays in its alphabetical position. The delete function works correctly too. Closing this ticket.
GOAL-BUG-001 | 1 | Shristi Sharmistha | 2025-04-15 | Received a report from beta user BT-089 about the target date not updating after they lowered their calorie goal from 1800 to 1600 kcal. We need to investigate how the target date and days left are calculated and updated.
GOAL-BUG-001 | 2 | Arjun Mehta | 2025-04-16 | I reproduced the issue. The calorie budget updates correctly in the database, and the required deficit calculation is correct. However, the no_of_days_left and target_date are not updating after the deficit recalculation. This seems to be a missing cascade in the database functions.
GOAL-BUG-001 | 3 | Arjun Mehta | 2025-04-17 | The dependency cascade should be: calorie changes → deficit recalculates → days_left recalculates → target_date recalculates. The deficit recalculation works, but the days_left and target_date functions are only called when saving the goal, not during the manual calorie edit. We need to address this.
GOAL-BUG-001 | 4 | Arjun Mehta | 2025-04-18 | I've identified that the deficit recalculation function does not trigger the days_left and target_date recalculation functions after a manual calorie change. This is a significant gap in the implementation that needs to be fixed.
GOAL-BUG-001 | 5 | Shristi Sharmistha | 2025-04-19 | Looking at the PRD, we should consider if there are other areas where similar gaps might exist. Can you check the dependency matrix from GOAL-003 to see if there are other paths that could be affected?
GOAL-BUG-001 | 6 | Arjun Mehta | 2025-04-20 | I've reviewed the dependency matrix and found two additional gaps: (1) when goal_weight changes, the target_date doesn't update in the quick-edit flow, and (2) when current_weight changes, WMC doesn't cascade to update the target_date. Both follow the same pattern as the calorie change issue.
GOAL-BUG-001 | 7 | Arjun Mehta | 2025-04-21 | I implemented a comprehensive refactor of the recalculation logic into a single function that ensures all dependent values update regardless of the trigger. This should address the cascade issues across all relevant paths.
GOAL-BUG-001 | 8 | Shristi Sharmistha | 2025-04-21 | I verified the fix with BT-089's scenario and confirmed that the target date now updates correctly when lowering the calorie goal. I also tested the goal weight and current weight changes, and both cascaded correctly. Closing the ticket.
GOAL-BUG-005 | 1 | Shristi Sharmistha | 2025-04-16 | I've found that the BMR validation from GOAL-004 is partially broken. When testing the user-defined below-BMR case, the warning shows correctly, and the user can save the goal. However, when reopening the goal page, the goal weight and target date fields are blank. This should not happen for user-defined cases.
GOAL-BUG-005 | 2 | Arjun Mehta | 2025-04-17 | I've reviewed the BMR validation implementation and confirmed that the save handler correctly implements the two paths. However, during the Sprint 6 performance refactoring, the save endpoint was reorganized, which introduced a regression. The goal_weight and target_date clearing logic was moved to a generic cleanup function that runs after all saves.
GOAL-BUG-005 | 3 | Arjun Mehta | 2025-04-18 | I've traced the regression to the exact commit from Sprint 6 where the save endpoint was refactored. The original code had the clearing logic inside a conditional block, but after refactoring, it was extracted to a separate function, losing the conditional context. This is the root cause of the issue.
GOAL-BUG-005 | 4 | Shristi Sharmistha | 2025-04-19 | This regression from the Sprint 6 refactoring raises a concern. Did the GOAL-004 tests not catch this? We need to ensure that our tests are robust enough to cover such changes.
GOAL-BUG-005 | 5 | Arjun Mehta | 2025-04-20 | You're right, the GOAL-004 tests verified the initial implementation but did not include regression tests for the refactored version. I'll add regression tests for all BMR validation scenarios before fixing the code to ensure the fix is verified.
GOAL-BUG-005 | 6 | Arjun Mehta | 2025-04-21 | I've written the tests covering all BMR scenarios: system-calculated below BMR (fields cleared), user-defined below BMR (fields preserved), system-calculated above BMR (normal flow), and user-defined above BMR (normal flow). All four tests are failing, confirming the regression.
GOAL-BUG-005 | 7 | Arjun Mehta | 2025-04-22 | I've fixed the clearing logic by moving it back inside the conditional block that only fires for system-calculated cases. Now, user-defined saves will never trigger field clearing regardless of BMR comparison. All four tests now pass.
GOAL-BUG-005 | 8 | Shristi Sharmistha | 2025-04-22 | I've manually verified all scenarios: system-calculated below BMR (fields clear, goal not saved), user-defined below BMR (warning shows, fields preserved, goal saved), and both above BMR cases normal flow. I'm closing the ticket now. This is the first time we've written tests before the fix, which is a good practice for health-critical features.
CF-BUG-003 | 1 | Shristi Sharmistha | 2025-04-17 | I found that the calorie nutrient field in the custom food create form does not show an asterisk, even though the PRD states it is mandatory. This could confuse users into thinking it's optional. We need to address this.
CF-BUG-003 | 2 | Kabir Sharma | 2025-04-18 | I checked the Figma designs, and the calorie asterisk is indeed present. This seems to be an implementation oversight. Priya, can you clarify why the asterisk wasn't included in the code?
CF-BUG-003 | 3 | Priya Nair | 2025-04-19 | The nutrient list is rendered dynamically from definitions, and while the is_mandatory flag exists, I didn't implement it in the rendering logic. The calorie nutrient is marked as mandatory in the database, but the frontend doesn't check this flag.
CF-BUG-003 | 4 | Shristi Sharmistha | 2025-04-20 | Are there any other nutrients that might be mandatory and also lack an asterisk? It's important we catch all potential issues.
CF-BUG-003 | 5 | Priya Nair | 2025-04-20 | Calorie is the only nutrient marked as mandatory in the database. All other nutrients are optional, so we should only focus on adding the asterisk for calorie.
CF-BUG-003 | 6 | Kabir Sharma | 2025-04-20 | That's good to know. The fix should be straightforward. Priya, please add a conditional render for the asterisk based on the is_mandatory flag in the nutrient definition.
CF-BUG-003 | 7 | Priya Nair | 2025-04-21 | I've implemented the fix by adding `{nutrient.is_mandatory && <span>*</span>}` to the nutrient row renderer. I also added a 'Required' label below the calorie input for better clarity. Testing shows only the calorie row displays the asterisk.
CF-BUG-003 | 8 | Shristi Sharmistha | 2025-04-21 | I've verified the changes. The calorie field now shows the asterisk and 'Required' label. The save validation correctly blocks submission without a calorie value. I'm closing this ticket.
CF-BUG-004 | 1 | Shristi Sharmistha | 2025-04-17 | I found a bug during QA. After saving a custom food, the Add button is not appearing on the create page. This is against our PRD requirement that states the Add button should be visible after saving.
CF-BUG-004 | 2 | Priya Nair | 2025-04-18 | Looking into the save flow from CF-003, I see that the Add button should be rendered when `is_saved` is true. However, the conditional check also requires `custom_food_id` to be defined. I suspect that might be the issue.
CF-BUG-004 | 3 | Priya Nair | 2025-04-19 | I added some console logs and confirmed that `is_saved` is true after saving, but `custom_food_id` is undefined. The API response includes the new ID, but it seems we're not storing it in the component state.
CF-BUG-004 | 4 | Priya Nair | 2025-04-20 | Tracing the save handler, I see that after the API call, we set `is_saved` to true but forgot to extract and store `custom_food_id` from the API response. This is a simple omission that needs fixing.
CF-BUG-004 | 5 | Shristi Sharmistha | 2025-04-20 | What should happen when the Add button is fixed? It should navigate to the adjust portion page for the new food, pre-populated with its data, right?
CF-BUG-004 | 6 | Priya Nair | 2025-04-21 | Yes, that's correct. I've implemented the fix by extracting `custom_food_id` from the API response and storing it in state. The Add button now appears correctly after saving, and tapping it navigates to the adjust portion page with the new food data.
CF-BUG-004 | 7 | Priya Nair | 2025-04-21 | Additionally, I added a success animation where a brief green flash appears on the Add button after saving. This was a suggestion from Kabir during a design review.
CF-BUG-004 | 8 | Shristi Sharmistha | 2025-04-21 | I just verified the fix by saving a custom food 'Masala Oats'. The Add button appeared with the green flash, and I was able to navigate to the adjust portion page with the food pre-filled. This also addresses the Indian food gap from NUTR-TASK-001. Closing the ticket now.
AN-CR-001 | 1 | Ananya Iyer | 2025-04-15 | Based on beta feedback, 30% of users find the current bar graph confusing. They struggle to differentiate between what they've consumed and what they still need. I suggest we consider a redesign that makes this distinction clearer.
AN-CR-001 | 2 | Kabir Sharma | 2025-04-16 | I've been working on two redesign options. Option 1 is a progress bar that fills as you eat, while Option 2 shows what's left. I believe Option 1 aligns better with user expectations. We should also clarify how we will visually indicate when users exceed their targets.
AN-CR-001 | 3 | Ananya Iyer | 2025-04-17 | I ran quick tests with 5 users on both options. All found Option 1 intuitive, while 3 of 5 were confused by Option 2. We should move forward with Option 1, but we need to define how to represent over-eating clearly.
AN-CR-001 | 4 | Shristi Sharmistha | 2025-04-18 | I approve Option 1. However, we need to rethink how we visually represent over 100%. Can we use a thermometer metaphor to show the overflow? This could help users understand both their goal achievement and any excess consumption.
AN-CR-001 | 5 | Kabir Sharma | 2025-04-19 | Great idea! I propose that we have a yellow fill for 0-99%, a green fill at 100%, and a red extension for anything above 100%. This way, users can easily see their progress and any overage. I'll create mockups for this.
AN-CR-001 | 6 | Priya Nair | 2025-04-22 | I've implemented the redesign based on Kabir's mockups. The new component has a yellow fill up to the actual percentage, a green cap at 100%, and a red overflow for amounts over that. Performance remains the same, loading within 2 seconds.
AN-CR-001 | 7 | Ananya Iyer | 2025-04-24 | I tested the new design with 8 beta users. All understood the filling concept immediately. However, one user didn't grasp the red overflow until they read the label. We might need to consider making that label more prominent.
AN-CR-001 | 8 | Shristi Sharmistha | 2025-04-26 | Let's deploy this to beta and inform all users about the improvements. I’ll send out an update to the 200+ beta users. Also, Kabir, please ensure the Figma documentation is updated for future reference.
AN-CR-002 | 1 | Ananya Iyer | 2025-04-15 | We've received feedback from beta users that the current label showing 'Xg left' is confusing. It could mean either remaining nutrients to consume or leftover nutrients. We need to clarify this.
AN-CR-002 | 2 | Kabir Sharma | 2025-04-16 | I suggest three alternatives for the label: Option A: '35g remaining' / '35g over target', Option B: '35g to go' / '35g over target', and Option C: 'Need 35g more' / '35g exceeded'. I think Option A is the clearest while still being concise.
AN-CR-002 | 3 | Ananya Iyer | 2025-04-17 | I tested all three options with 5 users. Option A was the clear winner with 5/5 understanding it immediately. Option B had one user confused thinking 'to go' meant takeaway food, which is a funny but valid concern. Option C felt too bossy for users.
AN-CR-002 | 4 | Shristi Sharmistha | 2025-04-18 | Let's go with Option A: 'Xg remaining' for under-target and 'Xg over target' for over-target. Also, ensure this terminology is consistent in the food diary comparison section (NUTR-017) for clarity.
AN-CR-002 | 5 | Kabir Sharma | 2025-04-19 | The current PRD states to display `¦target-actual¦`, but for over-target, this gives the same number regardless of label. We need to ensure the display is always a positive number. Luckily, the implementation already uses absolute values, so no changes are needed there.
AN-CR-002 | 6 | Priya Nair | 2025-04-20 | I've updated the label copy to replace 'left' with 'remaining' and 'over' with 'over target' in both the analysis and food diary sections. I've tested it in both locations, and everything looks good!
AN-CR-002 | 7 | Ananya Iyer | 2025-04-22 | I've verified the label copy in both sections, and it consistently shows 'remaining' and 'over target'. I also tested with a nutrient at exactly 100% and it correctly shows '0g remaining', which is perfect. Over-target displays '35g over target' clearly.
AN-CR-002 | 8 | Shristi Sharmistha | 2025-04-24 | Everything looks good! The updates ensure clarity and consistency across the app. This small UX detail is crucial for product polish. Ready for launch on May 1!