# Sprint 10 Planning — Nutrivana

May 13 to May 26, 2025

Monitor post-launch metrics, resolve all bugs from the launch week, and start investigating the pregnant women user segment. No new features will be developed this sprint.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 10 | metrics dashboard, cohort analysis, bug fixes |
| Priya Nair | Frontend Engineer | 10 | bug fixes, iOS Safari custom food issue |
| Kabir Sharma | Designer | 10 | App Store screenshot update, V2 design thinking |
| Ananya Iyer | Marketing | 10 | NPS survey, pregnant women interviews, partnership |
| Shristi Sharmistha | CEO & Product Manager | 10 | research coordination, V2 planning, investor update |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| MON-001 | Post-launch metrics dashboard setup | Arjun | 3 | P0 | Essential for tracking user engagement and product performance post-launch. |
| MON-002 | Pregnant women cohort analysis | Arjun | 5 | P1 | Critical to understand the engagement of this specific user segment identified during launch. |
| BUG-010 | Search results not resetting on diary date change | Priya | 2 | P2 | Fixing this bug is necessary for a smooth user experience. |
| AN-CR-003 | Analysis screen performance on low-end Android | Arjun | 3 | P2 | Improving performance will enhance usability for a segment of our users. |
| NPS-001 | NPS survey implementation and launch | Ananya | 3 | P1 | Gathering user feedback is vital for future improvements. |
| RES-001 | Pregnant women user interviews — 5 interviews | Ananya | 2 | P1 | Direct insights from engaged users will guide our product strategy. |
| MKT-001 | Dr. Kavitha Rao nutritionist partnership activation | Ananya | 2 | P2 | Activating this partnership will enhance our service offerings. |
| BUG-011 | Custom food serving unit not saving on iOS Safari | Priya | 3 | P1 | This bug affects a significant portion of our user base and needs urgent resolution. |
| V2-PLAN-001 | Q3 roadmap planning and V2 feature prioritisation | Shristi | 2 | P1 | Planning for the next quarter is crucial for aligning our future efforts. |

# Success Criteria

Metrics dashboard is live and accessible to all team members.

Pregnant women cohort analysis is completed with documented findings.

NPS survey is launched by May 20, with results shared with the team.

All P1 bugs are fixed and deployed.

Partnership with Dr. Kavitha Rao is activated.

Q3 priorities are documented based on NPS and cohort data.

Five interviews with pregnant women users are conducted.

# Dependencies

MON-002 requires MON-001 to be completed first.

RES-001 depends on identifying the 11 users from Ananya's manual review.

NPS-001 cannot launch until the in-app banner is built by Arjun.

# Risks

Risk: Pregnant women cohort analysis may have a small sample size of only 11 users, leading to potentially unreliable results. Mitigation: Arjun will perform bias checks before sharing any numbers externally.

Risk: NPS response rate may be low, resulting in unreliable scores if fewer than 100 users respond. Mitigation: The survey will only be sent to users who have logged food at least three times to ensure quality responses.

Risk: The iOS Safari bug affects about 15% of iOS users, which is critical to fix to avoid impacting our highest-value user segment. Mitigation: This bug is prioritized as P1 and must be resolved before the end of the sprint.

# Definition of Done

All 9 tickets are moved to Done in Jira.

Metrics dashboard is verified by Shristi to show accurate data.

Cohort analysis is shared in team Slack with full methodology documented.

NPS survey is live and results are available by May 21.

The iOS Safari bug is confirmed fixed on a physical iOS device.

Q3 priorities are documented and shared with Ravi.