# Sprint 2 Planning — Nutrivana

January 15 to January 28, 2025

Integrate the USDA database with a search function that operates in under one second, and initiate the implementation of goal setting with a fully functional EER formula for all user profiles.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 10 | Database integration and EER formula implementation |
| Priya Nair | Frontend Engineer | 10 | Fuzzy search implementation and UI adjustments |
| Kabir Sharma | Designer | 10 | Designing goal setting screens |
| Ananya Iyer | Marketing | 10 | Building waitlist and scheduling user interviews |
| Shristi Sharmistha | Product Manager | 10 | Reviewing PRD and coordinating sprint activities |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| NUTR-TASK-001 | USDA database integration and API setup | Arjun | 8 | P0 | Critical for enabling food search functionality. |
| NUTR-TASK-002 | Fuzzy search implementation | Arjun/Priya | 8 | P0 | Essential for improving search accuracy and user experience. |
| GOAL-001 | Set calorie goal with EER calculation | Arjun | 5 | P0 | Foundational for user goal setting features. |
| GOAL-002 | EER formula implementation all variants | Arjun | 8 | P0 | Necessary for accurate calorie goal calculations. |
| GOAL-003 | Required deficit surplus calculation | Arjun | 3 | P1 | Supports user goal tracking and adjustments. |
| GOAL-004 | BMR validation with warning message | Arjun | 3 | P1 | Ensures users receive accurate feedback on their calorie goals. |

# Success Criteria

Import over 300,000 USDA food items into Supabase and ensure they are searchable.

Achieve search results in under one second across all query types.

Implement fuzzy matching so that misspellings like 'chiken' correctly return 'chicken'.

Allow users to set calorie goals with EER calculations accurate for at least five different profiles (male/female, ages 19-65).

Validate BMR and block any calorie goals set below BMR with the correct error message.

# Dependencies

Completion of GOAL-SPIKE-001 from Sprint 1, as EER formula research is required for GOAL-001 and GOAL-002.

Finalization of the Supabase database schema (TECH-001) before the USDA import can begin.

# Risks

Risk: USDA API may impose rate limits that hinder real-time search functionality. Mitigation: Arjun will investigate API limits on Day 1. If limits are problematic, we will switch to a bulk import approach. A decision is needed by January 17.

Risk: The complexity of the EER formula (15 variants) may delay GOAL-002 into Sprint 3. Mitigation: GOAL-002 is prioritized as the highest implementation ticket. Arjun will start working on it on January 15 alongside NUTR-TASK-001.

# Definition of Done

All code is reviewed and merged into the main branch.

All features are tested and pass unit tests.

Documentation is updated to reflect new features and changes.

User interface is polished and matches design specifications.

Functionality is demoable to stakeholders by the end of the sprint.