# Sprint 6 Planning — Nutrivana

Sprint dates: March 12 to March 31, 2025

Complete custom food management and build the entire analysis feature. Ship MVP on March 31. No scope additions this sprint — focus is on completion and quality.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 14 | Technical oversight and performance testing |
| Priya Nair | Frontend Engineer | 14 | Custom food management and analysis features |
| Kabir Sharma | Designer | 14 | Designing analysis screens and graphs |
| Ananya Iyer | Marketing | 14 | App Store listing and waitlist communications |
| Shristi Sharmistha | CEO & Product Manager | 14 | Overall project management and sprint coordination |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| CF-003 | Save custom food with validation | Priya/Arjun | 5 | P0 | Core functionality needed for custom food management. |
| CF-004 | Search and select custom food | Priya | 2 | P1 | Enhances user experience in managing food options. |
| CF-005 | Edit custom food | Priya/Arjun | 3 | P1 | Allows users to modify entries, essential for usability. |
| CF-006 | Delete custom food | Priya | 1 | P2 | Basic functionality to remove unwanted entries. |
| CF-007 | Retroactive change reflects from edit date | Arjun | 5 | P1 | Ensures data integrity and user trust. |
| AN-001 | Per nutrient analysis screen | Kabir/Priya | 3 | P1 | Critical for users to understand their nutrient intake. |
| AN-002 | Daily bar graph actual vs target | Kabir/Priya/Ananya | 8 | P0 | Visual representation of progress is crucial for user engagement. |
| AN-003 | Color coding yellow green red | Kabir/Priya | 3 | P0 | Improves clarity and usability of nutrient data. |
| AN-004 | 7-day trend graph | Arjun/Priya | 5 | P1 | Helps users track their progress over time. |
| AN-005 | Date picker synced diary and analysis | Priya | 2 | P1 | Ensures users can easily navigate their data. |
| TECH-004 | Performance testing all operations | Arjun | 3 | P0 | Critical to ensure the app runs smoothly for MVP. |
| TECH-006 | Auto-save verification | Arjun/Priya | 2 | P0 | Essential for user experience and data retention. |
| TECH-007 | Date timezone handling verification | Arjun | 2 | P0 | Ensures accuracy in user data across time zones. |

# Success Criteria

Full end-to-end demo clean by March 25

All PRD performance requirements verified via TECH-004

Bar graph tested with real users (Ananya to test with 5 users) before March 28

MVP ships March 31 — all P0 and P1 tickets complete

# Dependencies

All team members must be available and focused on their tasks.

Designs must be finalized before development begins on analysis features.

# Risks

Risk: Potential delays in feature completion due to scope creep. Mitigation: Strict adherence to scope lock after March 15.

Risk: Performance issues during testing. Mitigation: Conduct thorough performance testing early in the sprint.

Risk: User feedback may require last-minute changes. Mitigation: Gather user feedback in advance and prioritize critical changes.

# Definition of Done

All code is reviewed and merged into the main branch.

Features are tested and confirmed to meet acceptance criteria.

Documentation is updated to reflect new features.

All tickets are marked as complete in the project management tool.