## Q1 OKRs
Objective | Key Result | KR Type | Target | Baseline | Current Value | % Complete | Owner | Status | Notes
Become the most accurate nutrition tracker Indians can actually trust with their health data | EER formula outputs match USDA reference values within 1% error across all 15 formula variants for 5 diverse test profiles (male/female, ages 19-65, all activity levels) | Outcome | 100% match | 0% verified | 100% match | 100% | Arjun | Achieved
| Zero data loss incidents — all logged food persists across logout, browser refresh, and browser close in all test scenarios | Outcome | 0 incidents | Unknown | 0 incidents | 100% | Arjun/Priya | Achieved
| All PRD performance targets met — USDA search under 1 second, diary date switch under 2 seconds, nutrient recalculation under 1 second | Outcome | 100% | 0% tested | 100% | 100% | Arjun | Achieved
| 8 out of 10 internal testers complete full food logging flow end to end without asking for help or hitting a blocking bug | Outcome | 80% | 0% | 80% | 100% | Shristi | Achieved
| Zero RLS data isolation failures — User A cannot read, edit, or delete User B's food logs, goals, or custom foods | Outcome | 0 failures | Untested | 0 failures | 100% | Arjun | Achieved
Deeply understand Indian users' nutrition tracking frustrations before we ask them to use our product | Complete minimum 5 user interviews with health-conscious urban Indians (ages 22-45) identifying their top 3 frustrations with existing nutrition apps | Output (leads to outcome insight) | 5 interviews | 0 | 3 interviews | 60% | Ananya/Shristi | Partial
| 7 out of 10 waitlist users confirm Indian food database gap as their top 1 or top 2 pain point (validated via pre-launch survey) | Outcome | 70% | Hypothesis only | 73% | 100% | Ananya | Achieved
| Document 20+ Indian foods missing from USDA database with user-confirmed priority ranking for custom food creation order | Outcome | 20 foods | 10 identified Sprint 2 | 31 foods | 100% | Shristi | Achieved
| Competitive analysis completed comparing Nutrivana vs MyFitnessPal vs HealthifyMe vs Cronometer on Indian food coverage, micronutrient tracking depth, and UX clarity | Output | Done by Feb 28 | 0 | Completed March 15 | 100% | Shristi | Achieved
Ship an MVP the entire team is proud to put in front of real users on March 31 | Full end-to-end demo completed — new user creates account, sets goals, logs 3 meals, views analysis — zero P0 bugs encountered by March 25 | Output (quality gate) | 1 clean demo | 0 | 1 clean demo | 100% | Shristi | Achieved
| Technical architecture spec documenting all major decisions (DB schema, auth, search, timezone handling) approved before any feature implementation | Output (process quality) | Done by Jan 15 | 0 | Done by Jan 10 | 100% | Arjun | Achieved
| Beta waitlist of 150+ users collected and pre-screened (health-conscious Indians, ages 22-45) ready for April 1 invite | Output | 150 users | 0 | 187 users | 100% | Ananya | Achieved

## Q1 Initiatives List
Initiative | Links to KR | Owner | Sprint | Status
USDA bulk import — 300,000 foods into Supabase with GIN + B-tree search indexes | KR: performance targets | Arjun | Sprint 2 | Done
EER formula research — all 15 variants across age, gender, activity level | KR: EER accuracy | Arjun | Sprint 1 | Done
EER formula implementation with unit tests for all 15 variants | KR: EER accuracy | Arjun | Sprint 2 | Done
Supabase RLS policy implementation on all tables | KR: zero isolation failures | Arjun | Sprint 1 | Done
Data isolation test suite — User A vs User B scenarios | KR: zero isolation failures | Arjun | Sprint 9 | Done
Performance test suite — all PRD timing requirements | KR: performance targets | Arjun | Sprint 6 | Done
5 user interviews — urban Indian health-conscious 22-45 | KR: user interviews | Ananya/Shristi | March | Done
Pre-launch waitlist survey — Indian food gap validation | KR: 70% confirm gap | Ananya | February | Done
Beta waitlist collection via Instagram + nutritionist network | KR: 150 users | Ananya | Jan-Mar | Done
Competitive analysis — MFP vs HealthifyMe vs Cronometer | KR: competitive analysis | Shristi | March | Done late
End-to-end demo dry run with full team | KR: clean demo | Shristi | Mar 25 | Done

## Q1 Review
Overall Assessment ? Q1 2025 was a quarter of strong achievements tempered by critical lessons in user research and testing.
OBJECTIVE 1
We successfully achieved all key results for Objective 1, with the EER formula reaching 100% accuracy and zero data loss. All performance targets were met, which reflects the hard work and dedication of our engineering team, particularly Arjun's leadership in ensuring robust backend performance. This success sets a solid foundation for future enhancements and user trust in our app's reliability.
OBJECTIVE 2
For Objective 2, we completed 3 out of the 5 planned user interviews, which was a significant shortfall in our original goal. While we confirmed the Indian food gap at 73% and documented 31 foods, the delay in conducting the remaining interviews hindered our ability to gather comprehensive insights. The missed interviews were primarily due to scheduling conflicts and a lack of prioritization in our marketing efforts, which we must address moving forward.
OBJECTIVE 3
We achieved our goal for Objective 3 by successfully shipping the MVP on March 31, which included a waitlist of 187 users and a completed technical specification by January 10. This accomplishment demonstrates our ability to execute under tight deadlines and reflects the collaborative efforts of the entire team. However, we learned that the FoodDiaryContext was deferred three times and became NUTR-BUG-001 in beta, highlighting the importance of timely decision-making in our development process.
3 THINGS TO CARRY FORWARD
Thing 1 ? Prioritize user interviews and establish a clear timeline to ensure all planned interviews are completed in future quarters.
Thing 2 ? Implement user testing for all features, including visual elements like the bar graph, well in advance of launch to gather critical feedback.
Thing 3 ? Develop a more agile approach to feature development to avoid deferrals and ensure timely delivery of critical components.

## Q2 OKRs
Objective | Key Result | KR Type | Target | Baseline | Current Value | % Complete | Owner | Status | Notes
Prove Nutrivana creates genuine daily nutrition tracking habits — not just downloads | Day 7 retention reaches 50% by June 30 | Outcome | 50% | 34% (beta week 1) | 47% | 94% | Shristi | Partial
| 40% of active users log food across breakfast, lunch AND dinner at least once per week by end of June | Outcome | 40% | 22% (beta) | 43% | 100% | Shristi | Achieved
| Average food logging streak (consecutive days) reaches 5 days by end of June | Outcome | 5 days | 2.3 days (beta) | 4.2 days | 84% | Shristi | Partial
| Users who create at least 1 custom food show 2x or higher Day 30 retention vs users who do not | Outcome | 2x | Hypothesis | 2.3x | 100% | Arjun/Shristi | Achieved
Make Nutrivana the nutrition app Indian users actually come back to — not just the one they downloaded once | 3000 MAU by June 30 | Output (growth) | 3000 | 0 (pre-launch) | 3512 | 100% | Ananya | Achieved
| 200+ custom Indian food entries created by users by June 30 — confirms Indian food gap solution is working | Outcome | 200 | 47 (beta) | 847 | 100% | Shristi | Achieved
| App Store rating reaches 4.0 or above by June 30 | Outcome | 4.0 | 3.8 (beta avg) | 4.2 | 100% | Shristi | Achieved
| NPS score of 35 or above by end of May, 40 or above by June 30 | Outcome | 35 by May, 40 by June | Unknown (first NPS May 20) | 41 | 100% | Ananya | Achieved
| Users who log Indian foods (via custom food or USDA Indian entries) have 20% higher Day 7 retention than users who do not | Outcome | 20% higher | Hypothesis | 31% higher | 100% | Shristi/Arjun | Achieved
Discover one unexpected insight that fundamentally changes what we build in Q3 | Identify at least one user segment with 3x or more engagement than overall average by May 31 | Outcome | 1 segment | None identified | Pregnant women segment | 100% | Shristi | Achieved
| Complete user research with minimum 13 users across 3 different user personas by May 31 | Output | 13 interviews | 3 done in Q1 | 13 interviews | 100% | Ananya/Shristi | Achieved
| 7 out of 10 users validate top 3 V2 features as important enough to prioritise over new user acquisition | Outcome | 70% validation | 0 | 70% | 100% | Shristi | Achieved
| Feature adoption report completed for Custom Food and Nutrient Analysis by May 31 | Output | 2 reports | 0 | 2 reports | 100% | Shristi | Achieved
Build a marketing foundation that generates organic trust — not just paid installs | 2 or more nutritionist partnerships generating active recommendations to their clients | Outcome | 2 | 0 | 2 | 100% | Ananya | Achieved
| Instagram following reaches 500 with engagement rate above 4% (not just follower count) | Outcome | 500 followers + 4% ER | 0 | 623 followers, 5.2% ER | 100% | Ananya | Achieved
| At least 3 user testimonials from beta users published on app store and website | Output | 3 testimonials | 0 | 7 testimonials | 100% | Ananya | Achieved
| 1 piece of earned media coverage in a health or nutrition publication | Output | 1 article | 0 | 0 articles | 0% | Ananya | Not Achieved

## Q2 Initiatives List
Initiative | Links to KR | Owner | Sprint | Status
Beta launch — 200 users April 1 | MAU, Day 7 retention baseline | Shristi/Ananya | Sprint 7 | Done
All P1 beta bugs fixed by April 28 | Day 7 retention, App Store rating | Arjun/Priya | Sprints 7-8 | Done
Bar graph redesign (AN-CR-001) | NPS, App Store rating | Kabir/Priya | Sprint 8 | Done
Public launch May 1 with full marketing | MAU 3000 | All | Sprint 9 | Done
Instagram campaign — fitness and health communities | MAU, Instagram following | Ananya | April-June | In Progress
NPS survey round 1 — May 20 | NPS KR | Ananya | May | Done
NPS survey round 2 — June 30 | NPS KR | Ananya | June | Done
User research — 10 beta users May | Discovery objective | Ananya/Shristi | May | Done
User research — pregnant women segment June | Discovery objective | Shristi | June | Done
Feature adoption report — Custom Food | Discovery objective | Shristi | May | Done
Feature adoption report — Nutrient Analysis | Discovery objective | Shristi | May | Done
Nutritionist outreach — 5 approached, 2 target | Nutritionist KR | Ananya | April-May | Partial
User testimonial collection from happy beta users | Testimonial KR | Ananya | May | Done
App Store listing optimisation — keywords, screenshots | App Store rating | Ananya/Kabir | April | Done
Retention cohort analysis — monthly | Day 7 retention KR | Arjun/Shristi | Monthly | Ongoing
Custom food retention correlation analysis | Custom food 2x KR | Arjun | June | Done

## Q2 Review
Overall Assessment ? This quarter was a mixed bag, with significant wins overshadowed by critical retention challenges.
OBJECTIVE 1
In Q2, we successfully exceeded our MAU target, reaching 3,512 users against a goal of 3,000, which reflects the effectiveness of our marketing strategies led by Ananya. Additionally, we achieved a remarkable NPS of 41, surpassing our target of 40, indicating strong user satisfaction. However, we missed our Day 7 retention target of 50%, achieving only 47%, primarily due to a 38% drop-off at the goal-setting step, which we failed to address in time. This retention issue is a clear signal that we need to refine our onboarding process to better support users in setting their goals.
OBJECTIVE 2
We made significant strides in our custom foods feature, with 847 custom foods created, far exceeding our target of 200. This success is particularly noteworthy as it led to a 2.3x retention rate for users engaging with custom foods, which is the most important product insight we've gained this quarter. However, we completely failed to generate any earned media articles, which was a key performance indicator for our marketing efforts. This failure highlights a gap in our outreach strategy that needs immediate attention to leverage our product successes in the public domain.
OBJECTIVE 3
Our exploration into user engagement revealed that pregnant women showed a 3.1x engagement rate, which is a significant finding that will shape our strategy for Q3. This insight opens up new avenues for targeted marketing and feature development tailored to this demographic. While we achieved our App Store rating of 4.2, exceeding the 4.0 target, we need to ensure that our product enhancements resonate with all user segments, not just the engaged ones. The combination of these insights will be crucial as we pivot our focus towards enhancing user experience and retention in the upcoming quarter.
3 THINGS TO CARRY FORWARD
Thing 1 ? Implement a more robust onboarding process that specifically addresses the goal-setting step to reduce drop-off rates.
Thing 2 ? Develop a targeted marketing strategy for pregnant women to capitalize on the high engagement rates discovered this quarter.
Thing 3 ? Create a dedicated plan for earned media outreach to ensure we leverage our product successes and improve visibility.