## Sprint Summary
Ticket | Committed | Delivered | Notes
RES-002 | Yes | Yes | June 3 — 2.3x confirmed, first-3-sessions insight discovered, 312 unique foods vs 847 entries distinction documented
RES-003 | Yes | Yes | June 2 — 67% weekly analysis engagement confirmed, 29% lift from AN-CR-001 redesign
RES-004 | Yes | Yes | June 4 — 38% drop-off confirmed, 80% of abandoners churn within 3 days, 1.8 min abandon time documented
RES-005 | Yes | Yes | June 3 — goal setup confusion in March interviews mapped to funnel finding
RES-006 | Yes | Yes | June 2 — no competitive threats identified, Nutrivana differentiation intact
MET-001 | Yes | Yes | June 4 — all 4 weeks of May locked, MAU 1,247 verified
RET-001 | Yes | Yes | June 2 — custom food users Day 30 retention 34% vs 15%, gap widening at Day 14
BUG-012 | Yes | Yes | June 4 — source_type filter added, regression test added
FUN-001 | Yes | Yes | June 4 — both funnels complete, 100% internal vs 62% real-world completion documented

## Retrospective Narrative
Retrospective Narrative
Sprint Summary | Sprint 11 was a pivotal sprint for Nutrivana, yielding critical insights that directly inform our Q3 priorities. We confirmed the custom food retention correlation and identified significant user drop-off points, enabling us to refine our onboarding process.
What Went Well | 1. The discovery of the first-3-sessions custom food insight in RES-002 was a significant win for our onboarding strategy. Arjun's analysis revealed that users who create their first custom food within the first three sessions have a Day 30 retention rate of 41%, compared to just 15% for those who do not. This insight will fundamentally change how we design the onboarding experience. 2. The validation of the March user interview data in RES-005 was another highlight. It demonstrated a consistent pattern across different research methods, indicating that goal setup confusion was a real issue for users. This methodological consistency gives us high confidence in our decision to simplify the onboarding process, which is a major step forward. 3. The competitive analysis in RES-006 confirmed that Nutrivana's differentiation remains strong. With no new competitors entering the market and our unique offerings intact, we can confidently focus on expanding our reach, particularly in the pregnant women segment, which is currently underserved.
What Did Not Go Well | 1. The analysis for RES-004 took the entire sprint instead of the planned five days. This delay stemmed from the need to validate timestamp data integrity across three tables, which is a reminder that research dependent on data quality validation can be time-consuming. We need to account for this in future sprint planning. 2. We recognized a pattern of waiting for data confirmation before acting on clear user signals, as highlighted in RES-005. The goal setup confusion was identified in March, but we did not act until June, resulting in three months of unnecessary churn. This is a recurring issue that we must address to improve our responsiveness to user feedback.
Key Learnings | 1. We must prioritize acting on user signals from qualitative research more swiftly. The goal setup confusion was evident in March, and delaying action until June resulted in avoidable churn. 2. The insight regarding the first-3-sessions window fundamentally shifts our perspective on onboarding. It emphasizes the importance of personalizing the user experience early on to enhance retention. 3. The disparity between internal testing completion (100%) and real-world completion (62%) indicates that we need to involve users who were not part of the feature development in our testing processes to ensure we capture genuine user behavior.
Decisions Made | 1. Simplified onboarding has been confirmed as the top priority for Sprint 12, backed by data showing a 38% drop-off rate and 80% of abandoners churning within three days. 2. We will integrate a custom food creation nudge into the simplified onboarding flow, as the first-3-sessions data supports its inclusion as a core feature. 3. Moving forward, internal testing must always include users who were not involved in building the feature to mitigate biases and ensure a more accurate representation of user behavior.
Action Items
Action | Owner | Due Date
Start simplified onboarding Figma designs | Kabir | June 10
Share 38% funnel data with Ravi as part of Q3 rationale | Shristi | June 12
Add custom food nudge to simplified onboarding brief | Shristi | June 12
Build the A/B test infrastructure for Sprint 12 | Arjun | June 13
Identify users who abandoned goal setup for simplified onboarding user testing | Ananya | June 12
Team Health | 4/5 | The team demonstrated strong collaboration and insight generation during this sprint. However, the delay in addressing user signals indicates we have room for improvement in our responsiveness to feedback.

## Metrics This Sprint
Metric | Value
Custom food 2.3x retention correlation | Confirmed — 34% vs 15% Day 30
Custom food first-3-sessions retention | 41% Day 30 vs 15% never
Goal setting abandonment rate | 38% of users who start
Abandoners who churn within 3 days | 80%
Average time on EER form — abandoners | 1.8 minutes
Average time on EER form — completers | 4.2 minutes
Analysis engagement weekly | 67% of active users
Analysis engagement before AN-CR-001 | 52%
Analysis engagement after AN-CR-001 | 67% (29% improvement)
MAU end of May confirmed | 1,247
Day 7 retention end of May | 45%
Custom foods cumulative end of May | approximately 300
Unique custom food names | 312
March user interviews — goal setup confusion mentions | 4 of 8 users
Internal testing goal setup completion | 100%
Real user goal setup completion | 62%