## Sprint Summary
Ticket | Committed | Delivered | Notes
ONBD-001 | Yes | Yes | June 16 — user tested with 3 previous abandoners, all 3 completed in under 2 minutes
ONBD-002 | Yes | Yes | June 18 — neutral defaults within 200 calories of full EER, profile completion trigger working
ONBD-003 | Yes | Yes | June 19 — Shristi completed in 1 min 47 sec from fresh account
PRE-001 | Yes | Yes | June 16 — ICMR values confirmed, Pregnant added as fourth goal option
PRE-002 | Yes | Yes | June 17 — trimester calculation and notification system complete
MET-002 | Yes | Yes | June 16 — June week 1 MAU 1,456, week 2 MAU 1,847
ONBD-004 | Yes | Yes | June 18 — A/B test live, preliminary 84% vs 61% after first week
BUG-013 | Yes | Yes | June 16 — Day 7 retention definition standardised across all reports
MKT-002 | Yes | In Progress | Pitch document ready, outreach begins Sprint 13
NPS-002 | Yes | Yes | June 14 — survey configured, ready for June 30 launch
PRE-003 | Yes | Partial | June 20 — Sprint 12 scope complete, Sprint 13 scope carries over as planned

## Retrospective Narrative
Retrospective Narrative
Sprint Summary | Sprint 12 was the most productive sprint since Sprint 6 (MVP). The team returned to building after two research sprints with complete clarity on what to build and why, resulting in a successful delivery of 10 out of 11 committed tickets.
What Went Well | 1. The ONBD-001 user testing result was extraordinary. Kabir tested the Figma prototype with 3 users who had previously abandoned the original EER onboarding (identified from funnel data by Ananya). All 3 completed the simplified flow in under 2 minutes, validating our redesign approach. 2. The ICMR prenatal research was thorough and clinically grounded, as documented in PRE-001. Using ICMR values over WHO values because Indian pregnant women have higher baseline iron and B12 deficiency rates is a product decision that shows genuine care for our specific users. Ananya's real-world validation gave us the confidence to commit to this approach. 3. The A/B test infrastructure Arjun built is clean and reusable, as seen in ONBD-004. The onboarding_variant column in user_profiles is the pattern we should use for all future A/B tests, allowing for simple, auditable, and permanent ties to user records for post-test analysis.
What Did Not Go Well | 1. Sprint 12 was the most ambitious sprint by story points (38). While everything was delivered, the team felt stretched in the final week with ONBD-003, PRE-003, and ONBD-004 all in flight simultaneously. This level of workload is acceptable for one sprint but should not become the regular pace, as it risks team burnout. 2. MKT-002 press pitch is ready but no outreach happened this sprint. Although Ananya built the pitch document, the actual outreach to publications requires a dedicated sprint focus that was not available with the simplified onboarding and prenatal work also in progress. This highlights the need for clearer prioritization in future sprints.
Key Learnings | 1. Data-justified sprints move faster than intuition-justified sprints. Every Sprint 12 decision had a data source, which allowed the team to spend less time debating scope and more time building. 2. Using previous abandoners as the user testing pool for ONBD-001 was the correct approach. Testing a redesign with users who failed tells you if the redesign solves the actual problem, which is crucial for effective product development. 3. ICMR vs WHO is not just a data choice — it is a positioning choice. Using ICMR values communicates that we serve Indian users specifically, which strengthens our brand identity.
Decisions Made | 1. Simplified onboarding ships to 100% of users in Sprint 13 pending A/B test final results. 2. ICMR values used for all prenatal presets, documented in technical spec under Data Sources. 3. Day 7 retention standard definition locked: user who opens app AND logs at least one food item on exactly day 7 from registration date. 4. Prenatal preset attribution line: Targets based on ICMR dietary guidelines for Indian pregnant women.
Action Items
Action | Owner | Due Date
Complete PRE-003 — notification UI, edge cases, user testing | Priya | June 26
Ship simplified onboarding to 100% once A/B test final results available | Arjun | June 28
Launch NPS-002 survey June 30 | Ananya | June 30
Begin press outreach with pregnant women story angle | Ananya | June 25
Complete Q2 OKR review | Shristi | June 30
Team Health | 4/5 | The combination of clear data-driven priorities and significant product wins created a high energy level, though the stretched final week was taxing.

## Metrics This Sprint
Metric | Value
Simplified onboarding A/B test — simplified completion | 84% (preliminary after 1 week)
Simplified onboarding A/B test — control completion | 61%
Simplified onboarding average time — simplified | 1.9 minutes
Simplified onboarding average time — control | 4.1 minutes
MAU June week 1 (June 1-7) | 1,456
MAU June week 2 (June 8-14) | 1,847
Day 7 retention June week 2 | 46%
Custom foods cumulative June 23 | approximately 634
App Store rating | 4.1
ONBD-001 user test: previous abandoners who completed simplified flow | 3 of 3
PRE-001 user validation: OB-GYN prescribed values matching ICMR | confirmed by 1 user
A/B test users in simplified group | 50% of new registrations from June 19