## Sprint Summary
Ticket | Committed | Delivered | Notes
PRE-003-COMPLETE | Yes | Yes | June 26 — 87 second average setup, all 11 pregnant users updated within 24 hours
ONBD-005 | Yes | Yes | June 28 — 84.7% vs 61.3% final A/B result, Day 7 retention 47.3% vs 43.1%
MET-003 | Yes | Yes | June 30 — all Q2 closing numbers verified: MAU 3512, retention 47%, NPS 41
Q2-REVIEW-001 | Yes | Yes | June 30 — shared with team and Ravi, all 4 objectives assessed honestly
RET-002 | Yes | Yes | June 30 — simplified onboarding users 51.2% Day 7 retention
BUG-014 | Not in plan | Yes | June 26 — discovered and fixed within 4 hours post-deployment
INVEST-001 | Yes | Yes | June 30 — Ravi responded same evening
MET-004 | Yes | Yes | June 30 — top 10 custom foods list locked, all 847 entries verified

## Retrospective Narrative
Retrospective Narrative
Sprint Summary | Sprint 13 closed Q2 on time and on quality. The team successfully delivered all committed features, including prenatal presets and simplified onboarding, while achieving significant user growth and retention metrics.
What Went Well | 1. The delivery of ticket PRE-003-COMPLETE was a standout success, with an average setup time of just 87 seconds for prenatal presets. This rapid adoption is unprecedented in our project history and reflects the team's hard work in understanding user needs, particularly for pregnant users who were all updated within 24 hours. 2. The swift response to BUG-014 was impressive, with the team identifying the root cause within an hour and deploying a fix in just 4 hours. This aligns with the health-critical response standard we established after GOAL-BUG-002, demonstrating our commitment to quality and user safety. 3. The Q2 OKR review (ticket Q2-REVIEW-001) was candid and thorough, highlighting our retention miss while providing a clear analysis of the drop-off reasons. This level of transparency will be invaluable for stakeholders and future team members, as it lays out the exact causes and corrective actions taken.
What Did Not Go Well | 1. Despite our successes, BUG-014 should not have reached production, as the testing for the prenatal presets did not cover the analysis screen. This oversight indicates a gap in our testing coverage, which we need to address by updating our definition of done to include verification on all relevant screens for future features. 2. The press outreach campaign (MKT-002) did not yield any media coverage, as Ananya's pitches to 4 publications received zero responses. This highlights the need for a more strategic approach to media relations, particularly in building relationships with journalists before pitching, as cold outreach proved ineffective.
Key Learnings | 1. Targeted features, like the prenatal presets, that address specific user needs lead to significantly higher adoption rates. This reinforces the importance of user research and tailored solutions in our product development process. 2. The lesson learned from BUG-014 emphasizes that testing must encompass all screens affected by a feature, not just the new ones. Moving forward, we must ensure comprehensive testing protocols are in place to prevent similar issues. 3. The Q2 OKR review process showed that focusing on fixing existing issues rather than adding new features can yield better retention results. For Q3, we should allocate at least one sprint dedicated to optimizations and fixes.
Decisions Made | 1. Simplified onboarding is now standard for all new users, with the A/B test code removed. 2. Prenatal presets shipped with ICMR values as standard, and the BUG-014 fix applied with regression tests in place. 3. Any feature touching micronutrient display must verify correct units on all screens where micronutrients appear. 4. Q3 will include at least one dedicated improvement sprint focusing solely on fixes and optimizations.
Action Items
Action | Owner | Due Date
Q3 OKR planning session | Shristi | July 7
Press outreach strategy revision — relationship-first not cold pitch | Ananya | July 7
Q3 sprint planning with simplified onboarding as standard baseline | All | July 7
Custom recipe builder technical design begins | Arjun | July 8
Prenatal marketing to OB-GYN offices and maternal health communities | Ananya | July 10
Team Health | 4/5 | The team is in a strong position with solid metrics and a clear path forward, but we need to address testing gaps and improve our media outreach strategy.

## Metrics This Sprint
Metric | Value
MAU June 30 (Q2 final) | 3,512
Day 7 retention June 30 (Q2 final) | 47%
App Store rating June 30 | 4.2
NPS June 30 | 41
Custom foods June 30 | 847 total entries, 312 unique food names
Top custom food | Chapati — 234 entries
Simplified onboarding completion (simplified group) | 84.7%
Simplified onboarding completion (control group) | 61.3%
Simplified onboarding Day 7 retention (simplified) | 47.3%
Simplified onboarding Day 7 retention (control) | 43.1%
Prenatal presets average setup time | 87 seconds
Pregnant users updated to prenatal presets within 24hr | 11 of 11
BUG-014 time from discovery to fix | 4 hours
MAU growth since launch (May 1 to June 30) | 847 → 3,512 (315%)
Paid acquisition contribution to growth | Zero
Partnership-driven organic installs | 412 (Nambiar 267, Kavitha 145)
Instagram followers | 623 at 5.2% engagement rate
Q2 OKR objectives achieved or partially achieved | 4 of 4
Q2 OKR KRs fully achieved | 13 of 17