## Sprint Summary
Ticket ID | Committed | Delivered | Notes
TECH-001 | Yes | Yes | Delivered Jan 8 — 2 days ahead of estimate
TECH-003 | Yes | Yes | Delivered Jan 10 — JWT + refresh token implemented
NUTR-TASK-003 | Yes | Yes | Delivered Jan 11 — goal_snapshots pattern agreed
GOAL-SPIKE-001 | Yes | Yes | Delivered Jan 7 — 15 formula variants documented
GOAL-SPIKE-002 | Yes | Yes | Delivered Jan 9 — RDA table completed
NUTR-EPIC-001 | Yes | Yes | Epic created with all child tickets listed
GOAL-EPIC-001 | Yes | Yes | Epic created
GOAL-EPIC-002 | Yes | Yes | Epic created
Overall delivery rate |  |  | Delivery rate was 100%, with all 8 tickets committed and delivered successfully.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | Sprint 1 was a foundational sprint focused on establishing the technical groundwork for Nutrivana, which involved critical architectural decisions and discussions.
What went well | 1. Arjun's spike-first approach worked perfectly. By completing GOAL-SPIKE-001 and GOAL-SPIKE-002 before any implementation, the team had complete EER formula and RDA data before a single line of goal setting code was written. 2. The NUTR-TASK-003 debate about empty diary representation was the most valuable architectural conversation of the entire project. Shristi caught the empty diary problem by reading the PRD requirement carefully, ensuring past diary entries always show the correct goal structure for that date. 3. The TECH-003 auth debate about session persistence vs JWT expiry was resolved well. The decision to implement a 1-hour access token with a 30-day refresh token gives users a seamless experience without compromising security.
What did not go well | 1. Priya's mid-sprint start on January 7 meant she had no input on TECH-001 database schema or TECH-003 auth before they were implemented. This led to her raising two frontend concerns on January 8 that required minor schema adjustments, highlighting the need for earlier involvement. 2. The technical spec was not completed by January 10 as planned. Although Arjun completed Sections 1-4, Sections 5-10 were not written until after Sprint 2, resulting in an incomplete spec at the time of approval.
Key learnings | 1. Architecture decisions need to be made before feature implementation, as demonstrated in Sprint 1. Two weeks of architecture work prevents months of rework, which is crucial for project efficiency. 2. Spike research should always happen one sprint before the implementation sprint. The results from GOAL-SPIKE-001 directly unblocked GOAL-001 and GOAL-002 in Sprint 2, showcasing the importance of timely research. 3. A full team review of the database schema before implementation is non-negotiable. This ensures that all team members, including those onboarding, are aligned and can contribute effectively.
Decisions made | 1. The dual date storage approach was adopted, using a local date_string for queries and a UTC timestamp for audit. This decision prevents midnight boundary bugs for IST users. 2. The JWT + 30-day refresh token strategy was implemented to enhance user experience. Users will not see the login screen if they open the app within 30 days. 3. The goal_snapshots pattern was established for date-accurate diary rendering. This architectural decision is crucial for maintaining the integrity of user data across different dates.
Action items
Action | Owner | Due Date
Complete Technical Spec Sections 5-10 | Arjun | Jan 28
Priya to review TECH-001 schema and raise any frontend concerns | Priya | Jan 15
Shristi to finalise PRDs for Food Logging and Goal Setting before Sprint 3 | Shristi | Jan 28
Ananya to share waitlist signup page with team for review | Ananya | Jan 15
Team health rating | 4/5 | The team had a strong start and was aligned on architecture. Priya's late start created minor friction but was resolved quickly, and team capacity is expected to balance in Sprint 2.

## Metrics This Sprint
Metric | Value / Details
Database tables designed | 12 tables
RLS policies implemented | 12 (one per table)
EER formula variants documented | 15
Micronutrients with RDA values documented | 40+
Authentication | JWT + refresh token implemented and tested