## Sprint Summary
Ticket ID | Committed | Delivered | Notes
NUTR-TASK-001 | Yes | Yes | Delivered Jan 24. USDA rate limit discovery → bulk import
NUTR-TASK-002 | Yes | Yes | Delivered Jan 27. Hybrid ILIKE + trigram solution
GOAL-001 | Yes | Yes | Delivered Jan 25. PRD activity level mismatch resolved
GOAL-002 | Yes | Yes | Delivered Jan 27. All 15 EER variants with unit tests
GOAL-003 | Yes | Yes | Delivered Jan 25
GOAL-004 | Yes | Yes | Delivered Jan 26
Overall delivery rate |  |  | 6 out of 6 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | In Sprint 2, we encountered significant challenges with external data sources, particularly the USDA API's limitations and the absence of common Indian foods. However, the team demonstrated agility by pivoting to a bulk import solution and implementing a hybrid search approach. Overall, we delivered all committed tickets and made crucial product decisions to address the gaps identified.
What went well | 1. Arjun's quick identification of the USDA rate limit issue on Day 1 led to a rapid pivot to a bulk import solution, showcasing effective problem-solving. 2. The hybrid ILIKE + trigram search solution implemented in NUTR-TASK-002 improved search performance to under 200ms, thanks to Priya's testing insights. 3. The clear decision to standardize on 4 USDA activity levels in GOAL-001 eliminated ambiguity and streamlined our PRD.
What did not go well | 1. The extent of the Indian food gap was a significant oversight; we should have investigated this risk in Sprint 1. 2. Arjun's workload was disproportionately high, carrying the majority of the sprint's tasks, which highlighted an imbalance in team contributions. 3. The lack of a proactive risk assessment for external data sources resulted in unexpected challenges that impacted our planning.
Key learnings | 1. Always validate external data sources for coverage before relying on them in product development. 2. Early detection of architectural issues can save significant rework; pivoting to bulk import early was crucial. 3. Distributing workload more evenly among team members is essential to maintain morale and productivity.
Decisions made | 1. Adopted USDA bulk import instead of real-time API for better performance. 2. Fast-tracked the Custom Food feature to Sprint 5 to address the Indian food gap. 3. Updated PRD to reflect 4 activity levels based on USDA standards.
Action items
Action | Owner | Due date
Add Custom Food to roadmap and create epic NUTR-CF-EPIC-001 | Shristi | Feb 3
Document Indian food gap — top 20 missing foods with user priority | Shristi/Ananya | Feb 10
Write unit tests for all 15 EER formula variants | Arjun | Feb 3
Begin reviewing GOAL-001 through GOAL-004 frontend requirements | Priya | Jan 29
Team health rating | 4 | Good sprint despite surprises. The team's ability to pivot quickly on the USDA rate limit issue was impressive. However, the Indian food gap discovery created anxiety about product viability, which we addressed by fast-tracking the Custom Food feature. Overall morale is good, but workload distribution needs attention.

## Metrics This Sprint
Metric | Value
Search response time | 200ms average after implementing hybrid search solution
Tickets delivered | 6 out of 6 tickets delivered successfully
Workload distribution | Arjun handled 5 out of 6 tickets, indicating a need for better task distribution