## Sprint Summary
Ticket ID | Committed | Delivered | Notes
GOAL-005 | Yes | Yes | Feb 3 — first-time check for default correctly implemented
GOAL-006 | Yes | Yes | Feb 4 — no debounce decision made
GOAL-007 | Yes | Yes | Feb 8 — floating point fix parseFloat(toFixed(2))
GOAL-008 | Yes | Yes | Feb 5 — untracked macros still recalculate
GOAL-009 | Yes | Yes | Feb 10 — PRD override: tabs → single scroll
GOAL-010 | Yes | Yes | Feb 6 — auto-recalculate on age/gender change
GOAL-011 | Yes | Yes | Feb 7 — custom override never touched by system
GOAL-012 | Yes | Yes | Feb 3 — Potassium unit discrepancy handled
NUTR-005 | Yes | Yes | Feb 10 — horizontal scroll confirmed intentional
NUTR-006 | Yes | Yes | Feb 10 — supplement toggle confirmed persistent
Overall delivery rate |  |  | 10 out of 10 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | Sprint 3 completed the entire goal setting feature. By the end of this sprint, a user can set calorie, macro, and micronutrient goals completely. Two notable things happened: (1) Priya discovered a real JavaScript floating point precision bug in GOAL-007 that would have caused validation failures for users entering 33.33/33.33/33.34. The fix (parseFloat(toFixed(2))) is now applied consistently. (2) The team made their first PRD override — changing the micronutrient list from tabs to single scroll based on Ananya's user feedback about discoverability.
What went well | 1. The floating point discovery in GOAL-007 shows the value of Priya testing edge cases. 33.33 + 33.33 + 33.34 = 99.99999999 in JavaScript. This would have frustrated users trying to set equal macro splits. Caught and fixed before any user saw it. 2. The PRD override on GOAL-009 (tabs to single scroll) was the team's first independent product decision. Kabir proposed it, Ananya validated it with user perspective, and Shristi approved. The decision was made and documented in 48 hours. 3. Priya's performance this sprint was outstanding. She took ownership of 5 out of 10 tickets, including GOAL-006 and GOAL-010, and delivered all of them on time. This improved balance in team capacity was a huge boost for our overall productivity.
What did not go well | 1. GOAL-009 took the longest of any Sprint 3 ticket, lasting 11 days versus the 3-day estimate. This was due to the PRD override requiring new Figma designs from Kabir, implementation changes from Priya, and a final design review. PRD overrides need to be flagged as scope-change risks in sprint planning. 2. The Potassium unit discrepancy in GOAL-012 (target in grams, data in mg) was caught late — on the day of implementation. This indicates that data quality checks on reference data should happen before the implementation sprint, not during.
Key learnings | 1. PRD overrides add scope — flag them explicitly in sprint planning as a risk. GOAL-009 took 4x estimated time because of the unplanned redesign. 2. Floating point arithmetic is a recurring source of bugs in nutrition calculations. The parseFloat(toFixed(2)) approach is now a team standard for all nutrient value displays. 3. Ananya's user perspective was critical in the GOAL-009 decision. She should be more involved in design reviews earlier, not just as a late-stage validator.
Decisions made | 1. Micronutrient list: single scroll with sticky category headers instead of tabs (GOAL-009). PRD updated. 2. parseFloat(toFixed(2)) rounding standard for all numeric nutrient displays (from GOAL-007 fix). 3. Untracked macros still recalculate in background — they are hidden from diary but values remain accurate if re-enabled (GOAL-008). 4. Supplement toggle is a persistent global setting, not a per-day toggle (NUTR-006).
Action items
Action | Owner | Due date
Add PRD override documentation process to team norms | Shristi | Feb 15
Apply parseFloat(toFixed(2)) audit across all existing calculation code | Priya/Arjun | Feb 20
Ananya to join all design reviews from Sprint 4 onwards | Shristi | Ongoing
Schedule data quality pre-check for USDA nutrient data before Sprint 4 | Arjun | Feb 14
Team health rating | 5/5 | Best sprint energy so far. Priya fully in flow. Kabir producing great designs. The floating point find and the PRD override both gave the team confidence in their own judgement. No escalations needed this sprint. Team working well together.

## Metrics This Sprint
Metric | Value
Total Tickets Committed | 10
Total Tickets Delivered | 10
Average Ticket Delivery Time | 5 days