## Sprint Summary
Ticket ID | Committed | Delivered | Notes
NUTR-007 | Yes | Yes | Feb 17 — two-step API design
NUTR-008 | Yes | Yes | Feb 17 — 2-char minimum added
NUTR-009 | Yes | Yes | Feb 24 — food-specific serving units discovered
NUTR-010 | Yes | Yes | Feb 19 — optimistic update pattern
NUTR-015 | Yes | Yes | Feb 20 — dash for zero and missing confirmed
NUTR-016 | Yes | Yes | Feb 22 — sticky total row
NUTR-017 | Yes | Yes | Feb 23 — weight maintain yellow not red
NUTR-018 | Yes | Yes | Feb 22 — always show even single food
NUTR-TASK-004 | Yes | Yes | Feb 24 — client-side calculation engine
Overall delivery rate |  |  | 9 out of 9 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | Sprint 4 was a landmark sprint for Nutrivana, culminating in a successful demo on February 24 that showcased our product's capabilities. We made significant architectural discoveries, particularly around food-specific serving units, which enhanced our understanding of the USDA data. However, we also identified areas for improvement, particularly in managing technical debt and scope changes.
What went well | 1. The discovery of food-specific serving units in NUTR-009 was a major win for our team. Arjun's deep dive into USDA data led to a swift resolution thanks to collaboration with Kabir and myself, allowing us to implement a solution in just one day. 2. The client-side calculation engine in NUTR-TASK-004 proved to be an excellent architectural choice. This decision ensures that our app maintains a 1-second performance even on slower connections, significantly improving user experience and preventing latency issues. 3. The implementation of the weight maintain color coding in NUTR-017 was executed flawlessly. By deciding to use yellow instead of red for over-calorie indicators, we established a clear and consistent visual cue across the app, enhancing user understanding.
What did not go well | 1. The FoodDiaryContext, identified as necessary, was not implemented this sprint, which has resulted in NUTR-BUG-001 and AN-BUG-003 for Sprint 7. This oversight highlights the need to prioritize critical architectural tasks to avoid accumulating technical debt. 2. NUTR-009 took the entire sprint, 12 days, instead of the estimated 5 days. This unexpected scope increase due to architectural discoveries should have been flagged earlier as a sprint risk, allowing us to adjust our plans accordingly.
Key learnings | 1. Deferred architectural work like the FoodDiaryContext can lead to future bugs. If something is identified as necessary, we should prioritize building it immediately. 2. We need to validate assumptions about the USDA data structure before planning implementation sprints. The unexpected serving units were a surprise that could have been avoided. 3. The optimistic update pattern should become our standard for all diary operations. We need to document this as a team pattern to ensure consistency moving forward.
Decisions made | 1. Utilize food-specific serving units from USDA data instead of a generic dropdown list (NUTR-009). 2. Implement a client-side calculation engine for food log array state changes (NUTR-TASK-004). 3. Adopt yellow for both over and under-calorie indicators for weight maintenance, avoiding red (NUTR-017). 4. Establish optimistic update as the standard pattern for all diary API operations (NUTR-010). 5. Ensure the sticky total row is always visible while scrolling (NUTR-016).
Action items
Action | Owner | Due date
Implement FoodDiaryContext in Sprint 5 before it is needed | Priya/Arjun | Mar 3
Audit USDA data structure for any other unexpected formats | Arjun | Mar 1
Document optimistic update pattern in technical spec | Arjun | Mar 7
Schedule full February 24 demo recording for Ananya to share with waitlist | Ananya | Feb 28
Team health rating | 5 | The excitement from the end-to-end functionality of the food diary on February 24 has boosted team morale significantly. Collaboration between Priya and Arjun was particularly effective during this sprint, and Kabir's design system continues to expedite our implementation process.

## Metrics This Sprint
Metric | Value
Total tickets delivered | 9
Average days to complete NUTR-009 | 12 days
Performance guarantee with client-side calculations | 1 second