## Sprint Summary
Ticket ID | Committed | Delivered | Notes
NUTR-011 | Yes | Yes | Mar 3 — reusable search component
NUTR-012 | Yes | Yes | Mar 3 — two-column list with calorie
NUTR-013 | Yes | Yes | Mar 4 — skip portion adjust for custom meal
NUTR-014 | Yes | Yes | Mar 9 — PRD override: dismissible prompt
NUTR-019 | Yes | Yes | Mar 5 — editingOriginalValues restore pattern
NUTR-020 | Yes | Yes | Mar 4 — optimistic deletion
NUTR-021 | Yes | Yes | Mar 10 — 100ms debounce for performance
NUTR-022 | Yes | Yes | Mar 10 — dual date storage IST + UTC
NUTR-023 | Yes | Yes | Mar 3 — no special logic needed
NUTR-024 | Yes | Yes | Mar 3 — auto-save via optimistic updates
NUTR-025 | Yes | Yes | Mar 4 — date_string architecture handles this
NUTR-026 | Yes | Yes | Mar 5 — USDA only bug seeded here
CF-001 | Yes | Yes | Mar 7 — serving unit free-text
CF-002 | Yes | Yes | Mar 8 — accordion grouping
Overall delivery rate |  |  | 14 out of 14 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | In Sprint 5, we successfully completed the food diary feature and made significant progress on custom food. The team delivered all 14 tickets, marking our most productive sprint yet. Notably, we tackled complex architectural challenges, made strategic product decisions, and identified areas for improvement.
What went well | 1. The reusable search component from NUTR-011 was a significant engineering achievement. It now efficiently handles USDA, custom food, and custom recipe sources, which will streamline future feature implementations. 2. The 100ms debounce solution implemented in NUTR-021 showcased our team's ability to address performance issues proactively. Priya's identification of the lag on mid-range Android devices led to a clever interpretation of the PRD, ensuring a smoother user experience. 3. The decision to implement the supplement toggle as a dismissible prompt (NUTR-014) reflects our commitment to balancing usability with design. The collaboration between Kabir and Ananya brought together design and user research insights, resulting in a more effective solution.
What did not go well | 1. The implementation of the duplicate check in NUTR-026 was limited to USDA food IDs, leaving a gap for custom food IDs. This oversight was noted during implementation but was not addressed, which will lead to NUTR-BUG-002 in Sprint 8. 2. We identified a risk of offline data loss in NUTR-024 but chose to defer a solution to V2 without any temporary mitigation. A network status indicator should have been added in Sprint 5 when the risk was first identified, rather than waiting.
Key learnings | 1. Address known gaps, such as the custom food ID issue from NUTR-026, within the same sprint to avoid higher costs of fixing them later. 2. The reusable component pattern has proven effective; we should continue to invest in abstraction early in the development process. 3. Involving multiple perspectives, like design and user research, leads to better product decisions, as seen with the supplement toggle implementation.
Decisions made | 1. The supplement toggle will be a dismissible prompt (Option C) rather than hidden or always visible (NUTR-014). 2. We decided on a dual storage approach for dates, using both local date_string and UTC timestamp (NUTR-022), ensuring a migration path for users. 3. For custom food serving units, we opted for a free-text input instead of a dropdown (CF-001), contrasting with the USDA's food-specific units. 4. We implemented a 100ms debounce on recalculation to comply with the PRD definition of 'after the action' (NUTR-021).
Action items
Action | Owner | Due date
Extend duplicate check to custom food IDs in Sprint 8 | Priya | Sprint 8
Add network status indicator in Sprint 6 | Arjun | Sprint 6
Schedule 5 user interviews for March research | Ananya | Mar 20
Complete user research report | Shristi | Mar 31
Team health rating | 5 | This was the best sprint of the project, with 100% delivery and high team confidence. Completing the food diary feature feels like a significant milestone, and our ability to execute quickly without compromising quality is encouraging.

## Metrics This Sprint
Metric | Value
Total tickets delivered | 14 tickets delivered out of 14 committed.
Sprint completion date | Sprint completed on March 11, 2025.
Team confidence level | Team confidence rated at 5/5.
Reusable search component | Handles 3 source types — USDA, custom food, custom recipe
Debounce performance improvement | 100ms applied to recalculation
IST timezone handling | Dual date storage — date_string for IST, UTC for audit
Custom food entries at sprint end | 0 — feature started but not yet live