## Sprint Summary
Ticket ID | Committed | Delivered | Notes
CF-003 | Yes | Yes | Mar 22 — zero calorie decision made
CF-004 | Yes | Yes | Mar 17
CF-005 | Yes | Yes | Mar 19
CF-006 | Yes | Yes | Mar 17 — soft delete + PRD cancel behaviour fixed
CF-007 | Yes | Yes | Mar 20 — effective_date versioning
AN-001 | Yes | Yes | Mar 19 — carousel swipe navigation
AN-002 | Yes | Yes | Mar 28 — emergency redesign 3 days before launch
AN-003 | Yes | Yes | Mar 21 — shared color function
AN-004 | Yes | Yes | Mar 24 — 0% for skipped days agreed
AN-005 | Yes | Yes | Mar 22
TECH-004 | Yes | Yes | Mar 26 — 20 query → 1 query optimisation
TECH-006 | Yes | Yes | Mar 24 — offline limitation documented
TECH-007 | Yes | Yes | Mar 26
Overall delivery rate |  |  | 13 out of 13 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | This sprint marked a significant milestone as we successfully shipped the MVP on time. The team demonstrated exceptional execution, completing all 13 tickets without deferring any scope. However, we faced a critical challenge with user testing that highlighted the importance of early feedback on visualizations.
What went well | 1. The MVP shipped on time, with every ticket completed and no deferred scope. This reflects the team's strong execution and commitment throughout the six sprints, particularly with the successful delivery of CF-003 which allowed zero calorie inputs. 2. The optimization found in TECH-004, where we reduced 20 sequential analysis queries into just 1, was crucial. This improvement ensured that our analysis page met the 2-second load time requirement, enhancing user experience significantly. 3. The decision made in CF-003 to allow zero calorie inputs was a smart move under pressure. It demonstrated our ability to make correct product decisions that align with user needs, especially for items like black coffee and plain water.
What did not go well | 1. The user confusion regarding the bar graph in AN-002 was a major concern discovered just 7 days before launch. This issue should have been identified earlier in Sprint 4 or 5 during design reviews, highlighting the need for more thorough testing of critical visualizations. 2. The specification for AN-004 was incomplete in the PRD, which required Arjun and me to define the details during implementation. This oversight should have been flagged during sprint planning to avoid confusion and delays.
Key learnings | 1. We must conduct user testing for critical visualizations at least 2 sprints before they are needed in production. 2. Incomplete sections in the PRD need to be flagged during sprint planning and completed before the sprint begins. 3. Known risks identified in retrospectives should have actionable items with due dates in the next sprint.
Decisions made | 1. Allowed zero calorie inputs (≥ 0 not > 0) for all nutrient inputs in custom food (CF-003). PRD corrected. 2. Implemented Option C patch (explicit numbers) for the bar graph in AN-002. AN-CR-001 created for proper redesign in Sprint 8. 3. Decided on 0% for days with no logs in AN-004 instead of null/gap. 4. Selected carousel swipe navigation instead of URL routing for analysis (AN-001). 5. Established that soft delete preserves diary history for custom food (CF-006).
Action items
Action | Owner | Due date
AN-CR-001 bar graph full redesign — Sprint 8 | Kabir/Priya | Sprint 8
Send beta invites | Shristi | April 1
Prepare beta feedback form | Ananya | April 1
Team celebration dinner — MVP shipped | Shristi | April 2
Sprint 7 planning — focus entirely on beta bugs | Shristi | April 1
Team health rating | 5 | The team is proud but tired after 3 months of intense building. The MVP shipped on time and with quality, but the stress from AN-002 was significant. The upcoming celebration dinner is well-deserved.

## Metrics This Sprint
Metric | Value
Features shipped | 5 (food diary, goal setting, custom food, analysis, authentication)
Performance | search 200ms, analysis load 0.8s, diary date switch 0.8s, recalculation <200ms
End-to-end demo | passed clean March 25
Beta waitlist | 187 users ready for April 1 invites
Known bugs at launch | 0 P0, 2 P1 (AN-002 patched, GOAL-BUG-004 will be discovered in Sprint 7)