## Sprint Summary
Ticket ID | Committed | Delivered | Notes
NUTR-BUG-001 | Yes | Yes | Fixed within 5 days.
NUTR-BUG-003 | Yes | Yes | Fixed within 6 days.
NUTR-BUG-004 | Yes | Yes | Fixed within 6 days.
NUTR-BUG-005 | Yes | Yes | Fixed within 5 days.
NUTR-BUG-006 | Yes | Yes | Fixed within 6 days.
GOAL-BUG-002 | Yes | Yes | Fixed within 6 days.
GOAL-BUG-003 | Yes | Yes | Fixed within 5 days.
GOAL-BUG-004 | Yes | Yes | Fixed within 6 days.
AN-BUG-002 | Yes | Yes | Fixed within 5 days.
AN-BUG-003 | Yes | Yes | Fixed within 4 days.
Overall delivery rate |  |  | 10 out of 10 tickets. 100%.

## Retrospective Narrative
Retrospective Narrative
Sprint summary | This sprint was challenging but ultimately productive as we tackled 10 bugs in 14 days. The most significant insight was the discovery that NUTR-BUG-001 and AN-BUG-003 stemmed from the same architectural debt, highlighting a need for better root cause analysis. Despite the pressure, our team's response to beta user feedback was commendable, and we managed to resolve critical issues promptly.
What went well | 1. The team's response time was exceptional. We managed to fix all P1 bugs within 6 days, including NUTR-BUG-001, which was a critical issue reported by beta users. 2. The resolution of AN-BUG-003 was particularly efficient as it was identified as a direct extension of NUTR-BUG-001. This recognition of shared root causes allowed us to save significant time and resources. 3. Ananya's communication with beta users was exceptional. By sending personal messages to those affected by GOAL-BUG-004 and confirming fixes, she helped build trust and foster a positive relationship with our user base.
What did not go well | 1. GOAL-BUG-004 was the most embarrassing bug of the project, as it involved micronutrient selections not being saved to the database. This fundamental oversight should have been caught by a cross-session persistence test before the MVP launch. 2. GOAL-BUG-002, which involved a gender change not triggering EER recalculation, posed a significant health risk. This was a PRD requirement that was never implemented, highlighting the need for better cross-checking of PRD requirements against actual implementation.
Key learnings | 1. Cross-session persistence testing must be part of the definition of done for any feature that stores user selections. This includes logging out, clearing the browser, and verifying that the state persists. 2. PRD requirements that trigger on profile changes must have explicit test cases for the trigger scenario, not just the initial setup scenario. 3. When a bug is found, we must conduct root cause audits to identify other components in the codebase that may share the same pattern.
Decisions made | 1. Implemented FoodDiaryContext as the shared state solution for all diary components. 2. Added 'Apply fix to all related components' as a standard item in the PR review checklist. 3. Included cross-session persistence tests in the definition of done for all features involving user selections.
Action items
Action | Owner | Due date
Add cross-session persistence test to DoD checklist | Shristi | Apr 15
Update PR review checklist to always ask 'what other components share this root cause' | Arjun | Apr 15
Create a regression test suite for all EER and BMR calculations | Arjun | Apr 28
Compile beta user feedback themes | Ananya | Apr 20
Triage remaining known issues for Sprint 8 | Shristi | Apr 15
Team health rating | 3 | The team is feeling tired after a sprint focused on bug fixing. While we expected some bugs, dealing with 10 in 14 days was more than anticipated. However, positive feedback from beta users and the absence of P0 bugs help maintain morale.

## Metrics This Sprint
Metric | Value
Beta users active | 200
Bugs reported by users | 6 (NUTR-BUG-001, 004, 006, GOAL-BUG-002, 004, and one false positive)
Bugs found internally | 4 (NUTR-BUG-003, 005, GOAL-BUG-003, AN-BUG-003)
Day 7 retention (first cohort) | 34%
Average daily food logs per user | 2.3 meals
Custom foods created | 23 (all Indian foods — chapati, dal, paneer top 3)
App Store early reviews | 3.8 average from 12 reviews