## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
MON-001 | Post-launch metrics dashboard setup | Task | Done | P0 | Arjun Mehta | Sprint 10 | 3 | Set up a real-time metrics monitoring dashboard for the team to track MAU, DAU, Day 7 retention, session length, and feature usage post-launch. The team was manually pulling metrics from Supabase before launch. With real users now the team needs a proper dashboard that updates daily without manual queries. Without this Shristi is running ad-hoc Supabase queries every morning to check numbers. | • Dashboard shows MAU, DAU, and Day 7 retention updated daily • Feature usage breakdown shows percentage of users using each core feature (food diary, goal setting, custom food, analysis) • Retention cohort chart shows Day 7 and Day 30 by weekly cohort • Dashboard accessible to all team members via read-only link • Custom foods created per day metric included as a key signal • Data refreshes automatically without manual Supabase queries
MON-002 | Pregnant women cohort analysis | Story | Done | P1 | Arjun Mehta | Sprint 10 | 5 | Following Ananya's discovery of 11 users who mentioned pregnancy in their free-text profile health goals field, run a formal cohort analysis comparing pregnant women users vs all other users across all key engagement metrics. This is the most important analytical task of Sprint 10. The results will determine whether pregnant women become a Q3 product priority. The initial signals Ananya noticed informally — 4.2 sessions per day vs 1.8 average — need to be formally verified with complete data before any strategic decision. | • Cohort analysis compares pregnant women vs all other users on: sessions per day, session length, Day 7 retention, feature usage • Specific micronutrients tracked most by pregnant women identified • Analysis confirms whether engagement difference is statistically meaningful given small sample size (11 users) • Iodine tracking behaviour specifically noted — unexpected signal • Results documented in shareable format for investor communication • Methodology documented so analysis can be repeated as user base grows
BUG-010 | Search results not resetting on diary date change | Bug | Done | P2 | Priya Nair | Sprint 10 | 2 | Post-launch users reported that when navigating to a different diary date while the food search panel is open, the search results from the previous date session remain visible. Users think they are searching in the new date's context but they are seeing results from their previous search. This creates confusion about which diary date food is being added to. | • Navigating to a different diary date clears search state completely • Search input field is empty when arriving on a new date • No previous search results visible when date changes • Fix uses the shared clearSearchState() utility created in Sprint 8 • Fix does not affect search state within the same date session
AN-CR-003 | Analysis screen performance on low-end Android devices | Change Request | Done | P2 | Arjun Mehta | Sprint 10 | 3 | Post-launch user feedback via App Store reviews mentions the nutrient analysis screen loads slowly on low-end Android devices (2GB RAM). One review specifically says 'app is slow when checking nutrition'. The analysis page triggers multiple FoodDiaryContext re-renders when the user navigates to it even when the data has not changed. Target is analysis screen under 1 second on mid-range Android (3GB RAM). | • Analysis screen loads in under 1 second on mid-range Android • FoodDiaryContext reads are memoized to prevent unnecessary re-renders • React.memo applied to analysis bar graph component • useCallback applied to data transformation functions • Performance tested on simulated low-end Android device profile • No regressions on iOS or desktop
NPS-001 | NPS survey implementation and launch | Story | Done | P1 | Ananya Iyer | Sprint 10 | 3 | Launch the first formal NPS survey to all active users on May 20. The survey asks the standard NPS question (likelihood to recommend, 0-10 scale) plus one open text question about the most important improvement. This is the first formal measurement of user satisfaction post-launch and directly tracks Q2 OKR Objective 2 KR for NPS 35+ by end of May. | • Survey sent only to users who have logged food at least 3 times • In-app survey as dismissible banner — not a blocking modal • NPS score calculated from responses using standard formula • Open text responses exported to CSV for qualitative analysis • Survey does not appear more than once per user per quarter • Results available for team review by May 21
RES-001 | Pregnant women user interviews — 5 interviews | Story | Done | P1 | Ananya Iyer | Sprint 10 | 2 | Conduct 5 structured user interviews with pregnant women users identified from the MON-002 cohort analysis. Goal is to understand their specific micronutrient tracking needs, what doctor-recommended targets they follow, what the current product does not support, and whether they have referred other pregnant women to Nutrivana. | • 5 interviews completed with pregnant women users by May 22 • Each interview covers: how they found Nutrivana, what they track, their doctor's specific recommendations, what the app cannot do, referral behaviour • Interview notes documented and shared with full team • Top 3 feature gaps identified and prioritised • At least one direct quote captured for investor communication
MKT-001 | Dr. Kavitha Rao nutritionist partnership activation | Task | Done | P2 | Ananya Iyer | Sprint 10 | 2 | Activate the second nutritionist partnership with Dt. Kavitha Rao (Bangalore-based dietitian, 18k Instagram followers). Partnership agreed in April but first post not yet scheduled. Coordinate the briefing document, tracking link, and post timing. | • Partnership briefing document sent to Kavitha • Custom UTM tracking link created for attribution • Post scheduled for week of May 19 • Install attribution monitored via tracking link
BUG-011 | Custom food serving unit not saving on iOS Safari | Bug | Done | P1 | Priya Nair | Sprint 10 | 3 | iOS Safari users report that the serving unit free-text field in custom food creation sometimes saves as empty even when a value was typed. This is a critical bug — serving unit is required for accurate nutrient calculation. If serving unit is empty the custom food cannot be logged correctly. Approximately 15% of iOS users based on bug report volume. | • Serving unit field saves correctly on iOS Safari 16 and 17 • Root cause identified and fixed • Fix uses onChange handler not onBlur for all free-text fields • Applied to all 6 free-text fields in the custom food form • No regression on Android Chrome or desktop browsers • Tested on physical iOS device not just simulator
V2-PLAN-001 | Q3 roadmap planning and V2 feature prioritisation | Task | Done | P1 | Shristi Sharmistha | Sprint 10 | 2 | Based on NPS survey results, cohort analysis findings, and pregnant women user interviews, create the initial Q3 roadmap prioritisation. This ticket formalises what was discussed in the Sprint 10 weekly meeting. Three confirmed Q3 priorities: simplified onboarding (38% goal setting drop-off from NPS open text), prenatal micronutrient presets (3.1x engagement), custom recipe builder (top NPS open text feature request). | • Q3 roadmap document updated with confirmed priorities and rationale • Each Q3 feature has clear data-based justification • Priority order confirmed and documented • Technical complexity estimates from Arjun included • Roadmap shared with Ravi for investor alignment • Q3 OKR draft started based on roadmap priorities

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
MON-001 | 1 | Shristi | 2025-05-13 | Every morning I am running 6 separate Supabase queries to check overnight numbers. This is not scalable. Can you build a simple dashboard that shows the 6 most important metrics without needing to run SQL queries?
MON-001 | 2 | Arjun Mehta | 2025-05-13 | I recommend building custom SQL views in Supabase and a lightweight internal dashboard page in the Next.js app. This will be faster than setting up Metabase or Mixpanel and can be ready in 2 days. I will also add a custom foods created per day metric as this is the most interesting signal for addressing the Indian food gap.
MON-001 | 3 | Arjun Mehta | 2025-05-15 | The dashboard is live now. One early finding worth noting is that users who create custom foods in their first 3 sessions have significantly higher session frequency the following week compared to those who do not. I will quantify this properly in the Sprint 11 feature adoption report. Also, we should clarify in the PRD that the dashboard needs to include session length as a metric.
MON-001 | 4 | Shristi | 2025-05-15 | Approved! The early custom food retention signal aligns perfectly with our hypothesis. Let's make sure to document this observation formally in the Sprint 11 research work. Also, we should consider edge cases where users may not have created any custom foods at all, as this could skew our metrics.
MON-002 | 1 | Ananya | 2025-05-13 | I've identified 11 users from the free-text health goals field who mentioned pregnancy. However, this method isn't perfect — some pregnant users might not have mentioned it. Can you also check users who have both folate AND iron goals set as a secondary identification method?
MON-002 | 2 | Arjun Mehta | 2025-05-14 | I can run both identification methods. The secondary method (folate + iron combination) identifies 4 additional users beyond the 11 already identified. So, we have a total of 15 potential pregnant users. I will run the analysis on both groups and compare.
MON-002 | 3 | Arjun Mehta | 2025-05-15 | Preliminary results on the 11 explicitly identified users show sessions per day: 4.2 vs 1.8 overall average, session length: 6.3 minutes vs 2.8 minutes, and Day 7 retention: 9 of 11 returned on day 7 (81.8%) vs 41.9% overall. These numbers are extraordinary, but I need to verify the methodology before sharing externally.
MON-002 | 4 | Shristi | 2025-05-15 | 81.8% Day 7 retention is the highest I’ve seen in any health app benchmark. Can you triple-check the cohort definition? We need to ensure there’s no survivorship bias — are these 11 users typical or are they self-selected super-users regardless of pregnancy?
MON-002 | 5 | Arjun Mehta | 2025-05-16 | The bias check is complete. The 11 users registered at different times (some beta, some launch week). Their first-week behavior before the high engagement period was similar to other users. The high engagement developed over time as they used the micronutrient tracking more deeply. There’s no survivorship bias — it’s a genuine behavioral difference.
MON-002 | 6 | Arjun Mehta | 2025-05-17 | Notable additional finding: 54% of pregnant users track iodine vs under 5% of all other users. This was unexpected. Iodine deficiency in pregnancy is a serious risk for fetal brain development. The fact that more than half of pregnant users are tracking iodine suggests these are medically informed, highly engaged users.
MON-002 | 7 | Ananya | 2025-05-17 | I can confirm from user interviews that the first interviewee mentioned her OB-GYN specifically told her to monitor iodine alongside folate and iron. This validates the data pattern — these users have doctor-prescribed tracking targets that our micronutrient feature supports better than any competitor.
MON-002 | 8 | Shristi | 2025-05-18 | The analysis is approved for sharing with Ravi in the next investor update. The headline number is 3.1x engagement (combining session frequency and session length multipliers). Pregnant women become a Q3 priority immediately. I’ll confirm this in the full team meeting.
BUG-010 | 1 | Priya Nair | 2025-05-13 | Root cause identified immediately. The diary date navigation handler was written before the Sprint 8 codebase audit and does not call clearSearchState(). Same pattern as NUTR-BUG-008 — one more place the utility was not applied. One line fix.
BUG-010 | 2 | Arjun | 2025-05-14 | Notes this is exactly the kind of bug the shared utility approach was supposed to prevent but the audit could only fix existing code — new code written post-audit needs discipline to use the utility. Proposes adding a linting rule that flags direct search state manipulation that bypasses clearSearchState().
BUG-010 | 3 | Priya Nair | 2025-05-15 | Fix deployed. Also found the analysis screen carousel navigation had the same issue — switching between nutrients in the analysis screen did not clear any active search state. Fixed both in the same PR.
BUG-010 | 4 | Shristi | 2025-05-15 | Approved. Arjun's linting rule idea is good — add it to the Sprint 10 action items. Prevention is better than finding the same bug class repeatedly.
AN-CR-003 | 1 | Arjun Mehta | 2025-05-14 | Root cause found. FoodDiaryContext triggers re-renders in all subscribed components whenever any diary data changes — even if the analysis screen data did not change. The analysis bar graph component is re-rendering on every food log action even when the user is not on the analysis screen.
AN-CR-003 | 2 | Priya | 2025-05-15 | Suggests React.memo on the analysis bar graph component as the highest-impact fix. The bar graph is the most complex component and it is re-rendering unnecessarily on every diary update. Additionally, we should test the edge case where the user rapidly logs multiple food items in succession to ensure the analysis screen remains performant.
AN-CR-003 | 3 | Arjun Mehta | 2025-05-19 | Optimisation complete. React.memo applied to analysis bar graph, 7-day trend chart, and per-nutrient analysis components. useCallback applied to the nutrient aggregation function. Analysis screen load time on mid-range Android simulation: 1.8 seconds → 0.7 seconds. However, we should clarify in the PRD that the performance testing must include scenarios with rapid food logging to ensure stability.
AN-CR-003 | 4 | Shristi | 2025-05-20 | Approved. The 0.7 second load time is well within the 1 second target. Notes for future: performance testing on low-end devices should be part of the definition of done for any new screen component. Also, we need to ensure that the memoization strategy is documented for future reference.
NPS-001 | 1 | Ananya Iyer | 2025-05-14 | I'm proposing we launch the NPS survey on May 20. The draft questions are: 'On a scale of 0-10, how likely are you to recommend Nutrivana?' and an open text question for feedback. Shristi, can you add the open text question? Arjun, could you build the in-app banner for this?
NPS-001 | 2 | Shristi | 2025-05-15 | The question wording looks good! I've added a second question: 'What one feature would make you most likely to recommend Nutrivana to a friend?' This will help us prioritize features for Q3 roadmap based on user feedback.
NPS-001 | 3 | Arjun | 2025-05-18 | The in-app banner is built and ready for testing. Just a technical note: the 3-food-log minimum filter is working correctly, which means users who registered but haven't logged food won't be included. This is crucial as their feedback could skew our NPS negatively and not reflect the true user experience.
NPS-001 | 4 | Ananya Iyer | 2025-05-21 | We've received results! There were 187 responses from about 800 eligible users, giving us a 23% response rate. The NPS score is 34. Breakdown: Promoters (9-10): 41%, Passives (7-8): 52%, Detractors (0-6): 7%. The top open text responses highlighted a need for a custom recipe builder, barcode scanner, and simplified goal setup. Notably, the complexity of goal setup is a common complaint, which aligns with our upcoming funnel analysis in Sprint 11.
RES-001 | 1 | Ananya Iyer | 2025-05-13 | Reaches out to 8 of the 11 identified users explaining they are doing research interviews and offering 3 months Nutrivana Pro free when premium launches. 6 respond positively. Schedules 5 for May 15-22.
RES-001 | 2 | Shristi | 2025-05-15 | Provides interview script. Non-negotiable questions: what does your doctor tell you to track, what trimester are you in, what does Nutrivana do that other apps do not, what does it not do that you wish it did, have you told any other pregnant women about it. We should also add a question about their preferred method of tracking micronutrients to ensure we're covering all bases.
RES-001 | 3 | Ananya Iyer | 2025-05-22 | Interviews complete. Most important findings: all 5 users have trimester-specific targets from their OB-GYN. The current app does not support trimester — users are manually editing their micronutrient goals every time they transition. Two users have already shared Nutrivana in their pregnancy WhatsApp groups — unprompted referrals. One edge case to note is that users in their third trimester expressed frustration with the lack of specific nutrient tracking for post-pregnancy recovery.
RES-001 | 4 | Shristi | 2025-05-23 | The WhatsApp group referral is the most strategically important finding. Pregnant women communities are tightly networked and highly trusting of recommendations from other pregnant women. If the product serves them well the segment is genuinely self-propagating. Prenatal presets confirmed as Q3 priority 2. We should also clarify in the PRD that we need to address the post-pregnancy recovery tracking needs as highlighted by the users.
MKT-001 | 1 | Ananya Iyer | 2025-05-14 | Briefing document sent to Kavitha. Highlights Nutrivana's Indian food coverage and micronutrient tracking depth as the key differentiators to mention. Post scheduled for May 21. One edge case to consider is if Kavitha's audience engagement drops below 2% — we should have a backup plan for additional promotion.
MKT-001 | 2 | Ananya Iyer | 2025-05-22 | Kavitha's post live May 21. 89 installs in 48 hours from her tracking link. Smaller than Dr. Nambiar's 156 (smaller audience) but 4.8% click rate on her followers — higher engagement rate than Nambiar's post. PRD correction: we need to ensure that future partnerships include a clause for audience size expectations to better gauge potential impact.
BUG-011 | 1 | Priya Nair | 2025-05-14 | Root cause found. iOS Safari has a known issue with input event handling — onBlur fires before the value is committed in some scroll and tap scenarios. The serving unit field was using onBlur to capture the value. When the bug triggers the field saves an empty string.
BUG-011 | 2 | Arjun | 2025-05-15 | Confirms this is a well-documented iOS Safari and React interaction issue. The fix (onChange instead of onBlur) is correct. Suggests applying it to all free-text fields in the custom food form proactively — not just the serving unit field.
BUG-011 | 3 | Priya Nair | 2025-05-16 | Fix deployed. onChange applied to all 6 free-text fields in the custom food form. Tested on iOS 16 and 17 physical device (Priya's iPhone). Bug not reproducible after fix. However, we should also ensure that any user who previously faced this issue is notified of the fix.
BUG-011 | 4 | Shristi | 2025-05-16 | Approved. Important fix. Indian users disproportionately use iPhones — this bug was silently blocking custom food creation for a significant portion of our most valuable users (those who create custom foods retain 2.3x better). Should have been caught in pre-launch iOS testing. Let's also update the PRD to reflect the need for comprehensive testing on all iOS devices.
V2-PLAN-001 | 1 | Shristi Sharmistha | 2025-05-23 | Documents Q3 priorities based on Sprint 10 findings. Priority 1 — simplified onboarding: NPS open text shows goal setup complexity as top complaint. 34 respondents mentioned it. This is a retention blocker not a feature gap. Priority 2 — prenatal presets: 3.1x engagement from an unserved segment. Priority 3 — custom recipe builder: top NPS feature request.
V2-PLAN-001 | 2 | Arjun | 2025-05-24 | Technical complexity estimates. Simplified onboarding: 2 sprints (new 3-question flow replacing EER setup, backend mapping, A/B testing). Prenatal presets: 1.5 sprints (ICMR research, trimester targets, auto-update logic, frontend). Custom recipe builder: 2 sprints (multi-ingredient recipe model, nutrient calculation, frontend). All three fit in Sprint 12-13 if simplified onboarding starts Sprint 12. We should also consider edge cases for users with dietary restrictions.
V2-PLAN-001 | 3 | Kabir | 2025-05-24 | Shares initial sketch for simplified onboarding — 3 questions: health goal, activity level in plain language, current weight. From these 3 the EER calculates invisibly. User sees only 'Your personalised calorie goal: 1847 kcal.' We need to ensure the design accommodates users who might not have their weight recorded, as this could skew the results.
V2-PLAN-001 | 4 | Shristi Sharmistha | 2025-05-25 | Q3 roadmap updated. Sharing with Ravi in the next investor update. Sprint 12 will begin simplified onboarding design and implementation. Sprints 12-13 will begin prenatal presets design and first implementation. Also, we need to clarify in the PRD that the custom recipe builder should include a feature for users to save their dietary preferences.