## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
ONBD-001 | Simplified onboarding — 3 question flow design | Story | Done | P0 | Kabir Sharma | Sprint 12 | 5 | Design the complete simplified onboarding flow that replaces the EER formula setup with a 3-question flow. The funnel analysis in Sprint 11 confirmed 38% of users abandon at the calorie goal setup step — 80% of those churn within 3 days. This design is the direct response to that finding. The user answers three questions and sees their personalised calorie goal without ever encountering the EER formula. Must be user tested with minimum 5 users before implementation begins. | • 3-question flow designed in Figma with all states and transitions • Each question fits on one screen — no scrolling • Activity level options use plain everyday language not exercise science terms • Result screen shows personalised calorie goal with one clear sentence explanation • Adjust manually option provided for users who want fine control • Pregnancy added as fourth health goal option (separate from main 3-question flow) • User tested with minimum 5 users including users who previously abandoned the original EER onboarding • Progress indicator shows users how many questions remain
ONBD-002 | Simplified onboarding — backend implementation | Story | Done | P0 | Arjun Mehta | Sprint 12 | 5 | Implement the backend changes for simplified onboarding. The existing EER formula logic is unchanged — only the API interface changes. The new onboarding endpoint accepts a simplified 3-field input and maps to the full EER parameters internally. Age and gender are optional with statistical defaults. When the user later adds these in profile the goal auto-recalculates using the GOAL-BUG-002 fix logic already in production. | • New onboarding API endpoint accepts simplified input: goal type, activity description, current weight • EER calculation runs with full accuracy internally • Age defaults to 30, gender defaults to neutral EER average if not provided at onboarding time • When user later adds age and gender goal auto-recalculates • All GOAL-BUG-002 profile change listener logic applies • New endpoint has tests covering all 3 question combinations
ONBD-003 | Simplified onboarding — frontend implementation | Story | Done | P0 | Priya Nair | Sprint 12 | 5 | Implement the simplified onboarding frontend based on Kabir's approved Figma designs. Replace the existing EER formula onboarding screens with the 3-question flow. The existing detailed goal setting screens are not deleted — they are moved to profile settings as Advanced goal settings accessible to users who want fine control. | • 3-question onboarding flow replaces EER formula screens for new users • Pregnancy variant shows trimester question when Pregnant is selected • Result screen shows personalised goal with Looks right and Adjust manually options • Adjust manually links to Advanced goal settings in profile • Old EER onboarding moved to profile settings not deleted • Existing users not affected — they see their existing goals unchanged • Completion trackable per user for A/B test measurement
PRE-001 | Prenatal micronutrient presets — research and design | Story | Done | P1 | Kabir Sharma | Sprint 12 | 5 | Research the clinically accurate trimester-specific micronutrient targets for pregnancy and design the prenatal presets feature. This is the Q3 priority 2 feature driven by the 3.1x engagement discovery from Sprint 10. Critical requirement: values must be sourced from ICMR (Indian Council of Medical Research) guidelines not just WHO — Indian pregnant women have different baseline nutritional profiles and ICMR accounts for this. | • Research sourced from ICMR and FSSAI prenatal nutrition guidelines • Trimester-specific targets defined for minimum 8 nutrients: folate, iron, calcium, vitamin D, iodine, zinc, B12, omega-3 • Pregnancy added as fourth option on health goal question • Trimester selection screen designed for Q1 Q2 Q3 options • Prenatal result screen shows which nutrients will be preset • User tested with minimum 3 pregnant users before implementation • B12 ICMR value (2.8mcg) used not WHO value (2.6mcg) for vegetarian Indian women baseline
PRE-002 | Prenatal presets — trimester auto-update logic | Story | Done | P1 | Arjun Mehta | Sprint 12 | 3 | Design and implement the backend logic for automatic trimester transitions. When a pregnant user provides their expected due date, the system calculates their current trimester and updates their micronutrient goals when they transition between trimesters. The auto-update pattern mirrors the GOAL-BUG-002 fix — profile changes automatically trigger goal recalculation with user notification. | • User can optionally enter expected due date during pregnancy onboarding • System calculates current trimester from due date • Weekly check at midnight IST detects trimester transitions • On transition: in-app notification sent with specific nutrient changes listed (e.g. Your folate goal updated from 400mcg to 600mcg) • User can manually override if auto-calculation is wrong • If no due date provided user manually selects current trimester • pregnancy_due_date, pregnancy_trimester, last_trimester_check columns added to user_profiles
MET-002 | Weekly metrics sheet — June week 1 and 2 | Task | Done | P1 | Arjun Mehta | Sprint 12 | 1 | Document weekly metrics for June weeks 1 and 2 in the June metrics tracking sheet. Continued from the May metrics sheet format established in MET-001. | • Week 1 (June 1-7) and Week 2 (June 8-14) metrics documented • All key metrics tracked: MAU, DAU, Day 7 retention, custom foods, App Store rating, session length • Numbers verified against Supabase raw data
ONBD-004 | Simplified onboarding A/B test setup | Story | Done | P1 | Arjun Mehta | Sprint 12 | 3 | Set up a proper A/B test to measure the impact of simplified onboarding on goal setup completion rate and Day 7 retention. 50% of new users see the original EER onboarding. 50% see the simplified 3-question flow. Results after 7 days determine whether to ship simplified onboarding to 100% of users in Sprint 13. | • A/B test assignment implemented at account creation • onboarding_variant column in user_profiles with values control or simplified • 50/50 random split on new user registration • Goal setup completion tracked per variant • Time to complete onboarding tracked per variant • Day 7 retention tracked per variant • Test runs minimum 7 days before results are read
BUG-013 | Retention numbers inconsistent between dashboard and reports | Bug | Done | P2 | Arjun Mehta | Sprint 12 | 2 | Shristi noticed the Day 7 retention on the MON-001 dashboard shows 46% but the retention cohort analysis in RET-001 shows 45% for the same period. The discrepancy is small but undermines data credibility for investor communications. Root cause is different definitions of Day 7 retention being used in different places. | • Root cause of discrepancy identified and documented • Both metrics standardised on the same definition • Definition documented formally: Day 7 retention equals user who opens app AND logs at least one food item on exactly day 7 from registration date • All existing reports updated to use standard definition
MKT-002 | Press outreach — building the data story | Task | In Progress | P2 | Ananya Iyer | Sprint 12 | 2 | Build the press-ready data story for outreach to health and nutrition publications. The Q2 OKR review identified earned media as a complete failure — 0 articles — because previous pitches lacked compelling data. This sprint Ananya builds 3 data-driven story angles that publications will actually want to cover. | • Press pitch document with 3 story angles created • Angle 1: Indian food gap in nutrition apps — quantified with data • Angle 2: Pregnant women segment discovery — 3.1x engagement story • Angle 3: Custom food personalisation drives 2.3x retention • Pitch ready for outreach in Sprint 13
NPS-002 | NPS survey round 2 — June 30 | Story | Done | P1 | Ananya Iyer | Sprint 12 | 2 | Set up and launch the second formal NPS survey on June 30 to measure Q2 closing NPS. Target is 40 or above per Q2 OKR KR. The survey uses the same format as NPS-001 with one additional question measuring simplified onboarding satisfaction for users who went through the new flow. | • Survey set up and ready to launch June 30 • Standard NPS question plus open text improvement question • Additional question for simplified onboarding users: How easy was it to set up your nutrition goals (1-5 scale) • Returning users from May survey see slightly different message • Results available same day for Q2 OKR review
PRE-003 | Prenatal presets — frontend implementation (partial) | Story | In Progress | P1 | Priya Nair | Sprint 12 | 5 | Implement the prenatal presets frontend based on Kabir's approved designs. This ticket starts in Sprint 12 and carries over to Sprint 13. Sprint 12 scope: pregnancy option in onboarding, trimester selection screen, prenatal micronutrient result display. Sprint 13 scope: trimester change notification UI, edge cases, user testing, and production deployment. | • Pregnancy option added to onboarding health goal question • Trimester selection screen implemented and functional • Prenatal micronutrient targets display correctly on result screen • Top 4 nutrients visible by default, 4 more in expandable section

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
ONBD-001 | 1 | Kabir Sharma | 2025-06-10 | I've drafted the initial design. Question 1: What is your main goal — options are Lose weight, Gain weight, Maintain weight. Question 2: How active are you — options are Lightly active, Moderately active, Very active. Question 3: What is your current weight — simple kg input. The result screen will show the personalised calorie goal with a single sentence.
ONBD-001 | 2 | Shristi | 2025-06-11 | The activity level descriptions are solid. However, the health goal options feel a bit clinical. I suggest using warmer language: for example, instead of 'Lose weight', we could say 'Lose some weight', and instead of 'Gain weight', we could use 'Build muscle or gain weight'. The language should feel more conversational.
ONBD-001 | 3 | Arjun | 2025-06-11 | From a technical perspective, Question 1 should map to the column 'weight_goal_type'. Question 2 maps to the 'activity_level_multiplier' — Lightly active should be 1.375, Moderately active 1.55, and Very active 1.725. Question 3 should map to 'current_weight_kg'. We still need to collect age and gender, but let's move that to the profile settings after the user sees their initial goal.
ONBD-001 | 4 | Kabir Sharma | 2025-06-12 | I've moved age and gender to the profile completion step that follows the initial calorie goal display. This way, users get an immediate win with their goal before providing more personal info. I also added a step indicator showing 1 of 3, 2 of 3, and 3 of 3 to improve user experience.
ONBD-001 | 5 | Ananya | 2025-06-12 | I tested the Figma prototype with 3 waitlist users who previously abandoned the original EER onboarding. All 3 completed the simplified flow successfully. The average time was 1 minute 43 seconds. One user commented that this is much simpler than the other app they tried, which only asked what they need to know.
ONBD-001 | 6 | Shristi | 2025-06-13 | User testing has passed with 3 out of 3 completions from users who previously abandoned the onboarding. This is the strongest validation data we've had in the project. I approve proceeding to implementation.
ONBD-001 | 7 | Kabir Sharma | 2025-06-16 | The full Figma designs are complete for all states. This includes question screens, the result screen, profile completion screen, adjust manually flow, and progress indicators. I've also designed the pregnancy variant — when a user selects 'Pregnant' on the health goal screen, a fourth question will appear asking which trimester they are in.
ONBD-001 | 8 | Priya | 2025-06-17 | Reviewing the designs from a frontend implementation perspective, I noticed the result screen needs both a 'Looks right' CTA and an 'Adjust manually' option. Some users will want to override the calculated goal. The 'Adjust manually' option should link back to the full EER onboarding, which is being moved to profile settings and not deleted.
ONBD-002 | 1 | Arjun Mehta | 2025-06-10 | Designs the new endpoint. Activity description maps to multiplier via lookup table. Lightly active 1.375, Moderately active 1.55, Very active 1.725. These are the three most statistically common activity levels in the existing user base. Default age 30 and gender neutral average produces EER within 150-250 calories of the exact value for most users — close enough for day 1, corrected when profile is completed.
ONBD-002 | 2 | Shristi | 2025-06-11 | What’s the accuracy impact of these defaults? For example, a 45-year-old woman and a 22-year-old man both getting the neutral default — how significant could the error be in their EER calculations?
ONBD-002 | 3 | Arjun Mehta | 2025-06-12 | The maximum error with neutral defaults is approximately 250 calories for extreme cases. This is much smaller than the 500+ calorie error from GOAL-BUG-002. The simplified flow trades minor initial imprecision for a 38 percentage point improvement in completion rate. However, we should ensure that the API documentation clearly states this edge case to avoid user confusion.
ONBD-002 | 4 | Arjun Mehta | 2025-06-18 | Backend complete and tested. 20 test profiles run. All within 200 calories of full EER calculation for the neutral defaults. Profile completion trigger for recalculation confirmed working correctly. Also, we should update the PRD to clarify that the recalculation will only occur after the user explicitly adds age and gender, rather than automatically.
ONBD-003 | 1 | Priya Nair | 2025-06-12 | Implementation started. Main complexity is routing — new users go to simplified flow, existing users returning to goal settings go to the full EER form. Solving with an is_new_user flag in the routing logic.
ONBD-003 | 2 | Priya Nair | 2025-06-17 | Implementation complete. Routing works correctly. One design improvement made during implementation — the calorie goal display on the result screen was showing 1847 kcal per day and the per day was redundant since kcal implies daily. Changed to 1847 kcal with subtitle Your daily calorie goal. Cleaner.
ONBD-003 | 3 | Kabir | 2025-06-18 | Design review complete. All screens match Figma. Progress indicators working. Pregnancy variant showing trimester question correctly. Looks right CTA and Adjust manually both functional. However, I noticed that if a user selects 'Pregnant' but does not complete the onboarding, they might end up with an incomplete profile. We should ensure that they can return to this question later.
ONBD-003 | 4 | Shristi | 2025-06-19 | Testing the flow on a fresh account. Completed in 1 minute 47 seconds from registration to first goal set. Target was under 3 minutes. Well within. Approved for A/B test deployment. Also, we need to clarify in the PRD that the Advanced goal settings should be clearly labeled to avoid confusion for users who might not realize they can access more detailed options.
PRE-001 | 1 | Shristi | 2025-06-10 | Kabir, please proceed with the prenatal research focusing on ICMR guidelines rather than just WHO. It's essential to note that Indian pregnant women, especially vegetarians, have different baseline nutritional statuses. ICMR publishes India-specific dietary reference values that we need to incorporate.
PRE-001 | 2 | Kabir Sharma | 2025-06-12 | Research is complete. Here are the key ICMR trimester targets: Folate: 400mcg T1, 600mcg T2, 500mcg T3. Iron: 35mg all trimesters (ICMR recommends 35mg for Indian women vs WHO 27mg due to higher baseline iron deficiency prevalence). Calcium: 1000mg T1-T2, 1200mg T3. Vitamin D: 600 IU all trimesters. Iodine: 220mcg all trimesters. B12: 2.8mcg all trimesters. Zinc: 11mg all trimesters.
PRE-001 | 3 | Arjun | 2025-06-13 | The B12 concern is particularly important for the Indian context. Vegetarian Indian women have significantly higher rates of B12 deficiency than the global average. The ICMR 2.8mcg vs WHO 2.6mcg difference is small in absolute terms but reflects a real population health difference. Using ICMR is the right call for our user base.
PRE-001 | 4 | Ananya | 2025-06-13 | I validated this with one interviewed pregnant user (with permission). Her OB-GYN prescribed 35mg iron and 600mcg folate in the second trimester — exactly matching ICMR values not WHO values. This real-world validation confirms using ICMR is clinically correct for Indian users.
PRE-001 | 5 | Kabir Sharma | 2025-06-14 | Design is complete. The pregnancy flow: user selects Pregnant on the health goal question. A new question appears: Which trimester — First weeks 1-12, Second weeks 13-26, Third weeks 27-40. The result screen shows personalized prenatal targets for the 4 most critical nutrients (folate, iron, calcium, vitamin D) with a 'See all 8 nutrients' expandable section.
PRE-001 | 6 | Shristi | 2025-06-15 | One design change: the pregnancy detection trigger Kabir originally proposed was too complex. Adding 'Pregnant' as the fourth option directly to the main health goal question is simpler and more direct. Users who are pregnant know they are pregnant — no detection needed.
PRE-001 | 7 | Kabir Sharma | 2025-06-16 | Agreed. 'Pregnant' has been added as the fourth option to Question 1. If selected, Question 2 becomes 'Which trimester?' Question 3 remains current weight. Pregnant users now go through a 4-question flow vs 3 for other users. This is clean and logical.
PRE-001 | 8 | Priya | 2025-06-17 | I've reviewed the designs. One critical product question raised — when a user transitions from the first to second trimester, does the system automatically update their micronutrient goals or do they manually change? We need to make a decision on this before implementation begins.
PRE-002 | 1 | Arjun Mehta | 2025-06-13 | Designs trimester calculation. If due date provided: weeks remaining = (due_date - today) / 7. T1 = 40-28 weeks remaining. T2 = 27-14 weeks remaining. T3 = 13-0 weeks remaining. Weekly check runs at midnight IST using the date_string timezone approach from NUTR-022.
PRE-002 | 2 | Shristi | 2025-06-14 | Approves. Critical requirement — the auto-update must never happen silently. User must see a notification showing exactly which goals changed and what the new values are. Not a generic goals updated message. Also, we should clarify that if the user enters a due date but the system fails to calculate the trimester correctly, it should default to T1.
PRE-002 | 3 | Arjun Mehta | 2025-06-17 | Implementation complete. Three new columns in user_profiles: pregnancy_due_date (nullable date), pregnancy_trimester (1/2/3 nullable), last_trimester_check (date). Notification template includes the exact changed values. Edge case noted: if the user enters a due date that is in the past, the system should prompt the user to re-enter a valid due date.
PRE-002 | 4 | Shristi | 2025-06-18 | Approved. The GOAL-BUG-002 lesson applied correctly — any auto-change to health-critical goals must notify the user with specific numbers not generic messages. Users deserve to know exactly what changed. We also need to ensure that the system logs any manual overrides for auditing purposes.
MET-002 | 1 | Arjun Mehta | 2025-06-09 | June week 1 metrics. MAU 1,456. Day 7 retention 45%. Custom foods cumulative 512. App Store rating 4.1. I noticed that the DAU was not included in the metrics. We should ensure that it is tracked consistently as it was in the previous month.
MET-002 | 2 | Arjun Mehta | 2025-06-16 | June week 2 metrics. MAU 1,847. Day 7 retention 46%. Custom foods cumulative 634. App Store rating 4.1. Growth accelerating — 391 new MAU in one week. An edge case to consider is if the App Store rating fluctuates due to user reviews; we should track any significant changes weekly to ensure accuracy.
ONBD-004 | 1 | Arjun Mehta | 2025-06-13 | A/B test setup complete. Random assignment at account creation using a simple modulo on user ID. onboarding_variant column added to user_profiles. 50/50 split confirmed across first 100 registrations.
ONBD-004 | 2 | Shristi | 2025-06-14 | We also need to track time-to-complete-onboarding as a metric — not just completion rate. The hypothesis is that more users will complete AND they will complete faster. Both parts need data for a comprehensive analysis.
ONBD-004 | 3 | Arjun Mehta | 2025-06-18 | First week A/B results preliminary. Control group EER: 61% goal setup completion, average 4.1 minutes. Simplified group: 84% completion, average 1.9 minutes. The hypothesis is confirmed on both dimensions. However, we should also consider the edge case where users abandon the onboarding process midway; we need to track that as well.
ONBD-004 | 4 | Shristi | 2025-06-19 | 84% vs 61% completion and 1.9 vs 4.1 minutes. This is the most impactful product change since the custom food creator. Let's confirm shipping simplified onboarding to 100% of users in Sprint 13 pending final 10-day A/B results. Also, I noticed the PRD didn't specify tracking user abandonment rates; we should add that to ensure we capture the full picture.
BUG-013 | 1 | Arjun Mehta | 2025-06-14 | Root cause found. Dashboard counts Day 7 as user who logged in on day 7. Cohort analysis counts user who logged food in days 6-8 (3-day window). Different definitions. Standardising on the stricter definition — must log food on exactly day 7. An edge case to consider is users who log food on day 6 but do not log anything on day 7; they should not be counted in the Day 7 retention.
BUG-013 | 2 | Arjun Mehta | 2025-06-16 | Standard definition applied everywhere. Day 7 retention locked definition: user who opens app AND logs at least one food item on exactly day 7 from registration date. All reports and dashboard now use this definition. This aligns with the PRD's requirement for precise tracking, ensuring we communicate accurate data to investors.
MKT-002 | 1 | Ananya Iyer | 2025-06-16 | Draft press pitch complete. Three angles ready. Angle 2 (pregnant women discovery) is the most newsworthy — an unexpected segment finding with 3.1x engagement is a genuine product story. Angle 1 (Indian food gap) is the evergreen story. Angle 3 (retention correlation) is more of a business metric than press story — moving it to investor update.
MKT-002 | 2 | Shristi | 2025-06-19 | Reviews pitch. Approves angles 1 and 2 for press. Angle 3 moves to investor communications as Ananya suggested. Outreach to maternal health publications starts Sprint 13 — the pregnant women story is the strongest angle for earning media coverage. We should also ensure that we have data to back the claim of 3.1x engagement; if the data is based on a small sample size, it might not be as compelling. Let's clarify that in the pitch.
NPS-002 | 1 | Ananya Iyer | 2025-06-13 | Sets up June 30 NPS survey. Adds the simplified onboarding satisfaction question. Users who went through simplified flow (onboarding_variant = simplified) see the extra question. Control group users do not.
NPS-002 | 2 | Arjun Kumar | 2025-06-14 | Implements the variant-aware survey trigger. Users who completed the May survey see a message acknowledging they already gave feedback once: We have made improvements since May. We would love your updated view. We should also consider how to handle users who might have skipped the survey last time.
NPS-002 | 3 | Ananya Iyer | 2025-06-30 | Survey launched at 10 AM June 30. Preliminary results by 6 PM. Noted an edge case where users who have not interacted with the app in over 3 months are not receiving the survey. We might need to adjust our user segmentation for future surveys.
NPS-002 | 4 | Ananya Iyer | 2025-06-30 | Final results. 312 responses from approximately 2,100 active users (15% response rate). NPS 41 — exceeds Q2 target of 40. Simplified onboarding satisfaction: 4.2 out of 5 from users who used the new flow. Goal setup mentioned positively in open text for the first time — setting goals is much easier now from 23 respondents. Also, I realized we need to clarify in the PRD that the onboarding satisfaction question is only for users who have completed the new flow.
PRE-003 | 1 | Priya Nair | 2025-06-17 | Implementation started. Pregnancy option added to onboarding goal question. Conditional routing working — selecting Pregnant shows trimester question, other options skip it. State management is cleaner than expected.
PRE-003 | 2 | Kabir | 2025-06-18 | Reviews first build in staging. One design note — prenatal result screen showing all 8 nutrients at once is overwhelming on mobile. Suggests default showing only the 4 most critical with expandable section for the other 4.
PRE-003 | 3 | Priya Nair | 2025-06-19 | Updated with expandable section. Cleaner. Top 4 visible: folate, iron, calcium, vitamin D. Expandable shows: iodine, B12, zinc, omega-3. Also, we should ensure that if a user selects 'Pregnant' but doesn't provide a due date, the app defaults to the first trimester.
PRE-003 | 4 | Shristi | 2025-06-20 | Good progress but carrying over to Sprint 13 as planned. Sprint 12 deliverables are complete. We need to clarify in the PRD that the trimester change notification UI should also handle cases where users manually override their trimester selection.