## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
TECH-001 | Database schema design for users, food logs, goals and nutrients | Task | In Progress | P0 | Arjun Mehta | Sprint 1 | 8 | We need to design a robust database schema that effectively manages user profiles, food logs, nutritional goals, and nutrient data. This schema must ensure data isolation for users and comply with the PRD requirements, including the handling of date-stamped food logs and various nutrient value formats. The implementation will utilize Supabase for data management. | • Database schema includes separate tables for users, food logs, goals, and nutrients. • RLS policies are implemented to ensure data isolation between users. • Food diary entries are date-stamped to track daily logs. • Nutrient values are stored in standardized units.
TECH-003 | Authentication and user session management | Task | Done | P0 | Arjun Mehta | Sprint 1 | 5 | We need to implement a robust authentication system that ensures user sessions are managed effectively. The system should allow users to log in and out while ensuring their food diary data persists across sessions. This will involve using JWT for authentication and a refresh token strategy to maintain user experience without compromising security. | • User food diary data must persist across logout and re-login. • JWT access token should have a 1-hour expiry with a 30-day refresh token. • Silent refresh must work without interrupting the user experience. • Users should not be logged out mid-session.
NUTR-TASK-003 | Date-stamped diary data model design | Task | Done | P0 | Arjun Mehta | Sprint 1 | 5 | We need to design a data model for the food diary that can handle date-stamped entries. This model must allow users to log meals for past, current, and future dates while ensuring that the food diary displays the correct nutrient columns, even when no entries exist for a selected date. The solution should also account for changes in user goals over time. | • Food diary maintains a separate log for each calendar date. • Empty food diary displays all target nutrients for any selected date. • Switching between dates loads the corresponding diary within 2 seconds. • Logged food items are associated with the exact date and meal section. • Cumulative totals for each target nutrient are calculated for the selected date.
GOAL-SPIKE-001 | Research all EER formulas by age group gender and activity level | Story | In Progress | P1 | Arjun Mehta | Sprint 1 | 5 | We need to conduct thorough research on the Estimated Energy Requirement (EER) formulas that vary by age group, gender, and activity level. This research will help us implement accurate calorie calculations in the Nutrivana app. The formulas must be categorized correctly to ensure users receive tailored nutritional guidance based on their specific profiles. | • Document all 15+ EER formula variants categorized by gender, age group, and activity level. • Confirm the mapping of PRD's 5 activity levels to USDA's 4 levels. • Ensure the formulas can dynamically update based on user input for gender and activity level.
GOAL-SPIKE-002 | Research RDA and MAX values for all micronutrients by age and gender | Story | Done | P1 | Arjun Mehta | Sprint 1 | 5 | We need to gather comprehensive data on the Recommended Dietary Allowance (RDA) and Maximum (MAX) values for all micronutrients based on age and gender. This will help us provide accurate nutritional information to our users. The data should be organized in a way that allows us to display it effectively in the app once users have set their calorie budgets. | • RDA and MAX values are documented for all tracked micronutrients by age and gender • Display micronutrient details only after the user sets their calorie budget • Categorize micronutrients into distinct buckets such as vitamins, minerals, and carbohydrates
NUTR-EPIC-001 | Epic: Food Diary Core | Epic | In Progress | P0 | Arjun Mehta | Sprint 1 | 8 | The food diary is a crucial feature for Nutrivana, enabling users to log their meals, recipes, and supplements seamlessly. This epic encompasses all user stories related to food logging, goal comparison, and meal breakdowns. It will serve as the backbone for tracking nutrient intake against user-defined goals, making it essential for our app's success. | • Users can log food items with detailed macros and micros. • The system calculates and displays cumulative nutrient totals.
GOAL-EPIC-001 | Epic: Calorie Goal Setting | Epic | In Progress | P0 | Arjun Mehta | Sprint 1 | 8 | This epic focuses on enabling users to set their calorie goals within the Nutrivana app. After completing the account setup, users will be required to establish a calorie target based on various personal metrics. The calorie calculation is essential as it acts as a prerequisite for accessing the food diary feature. This epic includes the implementation of the EER method for calorie calculations and necessary validations to ensure user input is within healthy limits. | • User can set a calorie goal post account setup. • Calorie calculation must be completed before allowing access to the food diary. • Validation checks for BMR must be implemented.
GOAL-EPIC-002 | Epic: Macro and Micro Goal Setting | Epic | In Progress | P1 | Arjun Mehta | Sprint 1 | 8 | This epic focuses on implementing the macro and micro goal-setting features within the Nutrivana app. The macro goals will allow users to set their carbohydrate, fat, and protein intake as a percentage of their target calories, while the micro goals will help users track essential nutrients based on RDA values. The complexity of allowing users to select up to 20 nutrients to track simultaneously will require careful UI design and implementation. | • Users can set macro goals as a percentage of total calories with a default distribution of 40:30:30. • Users can select/deselect up to 20 nutrients to track at a time, organized into category buckets.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
TECH-001 | 1 | Arjun Mehta | 2025-01-02 | I've created the initial schema design covering the users, food_logs, goals, and nutrients tables. I believe this will meet our requirements but would love your feedback.
TECH-001 | 2 | Shristi Sharmistha | 2025-01-03 | Thanks for sharing, Arjun. I noticed that the PRD emphasizes data isolation between users. Can you clarify how we will enforce Row Level Security in Supabase?
TECH-001 | 3 | Arjun Mehta | 2025-01-04 | Great point, Shristi. I plan to implement RLS policies by adding a user_id foreign key to each table. This way, the policy will ensure that users can only read and write their own rows.
TECH-001 | 4 | Shristi Sharmistha | 2025-01-05 | That sounds solid, Arjun. Just to ensure we cover everything, could you also account for the date-stamped diary requirement? Each food log needs to have an exact date attached.
TECH-001 | 5 | Arjun Mehta | 2025-01-06 | Absolutely, I will add a date column to the food_logs table to capture the exact date of each entry. This will help us maintain a clear food diary for users.
TECH-001 | 6 | Kabir Sharma | 2025-01-07 | Hey team, just a thought — how will we handle the nutrient goals for users? I think we should store them in three formats: percentage, grams, and kcal equivalents.
TECH-001 | 7 | Arjun Mehta | 2025-01-08 | Good catch, Kabir! I’ll ensure that the macro goals are stored in all three formats. It’s crucial for users to track their intake accurately.
TECH-001 | 8 | Ananya Iyer | 2025-01-09 | This is looking great, everyone! Just a reminder that we also need to incorporate RDA and MAX values for micronutrients based on age and gender. Let’s make sure that’s included in the schema as well.
TECH-003 | 1 | Arjun Mehta | 2025-01-03 | I've created this ticket to propose a JWT authentication system with a 24-hour token expiry. This should help us manage user sessions effectively.
TECH-003 | 2 | Shristi Sharmistha | 2025-01-04 | I noticed a potential conflict with our PRD. It states that food diary data must persist even if the user logs off. If the JWT expires after 24 hours and the user logs back in, will their food diary data still be there?
TECH-003 | 3 | Arjun Mehta | 2025-01-04 | Great point, Shristi! The JWT expiry is related to the authentication token, not the data itself. The data is stored in Supabase permanently. The concern lies with the session; if the JWT expires mid-session, the user will be logged out and lose any unsaved state.
TECH-003 | 4 | Shristi Sharmistha | 2025-01-05 | Understood. But what happens if a user opens the app after 7 days without logging in? Will they lose their session and have to re-login?
TECH-003 | 5 | Arjun Mehta | 2025-01-05 | That's the tradeoff we need to balance. Security requires short expiry times, while user experience benefits from longer sessions. I'm proposing a 1-hour access token expiry, a 30-day refresh token, and a silent refresh process in the background. This way, users only see the login screen if they haven't opened the app in 30 days.
TECH-003 | 6 | Shristi Sharmistha | 2025-01-06 | I like the 30-day refresh token approach. However, we need to ensure that users are never logged out mid-session. The silent refresh must work seamlessly.
TECH-003 | 7 | Arjun Mehta | 2025-01-08 | I've implemented the JWT and refresh token strategy with Supabase Auth. I've also updated the schema to include a refresh_tokens table. I've tested the silent refresh and it works as expected when the token expires.
TECH-003 | 8 | Shristi Sharmistha | 2025-01-10 | I verified the implementation today. I logged in, waited, and then came back to check. The session persisted, and the food diary data remained intact after re-login. I'm closing this ticket now.
NUTR-TASK-003 | 1 | Arjun Mehta | 2025-01-04 | I've drafted an initial data model for the food diary. It consists of a single food_logs table with the necessary columns. Let me know your thoughts!
NUTR-TASK-003 | 2 | Shristi Sharmistha | 2025-01-05 | Thanks for sharing, Arjun. I noticed that the PRD states we need to show an empty food diary with all target nutrient columns for any date. How do we handle this if there are no logs for that date?
NUTR-TASK-003 | 3 | Arjun Mehta | 2025-01-06 | Good point, Shristi. Currently, my schema only stores entries when food is logged. An empty date would have no rows in food_logs, which makes it tricky to display the correct columns.
NUTR-TASK-003 | 4 | Arjun Mehta | 2025-01-07 | I propose two solutions: Option A is to create a diary_dates table that logs every date the user has accessed the diary. Option B is to compute the empty diary structure on the fly based on the user's goal settings.
NUTR-TASK-003 | 5 | Shristi Sharmistha | 2025-01-08 | Option B sounds simpler, but what happens if the user changes their goals mid-day? The PRD specifies that changes should only affect future entries, not past ones.
NUTR-TASK-003 | 6 | Arjun Mehta | 2025-01-09 | Option B can handle this by fetching the goal settings that were active on the specific date the diary is being viewed. We'll need to store a goal_history with effective_date to track changes.
NUTR-TASK-003 | 7 | Arjun Mehta | 2025-01-10 | I've finalized the design: we'll have a food_logs table for logged items and a goal_snapshots table for user goals with effective_date. This way, we can build the diary structure dynamically and ensure past entries remain unchanged.
NUTR-TASK-003 | 8 | Shristi Sharmistha | 2025-01-11 | I approve the goal_snapshots approach. This aligns well with our requirements and addresses future concerns about goal changes. Great work, Arjun! Let's close this ticket.
GOAL-SPIKE-001 | 1 | Arjun Mehta | 2025-01-03 | I've completed the research on the EER formulas and documented over 15 variants categorized by gender, age group, and activity level. I noticed a discrepancy where our PRD mentions 5 activity levels, but the USDA documentation only lists 4. I’ve attached the full formula table for your review. Can you confirm which activity level mapping we should use?
GOAL-SPIKE-001 | 2 | Shristi Sharmistha | 2025-01-04 | Thanks for the detailed research, Arjun! After reviewing the formula table, I think we should go with the USDA's 4 activity levels: sedentary, low active, active, and very active. We can map the PRD's 5th level into the closest USDA category. Please proceed with the implementation using this mapping.
GOAL-SPIKE-001 | 3 | Arjun Mehta | 2025-01-05 | Got it, Shristi! I’ll start working on the implementation for GOAL-001 using the USDA mapping. I’ll ensure that the app can dynamically switch the EER formula based on user inputs for gender and activity level. I’ll keep you updated on my progress.
GOAL-SPIKE-001 | 4 | Arjun Mehta | 2025-01-06 | Just a quick update: I’ve started setting up the logic for the EER calculation in our React app. I’m also looking into how we can integrate Supabase RLS to ensure that users' data remains secure while they interact with their food diary. I’ll share a demo once I have a working prototype!
GOAL-SPIKE-002 | 1 | Arjun Mehta | 2025-01-03 | I've completed the research on RDA and MAX values from the USDA and NIH databases. I've documented the values for all tracked nutrients categorized by age and gender. I noticed that some nutrients, like vitamin K, have AI values instead of formal RDA. Should we treat AI values as RDA for display purposes?
GOAL-SPIKE-002 | 2 | Shristi Sharmistha | 2025-01-04 | Thanks for the update, Arjun! I think it makes sense to treat AI as RDA for simplicity. Our users won't need to know the distinction, and it will streamline the information we present. Let's proceed with that approach.
GOAL-SPIKE-002 | 3 | Arjun Mehta | 2025-01-05 | Great! I've shared the complete reference table with all the RDA and MAX values. This should be sufficient for us to start the implementation for GOAL-012. Let me know if you need anything else from my side.
GOAL-SPIKE-002 | 4 | Shristi Sharmistha | 2025-01-06 | I've reviewed the reference table, and everything looks good. We can now close this ticket. Thanks for your thorough work on this, Arjun! Looking forward to seeing how this integrates with the app.
NUTR-EPIC-001 | 1 | Shristi Sharmistha | 2025-01-05 | Hey Arjun, can you confirm if we can kick off the food diary development in Sprint 3? I want to ensure we have the USDA database integration and goal setting completed first, as they are critical dependencies.
NUTR-EPIC-001 | 2 | Arjun Mehta | 2025-01-06 | Hi Shristi, yes, I believe we can start in Sprint 3 as long as we stay on track with the USDA integration and goal setting. I’ll make sure to prioritize those tasks in our backlog. Let’s also consider how we’ll handle user data privacy with Supabase RLS as we build out the food diary.
GOAL-EPIC-001 | 1 | Shristi Sharmistha | 2025-01-02 | I've outlined the scope for this epic, which includes the critical dependency on the calorie goal feature. We need to ensure that users cannot access the food diary without setting their calorie goals first. This is a high priority for us, so let's keep the momentum going.
GOAL-EPIC-001 | 2 | Arjun Mehta | 2025-01-03 | Thanks for the update, Shristi. I agree on the priority level. Just to clarify, we need to complete the research on the EER formula as part of GOAL-SPIKE-001 before we can start on the actual implementation for GOAL-001 and GOAL-002. I’ll coordinate with the team to ensure we stay on track for Sprint 1.
GOAL-EPIC-002 | 1 | Shristi Sharmistha | 2025-01-02 | I've defined the scope for this epic, which will cover GOAL-005 through GOAL-012 and GOAL-SPIKE-002. It's crucial that the macro goal feature is dependent on the calorie goal being set first. We also need to ensure that the micro goal relies on the RDA research from GOAL-SPIKE-002 being completed before we can proceed.
GOAL-EPIC-002 | 2 | Arjun Mehta | 2025-01-03 | Thanks for the update, Shristi! I confirm the scope and the dependency chain. GOAL-SPIKE-002 is in Sprint 1, and we can plan the macro goal stories for Sprint 3 after the calorie goal is completed. We should also consider the UI implications of allowing users to track 20 nutrients in the food diary. Kabir will need to get involved early to ensure we design this effectively.