## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
NUTR-007 | Select USDA food database as source when adding food to diary | Story | Done | P0 | Priya Nair | Sprint 4 | 5 | This story focuses on allowing users to select the USDA food database as a source when adding food to their diary. Users should be able to access this feature through both the Add Food button and the Food Database tab. The interface must clearly distinguish this source from custom food and recipe options, ensuring a seamless user experience. | • User can select Food Database as a source when adding food • Food can be selected via Add Food in diary or Food Database tab • Search input field appears after selecting source • Only one item can be selected at a time • Food database selection interface is distinguishable from other sources • Search results are displayed in a scrollable list with clear labels • Previous input is cleared if source is changed or user navigates away • Food database appears instantly when adding food • User is redirected to adjust portion page after food selection
NUTR-008 | Search food with fuzzy matching in USDA database | Story | Done | P0 | Priya Nair | Sprint 4 | 5 | We need to implement a frontend search component that utilizes fuzzy matching to enhance user experience when searching for food items. The component should support partial matching and ensure that results are displayed quickly. It's crucial to confirm the minimum character count before a search is triggered to avoid performance issues. | • Search results displayed within 1 second of user input • System must support fuzzy or partial matching • All search results partially or fully matching item name should appear • Users allowed to go back from food database • If user changes source or navigates away, previous input cleared • Search results in scrollable list with clear food name labels
NUTR-009 | Adjust portion size with food-specific serving units and instant recalculation | Story | Done | P0 | Arjun Mehta, Priya Nair, Kabir Sharma | Sprint 4 | 8 | We need to implement a portion adjustment feature that allows users to specify serving sizes using food-specific units. The nutrient breakdown should recalculate instantly based on the selected serving size. This will ensure accurate logging and improve user experience. The PRD needs to be updated to reflect the need for food-specific serving units. | • User cannot add food without completing the portion page. • Nutrient breakdown recalculates instantly as user edits portion size.
NUTR-010 | Add food to diary and redirect to food diary page instantly | Story | Done | P0 | Priya Nair | Sprint 4 | 5 | This story focuses on enhancing the user experience by allowing users to add food items to their diary and be redirected instantly. The implementation must ensure that the nutrient data is updated correctly and that the user receives appropriate feedback based on their actions. Special attention is required for meal type selection to prevent errors during food logging. | • User is redirected to food diary page after adding food • Nutrient data updates correctly in the food diary • Food addition happens instantly without delays • No limit on the number of food items added • Warning message displayed if meal type is not selected
NUTR-015 | Display only goal nutrients as columns with logged food values | Story | Done | P0 | Priya Nair | Sprint 4 | 5 | This story focuses on displaying the nutrient values for logged food items in the food diary. The goal is to ensure that only the nutrients selected by the user are shown as columns, with the correct order and formatting. We need to clarify how to handle cases where nutrients are not present or have a value of zero. | • Only nutrients checked to track should be shown as columns in food diary • Column order: Calorie (if selected) → Macros alphabetical → Micros alphabetical • Max 20 nutrient columns displayed at once • Each logged food item shows its nutrient value under each target nutrient column • If food does not contain a target nutrient the value field should display '-' • Nutrient values in food diary are non-editable • User can scroll left to right to view all nutrient columns • If food has nutrient value of zero the value field shows '-'
NUTR-016 | View cumulative nutrient totals at bottom of food diary | Story | Done | P0 | Priya Nair | Sprint 4 | 5 | This story focuses on implementing a feature that displays cumulative nutrient totals at the bottom of the food diary. The totals should be updated in real-time as users log their meals. It's crucial that the totals accurately reflect the sum of each nutrient consumed throughout the day, regardless of the meal or food source. Additionally, we need to ensure that the total row remains visible as users scroll through their food entries. | • Cumulative total for each target nutrient displayed at the bottom of each nutrient column • Totals calculated from first food logged to last food logged regardless of meal or food source • Total must update in real-time as food is added or removed
NUTR-017 | Compare actual vs goal with color coding — red yellow green | Story | Done | P0 | Kabir Sharma, Priya Nair | Sprint 4 | 5 | This story involves implementing a color-coded system to compare actual nutrient intake against user-defined goals. The color coding will vary based on the type of goal (weight loss, gain, or maintenance) and will help users quickly assess their nutritional status. Special attention is needed for the weight maintenance case where over-consumption is treated differently. The implementation must be precise to avoid confusion in user experience. | • Cumulative actual intake is compared against daily goals for each nutrient. • Color coding reflects the correct status for calories based on weight goal type.
NUTR-018 | Per meal nutrient breakdown — bold total at end of each meal section | Story | Done | P1 | Priya Nair | Sprint 4 | 3 | This story involves implementing a meal subtotal row that displays the total nutrients for each meal at the end of the last food item. The total must be bold and should not include color coding, differentiating it from the daily cumulative total. We need to ensure that the meal total is displayed consistently, even when there is only one food item in the meal. | • Meal total is displayed as bold at the end of each meal section. • No color coding for meal totals. • Meal total shows even if there is only one food item.
NUTR-TASK-004 | Real-time nutrient calculation engine | Task | Done | P0 | Arjun Mehta, Priya Nair | Sprint 4 | 8 | We are building a real-time nutrient calculation engine that updates nutrient totals instantly as users add, edit, or delete food entries. This engine must meet the 1-second recalculation requirement without manual refreshes. The goal is to ensure cumulative totals are accurate even with rapid changes, and all values maintain unit consistency. | • Nutrient recalculation must happen within 1 second after any add, edit, or delete • Cumulative totals must be accurate with multiple rapid changes • Meal subtotals and daily totals must both update instantly • Over/under/on-track indicators must update accordingly

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
NUTR-007 | 1 | Shristi Sharmistha | 2025-02-12 | When selecting the USDA food database, we need to ensure that if a user searches for 'chicken' and then switches to a custom food source, the search input is completely cleared. Can you confirm how we will handle this state clearing?
NUTR-007 | 2 | Priya Nair | 2025-02-13 | I can confirm that we will implement the state clearing using React's useEffect cleanup function that triggers when the source changes. Also, Arjun, can you confirm what the API endpoint will return when a user selects a food item from the USDA search results?
NUTR-007 | 3 | Arjun Mehta | 2025-02-14 | The search endpoint will return food_id, food_name, and default serving size. The adjust portion page will then make a second API call with the food_id to fetch the full nutrient breakdown. This two-step approach will keep the search results fast and load detailed information only when necessary. Priya, please implement this accordingly.
NUTR-007 | 4 | Shristi Sharmistha | 2025-02-17 | I tested the USDA source selection from both the Add Food button and the Food Database tab. Both entry points work as expected, the search clears when switching sources, and the user is redirected to the adjust portion page instantly after food selection. This meets the PRD requirements, so I will close the ticket.
NUTR-008 | 1 | Shristi Sharmistha | 2025-02-12 | Before we start, can we confirm what the minimum character count should be before the search fires? Should a single character trigger a search?
NUTR-008 | 2 | Priya Nair | 2025-02-13 | I propose we set the minimum to 2 characters. A single character search like 'a' would return thousands of results, which could lead to performance issues. This way, we can narrow down the results meaningfully. Arjun, can you confirm that the backend handles a 2-character minimum correctly with the ILIKE/trigram approach?
NUTR-008 | 3 | Arjun Mehta | 2025-02-14 | The ILIKE path handles 2-3 character queries fine, and the trigram will kick in for longer queries. Setting the minimum to 2 characters on the frontend is correct. Priya, please proceed with implementing the search component with this in mind.
NUTR-008 | 4 | Shristi Sharmistha | 2025-02-17 | I verified the implementation and tested various scenarios: partial names like 'chic' correctly return 'chicken', misspellings like 'chiken' also return 'chicken', and short queries like 'da' return relevant items. However, we need to ensure that no results message is shown for completely unrecognized inputs. This aligns with our PRD requirements. Closing the ticket now.
NUTR-009 | 1 | Shristi Sharmistha | 2025-02-12 | For the serving unit options, should we use a fixed list like gram/cup/tablespoon, or do we need to consider food-specific units?
NUTR-009 | 2 | Arjun Mehta | 2025-02-13 | After looking into USDA data, we can't use a generic list. Each food has specific serving units with varying gram weights. For example, a 'cup' of oats is 156 grams, but a 'cup' of spinach is only 30 grams. We need to pull these specific units to ensure accurate nutrient calculations.
NUTR-009 | 3 | Shristi Sharmistha | 2025-02-14 | How many serving unit options do typical USDA foods have? Should we update the PRD to reflect the need for food-specific serving units?
NUTR-009 | 4 | Arjun Mehta | 2025-02-15 | Most foods have 2-5 serving unit options. For instance, 'Chicken, broiled' has options like 100g, 1 cup chopped, and 1 oz. The PRD only mentions a 'serving unit dropdown' without specifying if it should be generic or food-specific. We should definitely update it.
NUTR-009 | 5 | Kabir Sharma | 2025-02-16 | From a UX standpoint, displaying food-specific units like '1 breast (172g)' for chicken is crucial. A generic list would confuse users since the same unit can represent vastly different amounts for different foods. We should prioritize food-specific units for clarity.
NUTR-009 | 6 | Shristi Sharmistha | 2025-02-17 | Let's go with food-specific serving units from USDA data. This approach is technically sound and enhances user experience. We need to update the USDA import to include serving unit data for each food.
NUTR-009 | 7 | Arjun Mehta | 2025-02-20 | I've updated the USDA import to include a food_serving_units table with food_id, unit_name, and gram_weight. I've also updated the adjust portion API to return these serving units. The recalculation logic will be: new_nutrient_value = (base_nutrient_per_100g × gram_weight × quantity) / 100.
NUTR-009 | 8 | Shristi Sharmistha | 2025-02-24 | I tested with various foods, and the calculations are accurate. For example, oats cup (156g) vs spinach cup (30g) show different nutrient values. Nutrients below 1% correctly show '-' and zero nutrients are blank. Everything looks good, closing this ticket.
NUTR-010 | 1 | Shristi Sharmistha | 2025-02-14 | We need to ensure that the meal type validation is strictly enforced. If a user comes from the food database tab, they must select a meal type before they can add food. How do you plan to display the warning message for this scenario?
NUTR-010 | 2 | Priya Nair | 2025-02-15 | I propose that we disable the Add button until a meal type is selected when coming from the food database tab. The warning message can be shown inline below the meal type dropdown. For users coming from the diary, the meal type will be pre-filled, and the Add button will be active immediately. This should cover both entry points effectively.
NUTR-010 | 3 | Priya Nair | 2025-02-17 | I've implemented the optimistic update. After the redirect to the diary, the newly added food must appear in the correct meal section without a page reload. I need to confirm with Arjun that the POST /food-logs endpoint returns the saved food log entry so we can update the diary state without a second GET request.
NUTR-010 | 4 | Arjun | 2025-02-18 | The POST /food-logs endpoint does return the complete saved entry, including all nutrient values. This allows the frontend to append the new entry to the diary state immediately. I tested it with multiple entries, and everything updates correctly. Priya, you can proceed with the implementation.
NUTR-015 | 1 | Shristi Sharmistha | 2025-02-14 | For this story, we need to clarify the dash vs blank rule. When should a column show '-' versus being completely empty? This distinction is crucial for user understanding.
NUTR-015 | 2 | Priya Nair | 2025-02-15 | There are two cases to consider: Case 1 is when the food has the nutrient but the value is zero (e.g., chicken has 0mg Vitamin C), which should show '-'. Case 2 is when the food simply does not have data for that nutrient in the USDA database, which should also show '-'. The unit column should still be visible even if the value is '-'.
NUTR-015 | 3 | Priya Nair | 2025-02-18 | I've completed the column rendering. However, I caught an edge case: if a user has 20 tracked nutrients and adds a food item that only has values for 5 of those nutrients, should the other 15 columns that show '-' still be rendered, or should they be hidden to reduce visual clutter?
NUTR-015 | 4 | Shristi Sharmistha | 2025-02-19 | All 20 columns must always be visible, even if they show '-'. This is intentional as users need to see that a food has no Vitamin C, even if the column appears empty. The '-' represents information, not absence of it. Please finalize the implementation accordingly and ensure the column order is correct.
NUTR-016 | 1 | Shristi Sharmistha | 2025-02-17 | For this story, we need to ensure that the cumulative totals are pinned at the bottom of each nutrient column. Can you confirm if the total row will be sticky or scroll with the content?
NUTR-016 | 2 | Priya Nair | 2025-02-18 | I propose that the total row should be sticky at the bottom of the diary viewport. This way, users can always see their running totals while scrolling through long lists of logged foods. This is especially important for users tracking 15-20 nutrients across many meals. Kabir, can you confirm that this was the intended design?
NUTR-016 | 3 | Priya Nair | 2025-02-20 | I checked with Kabir offline, and he confirmed that the sticky total row is indeed the intended design. I've implemented it using CSS position: sticky. The total row calculation sums across ALL meals for the date, including breakfast, lunch, dinner, snacks, and supplements. One edge case I noticed is that if a user logs a food item that contains no target nutrients, it should be treated as 0 in the cumulative total.
NUTR-016 | 4 | Shristi Sharmistha | 2025-02-22 | I added foods to breakfast, lunch, and dinner, and confirmed that the total row sums all three meals correctly. I also tested scrolling with a diary containing 20 foods, and the total row remained visible at the bottom while scrolling. The real-time update works perfectly when adding and deleting foods. I will close this ticket now.
NUTR-017 | 1 | Shristi Sharmistha | 2025-02-17 | The color coding logic has three distinct cases. Most critical and easy to miss: calorie in weight MAINTAIN goal shows yellow for both over and under, never red. This is different from weight loss/gain where over calorie is red. Kabir, please design the difference display, and Priya, you'll implement the three-case logic.
NUTR-017 | 2 | Kabir Sharma | 2025-02-18 | I've shared the Figma design where the difference row shows actual, goal, and difference values. The color will be applied to the difference value text. I noted the maintain weight case where over-calories shows yellow not red — this is subtle and important for our maintain weight user persona. Priya, please ensure this is clear in your implementation.
NUTR-017 | 3 | Priya Nair | 2025-02-20 | I've implemented the color logic using weight_goal_type from GOAL-001 backend to determine which color rule to apply for calories. For all other nutrients, I'm using the simpler under/on-track/over rule based on RDA and MAX values. Shristi, can you confirm an edge case: what if a user has no MAX value set for a micronutrient? Should the nutrient ever turn red in that case?
NUTR-017 | 4 | Shristi Sharmistha | 2025-02-22 | If no MAX value exists for a micronutrient, it can only be yellow (under) or green (on track). It should never turn red because we have no threshold to define 'over'. Priya, please update your implementation accordingly. Kabir, once that's done, can you verify the color rendering? I'll test all three weight goal types after that.
NUTR-018 | 1 | Shristi Sharmistha | 2025-02-17 | Can you confirm how the meal subtotal row will interact with the sticky total row from NUTR-016? Will there be two total rows visible?
NUTR-018 | 2 | Priya Nair | 2025-02-18 | The meal subtotal will appear inline after the last food of each meal, while the daily cumulative total will remain sticky at the bottom. They serve different purposes, so there won't be any conflict.
NUTR-018 | 3 | Priya Nair | 2025-02-20 | I've completed the implementation. One edge case to note: if a user has only one food item in a meal, the meal total will match that item's values. Should we still display the meal total row in this case?
NUTR-018 | 4 | Shristi Sharmistha | 2025-02-21 | Yes, we should always show the meal total row, even with a single food item. This ensures consistent UX. Please verify that the meal totals are correct for both single-food and multi-food meals, and confirm that they are bold without color.
NUTR-TASK-004 | 1 | Arjun Mehta | 2025-02-12 | I'm considering two approaches for the calculation engine: server-side or client-side. The server-side would trigger an API call for each change, but that could introduce latency. What do you think, Priya? Would client-side fit better with our React architecture?
NUTR-TASK-004 | 2 | Priya Nair | 2025-02-13 | I recommend going with client-side calculations. The server-side approach could risk exceeding the 1-second requirement, especially on slower connections. We can simply sum each nutrient value across the food log entries in React state, which should be instant. The formula would look like this: nutrients.reduce((acc, food) => acc + food.nutrientValue, 0).
NUTR-TASK-004 | 3 | Arjun Mehta | 2025-02-20 | I've implemented the calculation engine as a pure JavaScript function that takes an array of food log entries and returns the calculated totals. Priya, can you integrate this into the React state? Just to note, we should also handle edge cases like rapid deletions or edits to ensure totals still update correctly.
NUTR-TASK-004 | 4 | Shristi Sharmistha | 2025-02-24 | I tested the engine with rapid additions and deletions, and it performs well. However, we need to ensure that the recalculated values maintain unit consistency, especially when switching between grams and milligrams. This aligns with the PRD requirement that all values must be consistent. Closing the ticket now since everything checks out.