## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
NUTR-BUG-001 | Nutrient totals not updating instantly after food addition — React state issue | Bug | Done | P1 | Priya Nair | Sprint 7 | 5 | We've identified a critical issue where the cumulative nutrient totals in the food diary do not update in real-time after adding food items. Users have reported needing to refresh the page to see updated totals, which undermines the app's core functionality. This ticket aims to diagnose and fix the underlying React state management issue to ensure totals update seamlessly. | • Nutrient totals update within 1 second after any food item is added, edited, or deleted. • No manual refresh is needed by the user to see updated totals. • Cumulative totals must accurately reflect all diary actions.
NUTR-BUG-003 | Serving unit dropdown not resetting when user navigates back from adjust portion | Bug | Done | P2 | Priya Nair | Sprint 7 | 3 | We've identified a bug where the serving unit dropdown retains the previous food's serving unit selection when navigating back and selecting a new food. This issue was found during internal beta testing and affects user experience significantly. We need to ensure that the dropdown resets to the default serving unit for the newly selected food. | • Serving unit dropdown resets to default when navigating back from adjust portion page. • Previous search input is cleared when navigating back.
NUTR-BUG-004 | Supplement section showing in diary without toggle being enabled | Bug | Done | P2 | Priya Nair | Sprint 7 | 3 | We've identified a bug where the supplement section is appearing in the food diary for new users who haven't enabled the supplement toggle. This is contrary to our PRD requirements, which state that the supplement section should only be visible if the user has explicitly enabled it. We need to address this issue to ensure a seamless user experience. | • Supplement section is hidden for new users with toggle state undefined. • Existing users with toggle OFF see nothing. • Existing users with toggle ON see the supplement section.
NUTR-BUG-005 | Goal comparison colors incorrect for weight maintain calorie case | Bug | Done | P1 | Priya Nair, Kabir Sharma | Sprint 7 | 5 | During a design review, a bug was identified in the color coding for calorie comparisons in the weight maintain goal. The system incorrectly displays red for over-calorie inputs instead of the expected yellow. This issue needs to be resolved to align with the PRD requirements for accurate user feedback. | • Color coding for weight maintain goal must show yellow for over-calorie inputs. • Ensure color coding is consistent between food diary and analysis bar graph. • Comparison updates must occur within 1 second of any changes.
NUTR-BUG-006 | Future date diary showing previous day data instead of empty diary | Bug | Done | P1 | Arjun Mehta, Priya Nair | Sprint 7 | 5 | A beta user reported that when selecting a future date in the food diary, the app displays today's food instead of an empty diary. This inconsistency can confuse users trying to plan their meals. We need to investigate the data fetching logic and ensure that the diary reflects the correct date. | • When a future date is selected, if no food is logged, an empty diary with target nutrient columns should be displayed. • When a future date is selected, if food is logged, all logged food for that date should be shown. • The food diary must maintain a separate log for each calendar date. • Switching between dates should load within 2 seconds.
GOAL-BUG-002 | EER formula not switching to correct formula when user changes gender | Bug | Done | P1 | Arjun Mehta | Sprint 7 | 3 | We have a critical issue where the EER formula does not update when a user changes their gender in the profile settings. This can lead to users being provided with incorrect calorie goals, particularly affecting female users who may be on a male calorie budget. This ticket aims to address the missing trigger for recalculating the EER when gender or activity level changes occur. | • EER formula updates automatically when gender or activity level changes. • Notification banner appears on the calorie goal page after an automatic update.
GOAL-BUG-003 | Macro gram values not updating when user changes calorie goal | Bug | Done | P2 | Priya Nair, Arjun Mehta | Sprint 7 | 5 | We discovered a bug where the macro gram values do not update when a user changes their calorie goal. While the macro kcal values adjust correctly, the gram values remain static. This issue affects user experience and needs to be addressed to ensure accurate macro tracking. | • Changing the calorie goal updates the macro gram values instantly based on the new calorie target. • The gram values should reflect the correct calculations based on the updated kcal values.
GOAL-BUG-004 | Selected micronutrient goals disappearing after page refresh | Bug | Done | P1 | Priya Nair, Arjun Mehta | Sprint 7 | 5 | Multiple beta users have reported that their selected micronutrient goals disappear after refreshing the page or closing and reopening the app. This issue is critical as it affects the core functionality of tracking micronutrients. We need to ensure that selected micronutrients persist across sessions and are saved correctly in the database. | • Selected micros must persist even after logout, refresh, page navigation • Once the nutrient is set, the same nutrient remains even if the user logs off, refreshes, or moves to another page • For selected nutrient, RDA value should be set and saved as daily target
AN-BUG-002 | Bar graph colored segment exceeding container boundaries when intake over 100% | Bug | Done | P2 | Priya Nair | Sprint 7 | 3 | We've encountered a bug where the colored segment of the bar graph exceeds the container boundaries when the intake exceeds 100%. This issue was identified during design QA and causes layout problems, making the app look unprofessional. We need to address this promptly to ensure a seamless user experience. | • Bar graph loads within 2 seconds • The graph shall not cause noticeable lag or unresponsiveness in the application UI • Length of colored part represents actual consumption as % of target • Red if actual/target % > 100 (calorie weight loss/gain)
AN-BUG-003 | Analysis section not updating after user deletes food from diary | Bug | Done | P1 | Priya Nair | Sprint 7 | 3 | During beta testing, it was found that the analysis section does not update after a user deletes food from their diary. While the diary list and cumulative totals update correctly, the analysis bar graphs continue to display outdated nutrient values until the user manually navigates away and back. This issue needs to be addressed to ensure a seamless user experience. | • The analysis section updates automatically when food is deleted from the diary. • Updates to the graph occur within 1 second of the food log change.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
NUTR-BUG-001 | 1 | Priya Nair | 2025-04-03 | I've found that after adding a food item from any source, the cumulative nutrient totals at the bottom of the food diary do not update until the user manually refreshes the page. This is consistent across all food sources and meal types.
NUTR-BUG-001 | 2 | Shristi Sharmistha | 2025-04-03 | This is a P1 issue since it breaks the core value proposition of Nutrivana. We need to ensure real-time tracking. Priya, can you investigate the root cause?
NUTR-BUG-001 | 3 | Priya Nair | 2025-04-04 | The food diary component displaying cumulative totals is not subscribed to the food log state changes. When a food is added, the cumulative total component reads from its own local state, not from the shared food log array. This is why the totals don't update automatically.
NUTR-BUG-001 | 4 | Arjun Mehta | 2025-04-05 | The optimistic update pattern stores the new food log in a local component state inside the FoodDiaryList component. Since the cumulative total component is a sibling, it cannot access this state directly. We need to implement a shared context for the food log array.
NUTR-BUG-001 | 5 | Priya Nair | 2025-04-06 | I will implement FoodDiaryContext to lift the food log array state up to a shared level. This will allow all diary components to subscribe and update automatically. I’ll start pairing with you, Arjun.
NUTR-BUG-001 | 6 | Priya Nair | 2025-04-07 | I've implemented FoodDiaryContext and updated all diary components to subscribe to it. After testing, the totals now update within 200ms after any food action. This should resolve the issue.
NUTR-BUG-001 | 7 | Arjun Mehta | 2025-04-08 | The Context implementation looks clean. This fix also resolves AN-BUG-003, which had the same root cause. I’ll link that ticket here for reference.
NUTR-BUG-001 | 8 | Shristi Sharmistha | 2025-04-08 | I verified the fix on staging. The totals update correctly after rapid additions, deletions, and edits. I’ll deploy this to beta and follow up with the users who reported the issue. Closing this ticket now.
NUTR-BUG-003 | 1 | Priya Nair | 2025-04-04 | I've found that when a user navigates back from the adjust portion page, the serving unit dropdown retains the previous selection. For example, after selecting '1 breast (172g)' for chicken and then going back to select oats, the dropdown still shows '1 breast' instead of the default oats serving unit.
NUTR-BUG-003 | 2 | Arjun Mehta | 2025-04-05 | Looking into the implementation from NUTR-009, it seems the selected value is maintained in component state, which leads to this issue. We need to ensure that when the food changes, the selected index resets to 0. This will prevent the dropdown from showing a unit that doesn't correspond to the new food.
NUTR-BUG-003 | 3 | Priya Nair | 2025-04-06 | I've traced the bug further. The selected serving unit is stored as an array index, which persists even when the dropdown options change. For chicken, index 2 corresponds to '1 breast', but for oats, index 2 corresponds to '1 oz (28g)'. We need to change this to store the selected unit as a string instead of an index to avoid this cross-food contamination.
NUTR-BUG-003 | 4 | Arjun Mehta | 2025-04-07 | I agree that storing the unit name string is a safer approach. However, we should consider if there are scenarios where a user might want to keep the same serving unit across different foods. For instance, someone who always thinks in '100g' might prefer to stay on that unit when switching foods.
NUTR-BUG-003 | 5 | Shristi Sharmistha | 2025-04-08 | Is it possible that we could implement a check to preserve the selection if the new food has the same unit name? This could enhance user experience for those who prefer consistency in their measurements.
NUTR-BUG-003 | 6 | Arjun Mehta | 2025-04-09 | I recommend we always reset to the default unit on food change. The most common use case is that users will expect the default serving unit for each food. The edge case of wanting to keep the same unit is less common and could lead to confusion.
NUTR-BUG-003 | 7 | Priya Nair | 2025-04-10 | I've implemented the fix. Now, when the food_id changes, the selected serving unit resets to null, which causes the component to select the first (default) unit. I've tested this with multiple food selections, and it seems to work correctly.
NUTR-BUG-003 | 8 | Shristi Sharmistha | 2025-04-10 | I've verified the fix. I selected chicken with '1 breast', navigated back, and then selected oats — the default oats unit shows correctly. I've tested several food switches, and each time the correct default unit is displayed. We can close this ticket.
NUTR-BUG-004 | 1 | Priya Nair | 2025-04-05 | I found a bug during beta testing. New users are seeing the supplement section in their food diary even though they haven't enabled the toggle. Steps to reproduce: create a new user account and check the diary. This needs to be fixed to align with our PRD.
NUTR-BUG-004 | 2 | Kabir Sharma | 2025-04-06 | Checked the Figma design. The supplement section should be completely hidden when the toggle is off. Priya, could you look into the conditional rendering logic in the diary component?
NUTR-BUG-004 | 3 | Priya Nair | 2025-04-07 | I've traced the issue. The conditional rendering is currently set as `if (supplementEnabled ¦¦ supplementEnabled === undefined)`. This logic is incorrect; it should be `if (supplementEnabled === true)`. The `undefined` case should show the dismissible prompt instead. I'll make the necessary changes.
NUTR-BUG-004 | 4 | Kabir Sharma | 2025-04-08 | That makes sense. Just to confirm, new users should see the dismissible prompt, and existing users with the toggle OFF should see nothing. Can you also ensure that existing users with the toggle ON see the supplement section?
NUTR-BUG-004 | 5 | Shristi Sharmistha | 2025-04-09 | How many beta users have been affected by this? If they logged data in the supplement section thinking it was supposed to be there, what happens to that data when we fix this?
NUTR-BUG-004 | 6 | Arjun (CTO) | 2025-04-10 | Checked the database, and it turns out none of the affected beta users have logged any supplement entries. They only saw the section. So we can safely fix this without any data migration concerns.
NUTR-BUG-004 | 7 | Priya Nair | 2025-04-11 | I've implemented the fix. Now we have three explicit states: `undefined/null` shows the dismissible prompt, `false` shows nothing, and `true` shows the supplement section. I've tested all three states with both fresh and existing accounts.
NUTR-BUG-004 | 8 | Kabir Sharma | 2025-04-11 | I verified the design against Figma. New users see the prompt correctly, and the dismiss functionality works as expected. Shristi, can you verify this on staging before we deploy to beta?
NUTR-BUG-005 | 1 | Kabir Sharma | 2025-04-04 | I spotted a bug during the design QA. I created a test account with a weight maintain goal and logged food that exceeded the calorie target. The difference cell turned red instead of yellow. According to the PRD, it should show yellow for over-calorie inputs in this case. I've attached a screenshot for reference.
NUTR-BUG-005 | 2 | Priya Nair | 2025-04-05 | I've reviewed the color logic implementation from NUTR-017. The code has three branches for weight loss, gain, and maintain. The weight maintain branch is indeed implemented, but there's a logic error. The condition `if (goalType === 'maintain' && percentage > 100) return 'yellow'` is correct, but it’s checked after a general condition that returns red for any percentage over 100. This means it never reaches the maintain-specific logic.
NUTR-BUG-005 | 3 | Kabir Sharma | 2025-04-06 | Are all three cases broken or just the over-100% maintain case? I want to ensure we’re not missing other potential issues. Can we confirm the under and exact cases are functioning correctly for all goal types?
NUTR-BUG-005 | 4 | Priya Nair | 2025-04-07 | I checked all three weight goal types against the percentage conditions. The under and exact cases are correct for all goal types. The only issue is with the over case for weight maintain due to the early return in the general condition. We need to restructure the logic to fix this.
NUTR-BUG-005 | 5 | Arjun (CTO) | 2025-04-08 | I reviewed the code and confirmed the early return bug. The proposed fix should check the goal_type first before applying the general percentage rules. The new logic should ensure that maintain cases are handled correctly. This aligns with the PRD and clinical reasoning.
NUTR-BUG-005 | 6 | Shristi Sharmistha | 2025-04-08 | I confirm that the proposed fix aligns with the PRD requirements and the clinical reasoning discussed in NUTR-017. The early return pattern is indeed dangerous for case-specific logic. We need to ensure that goal_type is evaluated first in all cases.
NUTR-BUG-005 | 7 | Priya Nair | 2025-04-09 | I've implemented the restructured condition where goal_type is evaluated first, followed by percentage conditions within each branch. I've also fixed the same logic in the AN-003 color function since both the food diary and analysis share this function.
NUTR-BUG-005 | 8 | Kabir Sharma | 2025-04-09 | I tested all combinations: weight loss under/exact/over are correct, weight gain under/exact/over are correct, and weight maintain under/exact/over are all correct now (under=yellow, exact=green, over=yellow). I’ve verified that the design matches the expected colors in all scenarios. Shristi, can you verify this on staging?
NUTR-BUG-006 | 1 | Shristi Sharmistha | 2025-04-06 | We received a report from beta user Rahul stating that when he taps on tomorrow's date, he sees today's food instead. Priya and Arjun, can you reproduce this issue and investigate?
NUTR-BUG-006 | 2 | Priya Nair | 2025-04-07 | I reproduced the bug. When I navigate to tomorrow's date, it shows today's food. The date picker shows the correct date, but the diary data is not updating. It seems like the data fetching logic is out of sync with the date picker.
NUTR-BUG-006 | 3 | Arjun Mehta | 2025-04-08 | I've looked into the data fetching logic. The food diary component uses both the URL parameter and React state for the date. The issue arises because the useEffect for fetching data is dependent on the URL parameter, which doesn't change when the date picker updates. We need to fix this.
NUTR-BUG-006 | 4 | Priya Nair | 2025-04-09 | To clarify the PRD, we need to ensure that when a future date is selected and no food is logged, the diary should show an empty state. This wasn't explicitly mentioned before. Also, we should consider edge cases like switching dates at midnight.
NUTR-BUG-006 | 5 | Arjun Mehta | 2025-04-10 | I propose two solutions: Option A is to update the URL when the date changes, which keeps the URL in sync with the app state. Option B is to change the useEffect to watch the React state instead of the URL parameter. Option A is more robust but takes longer to implement.
NUTR-BUG-006 | 6 | Shristi Sharmistha | 2025-04-11 | Does Option A affect the browser back button functionality? Users should be able to navigate back to the previous date without issues. If Option A supports this, I recommend we go with it.
NUTR-BUG-006 | 7 | Arjun Mehta | 2025-04-12 | I've implemented Option A. The date picker now updates the URL correctly, and the useEffect watches the URL parameter. Both the URL and React state are in sync, and the back button works as expected.
NUTR-BUG-006 | 8 | Shristi Sharmistha | 2025-04-12 | I verified the fix. Navigating to tomorrow shows an empty diary if no food is logged. I also tested the midnight edge case from NUTR-022, and the food logged at 11:55 PM and 12:05 AM appears on the correct dates. Closing this ticket.
GOAL-BUG-002 | 1 | Shristi Sharmistha | 2025-04-05 | Preethi reported that after changing her gender from male to female, her calorie goal did not update. This is a health-critical bug that needs urgent attention. Can you investigate this, Arjun?
GOAL-BUG-002 | 2 | Arjun Mehta | 2025-04-06 | I've reproduced the issue using Preethi's profile: female, age 28, active lifestyle, 65kg, and 170cm. The expected EER for her should be around 2245 kcal, but the system is showing 2847 kcal, which matches the male formula. Confirmed the bug.
GOAL-BUG-002 | 3 | Arjun Mehta | 2025-04-07 | Investigating the EER formula logic, I found that the formula lookup is based on gender, age group, and activity level. The recalculation only occurs when the user visits the calorie goal page, which isn't compliant with the PRD requirement of automatic updates. We need to implement a trigger on the user_profile table.
GOAL-BUG-002 | 4 | Shristi Sharmistha | 2025-04-08 | Should the trigger automatically save the new EER, or should it prompt the user to confirm the changes? I’m concerned about changing someone’s calorie goal without their awareness.
GOAL-BUG-002 | 5 | Arjun Mehta | 2025-04-09 | I recommend that we auto-recalculate and save the new EER. The PRD states that a new formula must be selected automatically. However, we should also add a notification banner on the calorie goal page to inform users: 'Your calorie goal was updated due to profile changes. Please review and confirm.' This keeps the user informed.
GOAL-BUG-002 | 6 | Arjun Mehta | 2025-04-10 | I've implemented the trigger on the user_profile table. It now fires when gender, age, height, weight, or activity_level changes. It calls the EER recalculation function and saves the new values. A `profile_changed_flag` is set for the calorie goal page to show the notification banner.
GOAL-BUG-002 | 7 | Shristi Sharmistha | 2025-04-11 | I tested the changes with Preethi's values. After changing her gender from male to female, the calorie goal updated to 2245 kcal immediately. The notification banner also appeared correctly. I also tested changes in age and activity level, and they updated as expected. This looks good to close.
GOAL-BUG-002 | 8 | Arjun Mehta | 2025-04-11 | Great, I'm glad the tests went well. I’ll notify Preethi that her account has been corrected and close this ticket now.
GOAL-BUG-003 | 1 | Priya Nair | 2025-04-07 | I found a bug during beta testing. When a user changes their calorie goal from 2000 to 1800 kcal, the macro gram values do not update. For example, carbs should show 180g instead of 200g. The macro percentages remain unchanged, but the gram values are frozen at the old calculation.
GOAL-BUG-003 | 2 | Arjun Mehta | 2025-04-08 | I reviewed the macro calculation chain. The issue seems to be that the gram values are calculated in a separate useEffect that only watches the macro percentages. It should also watch the kcal values to trigger updates when the calorie goal changes.
GOAL-BUG-003 | 3 | Priya Nair | 2025-04-09 | I traced the gram calculation logic and confirmed that the dependency array in the useEffect is incorrect. It should watch the kcal values instead of the percentages. This is why the gram values are not updating when the calorie goal changes.
GOAL-BUG-003 | 4 | Arjun Mehta | 2025-04-09 | Exactly, Priya. The gram values should update through two paths: changing the calorie goal or changing the macro percentages. Both paths need to trigger the same gram calculation. Let's fix the dependency array to watch kcal values.
GOAL-BUG-003 | 5 | Shristi Sharmistha | 2025-04-10 | This sounds similar to the floating point issue we had in GOAL-007. Are there other parts of the macro calculation chain that might have similar dependency issues? We should ensure this doesn't happen again.
GOAL-BUG-003 | 6 | Priya Nair | 2025-04-11 | I did a systematic audit of all macro-related useEffects. I found two more with similar issues where the required deficit/surplus value does not recalculate when macros change. I will fix these along with the gram calculation issue.
GOAL-BUG-003 | 7 | Priya Nair | 2025-04-12 | I updated the gram calculation useEffect to watch kcal values and fixed the two other dependency issues found in the audit. I tested the full chain: changing calorie goal updates kcal, which now updates grams and deficit/surplus correctly.
GOAL-BUG-003 | 8 | Shristi Sharmistha | 2025-04-12 | I verified all three paths: changing calorie goal, changing macro percentage, and changing both together. The gram values update correctly in all scenarios. The floating point edge case from GOAL-007 also passes. We can close this ticket.
GOAL-BUG-004 | 1 | Shristi Sharmistha | 2025-04-06 | We've received multiple reports from beta users about their micronutrient selections disappearing after a page refresh. This is a significant issue that needs immediate attention. Priya and Arjun, can you investigate this as a P1?
GOAL-BUG-004 | 2 | Priya Nair | 2025-04-07 | I've reproduced the bug. I selected 8 micronutrients (calcium, iron, folate, vitamin A, vitamin C, vitamin D, magnesium, zinc) and refreshed the page. All selections were lost, and the food diary also lost the micronutrient columns. This confirms the selections are not persisting.
GOAL-BUG-004 | 3 | Priya Nair | 2025-04-08 | Looking into the implementation from GOAL-010, it seems the selected_micros are only stored in React state. When the component unmounts, the state is destroyed, and nothing is saved to Supabase. We need to implement the API call to save these selections.
GOAL-BUG-004 | 4 | Arjun Mehta | 2025-04-09 | I checked the database and confirmed that there are no saved records of micronutrient selections. The user_micronutrient_goals table is empty. We need to add the INSERT call to save the selections when a user selects a micronutrient.
GOAL-BUG-004 | 5 | Shristi Sharmistha | 2025-04-10 | Priya, how are the food diary columns appearing if nothing is saved in the database? Shouldn't they be empty? I want to ensure we understand how the UI is functioning.
GOAL-BUG-004 | 6 | Priya Nair | 2025-04-10 | The food diary columns are reading from the same React state as the goal settings during the session. Everything works fine until a refresh. We need to ensure the food diary reads from the database instead.
GOAL-BUG-004 | 7 | Arjun Mehta | 2025-04-11 | I've implemented the database persistence with a POST /user-micronutrient-goals endpoint. This will save user_id, nutrient_id, is_tracked, rda_value, and is_custom. On page load, GoalSettings will fetch saved selections from the database.
GOAL-BUG-004 | 8 | Priya Nair | 2025-04-12 | I've implemented the load-from-database functionality on mount. The GoalSettings component now fetches the user's saved micronutrient selections on initial render. I tested it by selecting 8 micros, refreshing, and all selections persisted. I've also confirmed that the food diary columns are now generated from the database. Closing the ticket.
AN-BUG-002 | 1 | Kabir Sharma | 2025-04-08 | I've noticed that the colored segment of the bar graph is overflowing the container when the intake exceeds 100%. For example, at 150% of the calorie goal, the CSS width is set to 150%, causing it to overlap with other UI elements. This needs urgent attention.
AN-BUG-002 | 2 | Priya Nair | 2025-04-09 | The issue seems to stem from the inline style `width: ${percentage}%` applied to the colored segment. We should implement a maximum width constraint to prevent overflow. I suggest capping the width at 100% and using a red color to indicate over-target status instead.
AN-BUG-002 | 3 | Kabir Sharma | 2025-04-10 | Capping the width at 100% is a good start, but how do we visually communicate that the user is over their target? If both 100% and 150% show a full red bar, we might confuse users. I propose either showing the over-percentage number prominently or adding a small overflow indicator.
AN-BUG-002 | 4 | Shristi Sharmistha | 2025-04-11 | From a user testing perspective, which approach would be clearer? We've seen users struggle with interpreting the bar graph. Adding more visual complexity might worsen confusion. We need to ensure clarity in our design.
AN-BUG-002 | 5 | Ananya | 2025-04-11 | I recommend going with the option that caps at 100% and displays the over-target percentage in bold red below the bar. This aligns with our findings from AN-002 where explicit numbers were preferred over visual metaphors. Simplicity is key.
AN-BUG-002 | 6 | Kabir Sharma | 2025-04-12 | I've designed the cap + number approach. The bar will cap at 100% width, be colored red, and the percentage will be displayed in bold red below with an 'over target' label. This should maintain consistency with the previous design from AN-002.
AN-BUG-002 | 7 | Priya Nair | 2025-04-12 | I've implemented the CSS fix by adding `max-width: 100%` and `overflow: hidden` to the colored segment. The percentage display now shows the value and 'over target' label in red when the percentage exceeds 100. The layout is stable across all tested values.
AN-BUG-002 | 8 | Kabir Sharma | 2025-04-13 | I've verified the changes with various test cases including 50%, 100%, 150%, 200%, and even 500%. The layout remains stable and readable at all values. I believe we can close this ticket now as it meets the requirements.
AN-BUG-003 | 1 | Priya Nair | 2025-04-04 | I've found a bug where deleting food from the diary doesn't update the analysis section. For example, if I log 200g of chicken, the protein bar shows 50%. After deleting the chicken, the bar still shows 50% until I navigate away and back. This is a critical issue that needs fixing.
AN-BUG-003 | 2 | Priya Nair | 2025-04-04 | The root cause seems to be similar to NUTR-BUG-001. The analysis section isn't subscribing to the FoodDiaryContext changes. We need to extend the context subscription to the analysis components so they update automatically.
AN-BUG-003 | 3 | Arjun Mehta | 2025-04-05 | Confirming that the FoodDiaryContext fix from NUTR-BUG-001 was applied to the diary components, but not to the analysis section. The analysis still relies on its local state, which only updates on initial mount or manual navigation. We need to address this.
AN-BUG-003 | 4 | Priya Nair | 2025-04-05 | I mentioned this in NUTR-BUG-001 comment 7. The fix will be to subscribe the analysis components to FoodDiaryContext, allowing them to re-fetch and re-render when the food log array changes.
AN-BUG-003 | 5 | Shristi Sharmistha | 2025-04-06 | Should we calculate the analysis from the food log array in Context or re-fetch from the API on every change? Client-side calculation is faster but requires that the logic matches the food log state precisely.
AN-BUG-003 | 6 | Arjun Mehta | 2025-04-06 | I recommend going with client-side calculations. The FoodDiaryContext already contains the complete food log array for the current date, and we can sum those nutrient values without additional API calls. This aligns with our approach from NUTR-TASK-004.
AN-BUG-003 | 7 | Priya Nair | 2025-04-07 | I've implemented the fix. The analysis components now subscribe to FoodDiaryContext. When the food log changes, the analysis components will re-calculate nutrient totals client-side and update the bar graphs accordingly.
AN-BUG-003 | 8 | Shristi Sharmistha | 2025-04-08 | I've verified the fix. Adding chicken updates the protein bar in the analysis, editing the portion updates it, and deleting chicken correctly updates it to 0%. All changes are reflected within 200ms, matching the performance we aimed for. Closing this ticket.