## Tickets
Ticket ID | Title | Type | Status | Priority | Assignee | Sprint | Story Points | Description | Acceptance Criteria
CF-BUG-001 | Custom food edits reflecting in diary for ALL dates instead of only from edit date onwards | Bug | Done | P1 | Arjun Mehta | Sprint 9 | 5 | We've identified a critical bug affecting the historical nutrient data for users who edit custom foods. When users change nutrient values, the updates are incorrectly applied to all past diary entries instead of just the entries from the date of the edit. This issue compromises data integrity for several beta users, and we need to address it urgently. | • Custom food edits should only affect diary entries from the date of the edit onwards. • Historical diary entries should reflect the nutrient values as they were before the edit.
CF-BUG-002 | Deleted custom food still appearing in past diary entries | Bug | Done | P2 | Arjun Mehta | Sprint 9 | 5 | A beta user reported that after deleting a custom food item, it still appears in their past diary entries. The user cannot edit or delete this entry, resulting in a broken state. We need to ensure that the deletion of a custom food item also updates any related diary entries appropriately. | • Deleted custom food records should not appear in the diary. • Diary entries should display the last known nutrient values for deleted custom foods.
AN-BUG-001 | 7-day trend not calculating correctly for days with no food logged | Bug | Done | P0 | Arjun Mehta, Priya Nair | Sprint 9 | 8 | We've identified a critical bug affecting the 7-day trend calculation in our app. Users are reporting that days with no food logged are completely missing from the trend graph, leading to incorrect visual representation of their dietary habits. This issue needs immediate attention as it impacts user experience significantly. | • Trend shown for selected date and 6 days before it • Days with no logs should show as 0% (not null/gap) • Updates to graph after logging or removing food render within 1 second
AN-BUG-004 | Wrong color shown for weight maintain calorie goal in analysis bar graph | Bug | Done | P1 | Arjun Mehta, Priya Nair | Sprint 9 | 3 | During launch-day QA, we discovered that the analysis bar graph is showing the wrong color for the weight maintain calorie goal. While the food diary color was fixed in Sprint 7, the analysis section still displays red for over-calorie, instead of the expected yellow. This needs to be addressed to ensure consistency across the app. | • Analysis bar graph shows yellow for over-calorie in weight maintain goal • Color logic is consistent with food diary section
AN-BUG-005 | DV% values in analysis showing more than 2 decimal places | Bug | Done | P2 | Priya Nair | Sprint 9 | 3 | During launch-day QA, it was discovered that the analysis section of the app displays DV% values for some micronutrients with excessive decimal places, such as '45.6789%' instead of the required '45.68%'. This issue arises because the rounding logic was not applied to the text labels, even though the bar graph displays rounded values. We need to ensure all numeric displays adhere to the PRD requirement of rounding to 2 decimal points. | • All DV% values in the analysis section are rounded to 2 decimal places. • The 'actual consumed' and 'remaining/over' amount displays also round to 2 decimal places.
TECH-005 | Data isolation testing — user A cannot see or modify user B's data | Task | Done | P0 | Arjun Mehta | Sprint 9 | 5 | This task focuses on ensuring that user data is properly isolated in our app. We need to confirm that user A cannot access or modify user B's data in any way. This involves creating a comprehensive test suite that covers various scenarios, including reading, modifying, and deleting data. The results will be critical for our public launch. | • User A cannot read User B's food logs • User A cannot read User B's custom foods • User A cannot read User B's goal settings • User A cannot delete User B's diary entries • User A cannot edit User B's custom foods
CF-EPIC-001 | Epic: Custom Food Management — closing on MVP completion | Epic | Done | P0 | Arjun Mehta | Sprint 9 | 8 | The Custom Food Management epic is now complete with all child tickets resolved. Users can create, log, edit, and delete custom foods, with the Indian food gap addressed. We've seen real user engagement with 47 custom entries, including Chapati and Dal Tadka. This epic closure reflects our journey and the learning we've gained about data versioning. | • All child tickets are closed and validated. • Users can manage custom foods without data integrity issues. • Feature usage data is collected and analyzed.

## Comments
Ticket ID | Comment Number | Author | Date | Comment Text
CF-BUG-001 | 1 | Shristi Sharmistha | 2025-04-29 | This is a P1 data integrity bug. We need to prioritize fixing this immediately as it affects multiple beta users' historical data.
CF-BUG-001 | 2 | Arjun Mehta | 2025-04-30 | I've started investigating the effective_date versioning from CF-007. The custom_food_versions table has the necessary data, but I need to check the query logic for diary entries to see how it's fetching the nutrient values.
CF-BUG-001 | 3 | Arjun Mehta | 2025-05-01 | I've traced the query logic. The join condition for fetching custom food nutrient values is using `WHERE effective_date <= NOW()` instead of `WHERE effective_date <= diary_date_string`. This is causing the latest version to be returned regardless of the diary date.
CF-BUG-001 | 4 | Priya Nair | 2025-05-02 | I checked the frontend API call to `/food-logs?date=YYYY-MM-DD`. It uses the date parameter for filtering food logs but not for fetching custom food nutrient details. This is a one-line bug that needs fixing.
CF-BUG-001 | 5 | Shristi Sharmistha | 2025-05-03 | Can we quantify how many users are affected by this issue? It’s crucial to understand the scope before we proceed with the fix.
CF-BUG-001 | 6 | Arjun Mehta | 2025-05-04 | I ran a query and found 8 users who have both custom food entries and have edited those foods. All of them have experienced this issue. The original values are preserved in the custom_food_versions table, so we can restore the correct display without data migration.
CF-BUG-001 | 7 | Arjun Mehta | 2025-05-05 | I've implemented the fix by changing the query to use the diary date string for the effective_date condition. The new condition is `WHERE effective_date <= $diary_date`.
CF-BUG-001 | 8 | Shristi Sharmistha | 2025-05-07 | I verified the fix by editing the protein value for 'Homemade Paneer'. The historical entries now reflect the correct nutrient values. I'll notify the affected users and close this ticket.
CF-BUG-002 | 1 | Shristi Sharmistha | 2025-04-29 | We've received a report from beta user BT-156 stating that deleted custom foods still show up in their diary entries. They can't interact with these entries. Let's investigate how this is happening.
CF-BUG-002 | 2 | Arjun Mehta | 2025-04-30 | I've reviewed the soft delete implementation from CF-006. The custom_foods record gets a deleted_at timestamp, but food_logs entries are not updated. They still reference the custom_food_id of the deleted item, which is why they appear broken in the diary.
CF-BUG-002 | 3 | Arjun Mehta | 2025-04-30 | The diary rendering logic joins food_logs with custom foods, but since deleted foods have deleted_at set, the join returns null data. This results in empty rows in the diary. We need to ensure that food_logs store a snapshot of nutrient values at the time of logging.
CF-BUG-002 | 4 | Priya Nair | 2025-05-01 | When the custom food data is null in the diary, it shows an empty row with disabled edit/delete buttons. This is confusing for users. We need to clarify how to handle deleted custom foods in diary entries.
CF-BUG-002 | 5 | Shristi Sharmistha | 2025-05-02 | What should be the correct behavior for diary entries when a user deletes a custom food? Should we delete the entries, keep them with last known values, or show a placeholder?
CF-BUG-002 | 6 | Arjun Mehta | 2025-05-03 | I recommend we preserve the diary entries with the last known nutrient values. This aligns with our historical data integrity approach. I'll implement a fix that stores a nutrient snapshot in the food_logs table.
CF-BUG-002 | 7 | Arjun Mehta | 2025-05-05 | I've implemented the fix. Now, food_logs will store a snapshot of nutrient values at the time of logging. Deleted foods will show their last-known name and nutrient values correctly in the diary.
CF-BUG-002 | 8 | Shristi Sharmistha | 2025-05-06 | I've tested the fix by deleting the custom food 'Test Food'. It still appears in past diary entries with the correct nutrient values, and I can edit or delete the entry from the diary. This requires a one-time migration to backfill existing food_log entries without snapshots. Closing the ticket.
AN-BUG-001 | 1 | Shristi Sharmistha | 2025-04-29 | Given the number of reports we've received, I am marking this as P0. The trend graph is crucial for our users, especially for those tracking their weight. Let's assign this to Arjun and Priya immediately.
AN-BUG-001 | 2 | Arjun Mehta | 2025-04-30 | I've looked into the trend endpoint from AN-004. The current SQL query only returns rows for dates that have food_log entries. This means that days with zero logs return no row at all. We need to modify this to ensure we get a complete set of 7 data points.
AN-BUG-001 | 3 | Priya Nair | 2025-04-30 | I can confirm that the frontend charting library connects consecutive data points. If we only receive 4 data points for 7 days, the line will incorrectly imply continuity. We need to ensure that the trend line accurately reflects all 7 days.
AN-BUG-001 | 4 | Arjun Mehta | 2025-05-01 | To fix this, we could either generate a date series in SQL and LEFT JOIN it with food_logs, or we could fetch the 7 dates in application code and fill in 0 for any missing dates. What do you think?
AN-BUG-001 | 5 | Priya Nair | 2025-05-01 | I recommend the second option. Filling in the zeros at the application level is cleaner and avoids database-specific syntax issues. We already know the 7-date range being requested.
AN-BUG-001 | 6 | Arjun Mehta | 2025-05-02 | Agreed. I'll implement the zero-fill logic in the trend endpoint. After fetching the food_log aggregates, I'll create a complete 7-date array, ensuring we return exactly 7 data points regardless of the logs.
AN-BUG-001 | 7 | Priya Nair | 2025-05-05 | I've updated the frontend to ensure it always receives exactly 7 data points. Zero days will now show as a point at 0% with a visual indicator, ensuring clear distinction between zero intake days and low-intake days.
AN-BUG-001 | 8 | Shristi Sharmistha | 2025-05-08 | I've tested the updates. When logging 7 consecutive days, all points show correctly. With only 3 days logged, the trend shows all 7 points with zero days indicated as 0%. This looks good. Let's close the ticket and notify the beta users.
AN-BUG-004 | 1 | Shristi Sharmistha | 2025-04-30 | I've tested the analysis bar graph for a weight maintain account and noticed that it shows red for over-calorie instead of yellow. The food diary color was fixed in Sprint 7, but this section still needs attention.
AN-BUG-004 | 2 | Arjun Mehta | 2025-04-30 | I traced the color functions and confirmed that the fix from NUTR-BUG-005 was applied to the `getDiaryColorClass()` function. However, the analysis bar graph uses a separate function `getAnalysisBarColor()` which hasn't been updated yet.
AN-BUG-004 | 3 | Priya Nair | 2025-05-01 | This is exactly the scenario we flagged in NUTR-BUG-008. The color functions are separate, even though they implement the same logic. We should refactor them into a shared function to avoid this issue in the future.
AN-BUG-004 | 4 | Shristi Sharmistha | 2025-05-01 | Agreed. We've identified this pattern multiple times now. We need a single shared color logic function that both the food diary and analysis can use. Arjun, can you handle the refactor?
AN-BUG-004 | 5 | Arjun Mehta | 2025-05-02 | I'll create a single `getNutrientColorClass(goalType, percentage, nutrientType)` function in a shared utilities file. This way, any future color logic changes will only need to be made in one place.
AN-BUG-004 | 6 | Priya Nair | 2025-05-03 | I've implemented the refactoring. The previous functions have been removed and replaced with imports from the shared function. I've tested to ensure both sections display identical colors for all weight goal types.
AN-BUG-004 | 7 | Priya Nair | 2025-05-04 | I ran a comprehensive color test matrix: 3 weight goal types × 4 nutrient types × 3 percentage ranges = 36 test combinations. All tests passed correctly in both food diary and analysis. I'll document this as a regression test suite.
AN-BUG-004 | 8 | Shristi Sharmistha | 2025-05-06 | I've verified the analysis bar graph now shows yellow for over-calorie in the weight maintain goal, which is correct. All other combinations are consistent as well. Closing this ticket as the shared utility approach prevents any future recurrence of this bug.
AN-BUG-005 | 1 | Shristi Sharmistha | 2025-04-30 | I've noticed that the analysis section shows unrounded DV% values like '45.6789%' and '12.3456%'. The food diary and adjust portion page round correctly, but it seems the analysis section was built separately and missed this rounding logic.
AN-BUG-005 | 2 | Priya Nair | 2025-05-01 | I traced the DV% calculation in the analysis section. The bar graph uses rounded values, but the text label shows the raw float from the database. We need to apply rounding to the text label as well. The calculation is done as (actual/target)%, but the text label is using the unrounded float.
AN-BUG-005 | 3 | Arjun Mehta | 2025-05-02 | The unrounded float is due to how we're aggregating nutrient totals with SUM(quantity × nutrient_value_per_unit). This produces floating point values like 45.6789. We should implement rounding before displaying these values. The food diary does this correctly using parseFloat(toFixed(2)).
AN-BUG-005 | 4 | Priya Nair | 2025-05-03 | I've checked all numeric displays in the analysis section and found three places where rounding is missing: (1) DV% text label, (2) 'actual consumed' value, and (3) 'remaining/over' amount display. We need to ensure all these are rounded.
AN-BUG-005 | 5 | Arjun Mehta | 2025-05-04 | This rounding issue has appeared multiple times (GOAL-007, NUTR-BUG-009, and now AN-BUG-005). We should create a shared utility function formatNutrient(value, decimalPlaces) to handle this consistently across the app.
AN-BUG-005 | 6 | Priya Nair | 2025-05-05 | I've implemented the formatNutrient utility function. Now all numeric nutrient displays across the food diary, adjust portion page, analysis, and goal setting use this single function with a default of 2 decimal places.
AN-BUG-005 | 7 | Priya Nair | 2025-05-05 | I've applied the formatNutrient function to all three unrounded displays in the analysis section. I also did a sweep of the codebase and found two more instances in the goal setting page that were showing unrounded values. I've fixed those as well.
AN-BUG-005 | 8 | Shristi Sharmistha | 2025-05-05 | I've verified the changes. The analysis section now shows '45.68%' instead of '45.6789%', and '34.79g remaining' instead of '34.7892g remaining'. All numeric values across the app are consistently rounded to 2 decimal places. Closing the ticket. The formatNutrient utility is a great addition for consistency.
TECH-005 | 1 | Arjun Mehta | 2025-04-29 | I've created a comprehensive data isolation test suite that includes five key scenarios. Each test uses two real accounts to ensure accurate results. The tests cover whether User A can access User B's food logs, custom foods, goal settings, and whether User A can delete or edit User B's entries.
TECH-005 | 2 | Arjun Mehta | 2025-05-01 | I ran all isolation tests against the Supabase RLS policies from TECH-001. All tests passed successfully. User A querying User B's data returns empty results, and attempts to DELETE or PATCH User B's records return a 403 error. The RLS policies are functioning as expected.
TECH-005 | 3 | Arjun Mehta | 2025-05-03 | I did find a concern during testing related to CF-BUG-002. The nutrient snapshots in food_logs store food names and nutrient values directly. While User A cannot access User B's custom_food_id due to RLS, it's worth noting that if RLS failed, User A could theoretically see User B's food names. However, tests confirm this scenario is impossible, so there's no real vulnerability.
TECH-005 | 4 | Shristi Sharmistha | 2025-05-05 | All isolation tests have passed, and I appreciate the thorough documentation of the test cases. Please add these to the regression test suite for future reference. The CF-BUG-002 snapshot concern is noted as a theoretical analysis, but it’s good to document it. I'm signing off on this ticket as the data security is solid for our public launch.
CF-EPIC-001 | 1 | Shristi Sharmistha | May 10, 2025 | I'm closing the Custom Food Management epic as all child tickets are resolved. The effective date versioning has been implemented successfully after three iterations, and we've validated that users can create and manage custom foods without issues. However, we need to ensure that when users delete a custom food, the corresponding entries in the food_logs table are preserved. This edge case was highlighted during testing.
CF-EPIC-001 | 2 | Arjun Mehta | May 10, 2025 | I acknowledge the closure of this epic. The journey from identifying the Indian food gap to seeing users log Chapati and Dal Tadka has been significant. I want to note that we need to update the PRD to reflect that the food_logs table must maintain historical data for deleted foods, ensuring that users have a complete record of their entries. This will help us avoid any confusion in future iterations.