# Sprint 13 Planning — Nutrivana

June 24 to June 30, 2025

Finalize all Q2 deliverables by shipping prenatal presets and rolling out simplified onboarding to all users. No new features will be built this sprint.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 7 | ONBD-005 rollout, MET-003, MET-004, RET-002 |
| Priya Nair | Frontend Engineer | 7 | PRE-003-COMPLETE, BUG-014 if discovered |
| Kabir Sharma | Designer | 7 | Design review for PRE-003, design support |
| Ananya Iyer | Marketing | 7 | NPS-002 launch, MKT-002 press outreach |
| Shristi Sharmistha | CEO & Product Manager | 7 | Q2-REVIEW-001, INVEST-001, overall coordination |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| PRE-003-COMPLETE | Prenatal presets — complete and ship | Priya | 3 | P0 | This feature is critical for user feedback and must be live before the NPS survey. |
| ONBD-005 | Simplified onboarding — ship to 100% | Arjun | 2 | P0 | This needs to be deployed to improve user experience and retention metrics before Q2 closes. |
| MET-003 | Weekly metrics — June complete and Q2 final | Arjun | 2 | P0 | Final metrics are essential for the Q2 review and must be accurate. |
| Q2-REVIEW-001 | Q2 OKR review — all objectives assessed | Shristi | 3 | P0 | This review is necessary to evaluate our performance and share insights with stakeholders. |
| RET-002 | Retention cohort analysis — June cohort | Arjun | 3 | P1 | Understanding retention will inform our strategies moving forward. |
| BUG-014 | Prenatal goal values wrong units (if discovered) | Priya | 2 | P1 | This is a contingency ticket in case a critical bug is identified post-deployment. |
| INVEST-001 | Q2 investor update to Ravi | Shristi | 1 | P1 | Timely communication with investors is crucial for maintaining trust and transparency. |
| MET-004 | June metrics sheet finalised | Arjun | 1 | P0 | Finalizing metrics is necessary for the Q2 OKR review. |

# Success Criteria

Prenatal presets live in production by June 26

Simplified onboarding shipped to 100% of users by June 28

Q2 OKR review complete and shared by June 30

All Q2 closing numbers verified: MAU 3512, retention 47%, NPS 41, App Store 4.2, custom foods 847

Investor update sent to Ravi by June 30

Zero P1 bugs in production at Q2 close

# Dependencies

All features must be fully developed and tested before this sprint.

Final metrics must be pulled from Supabase at the close of business on June 30.

# Risks

Risk: If a bug is found in PRE-003-COMPLETE, it could delay the release. Mitigation: Priya will conduct thorough testing of the entire user journey before deployment.

Risk: MAU number may fluctuate, affecting Q2 metrics. Mitigation: Arjun will pull the final MAU number on June 30 after 5 PM IST to ensure accuracy.

Risk: Ravi's response to the Q2 update may require additional follow-up. Mitigation: Build time for follow-up correspondence into the June 30 schedule.

# Definition of Done

Prenatal presets live with zero P1 bugs.

Simplified onboarding at 100% rollout.

All Q2 closing numbers verified against Supabase raw data.

Q2 OKR review shared with team and Ravi.

Investor update sent and acknowledged.

June metrics sheet complete.