# Sprint 1 Planning — Nutrivana

January 1 to January 14, 2025

Establish the complete technical foundation to enable seamless feature development in subsequent sprints.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 10 | Database schema design and authentication setup |
| Priya Nair | Frontend Engineer | 5 | Setting up development environment and onboarding |
| Kabir Sharma | Designer | 10 | Working on design system and initial wireframes |
| Ananya Iyer | Marketing | 10 | Initiating waitlist collection and user research |
| Shristi Sharmistha | CEO/Product Manager | 10 | Finalizing PRD and team coordination |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| TECH-001 | Database schema design | Arjun | 3 | P0 | Essential for data management and feature implementation. |
| TECH-003 | Authentication and user session management | Arjun | 5 | P0 | Crucial for user security and session handling. |
| NUTR-TASK-003 | Date-stamped diary data model design | Arjun | 5 | P0 | Foundation for the food diary feature. |
| GOAL-SPIKE-001 | Research EER formulas by age gender activity level | Arjun | 2 | P0 | Necessary for accurate calorie tracking. |
| GOAL-SPIKE-002 | Research RDA values for all micronutrients | Arjun | 2 | P1 | Supports nutritional accuracy in the app. |
| NUTR-EPIC-001 | Create Food Diary Core epic | Shristi | 1 | P0 | Sets the stage for future diary features. |
| GOAL-EPIC-001 | Create Calorie Goal Setting epic | Shristi | 1 | P0 | Initial step towards user goal setting functionality. |
| GOAL-EPIC-002 | Create Macro and Micro Goal Setting epic | Shristi | 1 | P0 | Essential for comprehensive user goal tracking. |

# Success Criteria

Supabase database schema is fully designed with all necessary tables and columns.

JWT authentication is implemented and verified with test accounts.

Research on EER formulas is completed and documented.

RDA values for all tracked micronutrients are compiled.

All epics are created in Jira with associated child tickets.

Initial draft of the technical specification is started.

# Dependencies

Supabase account must be set up before starting database schema design.

Google Cloud project needs to be created for future API integrations.

Priya's onboarding must be completed by January 7 for effective collaboration.

# Risks

Risk: Complexity in EER formula research may delay subsequent tasks. Mitigation: Research starts on January 2, and findings will be shared by January 7 for assessment.

Risk: Priya's mid-sprint start could affect the timeline for the first feature implementation. Mitigation: Kabir will share the design system with Priya on her first day to expedite onboarding.

# Definition of Done

All tickets are marked as Done in Jira.

Database schema is reviewed and approved by Shristi.

Authentication process is tested with two user accounts.

Research findings are documented and shared in Slack.

Technical specification draft sections 1-4 are completed by Arjun.