# Sprint 1 Planning — Nutrivana

January 1 to January 14, 2025

Establish the complete technical foundation for the app, including database design and authentication setup. No user-facing features will be developed this sprint.

# Team Capacity

| Person | Role | Available Days | Focus This Sprint |
| --- | --- | --- | --- |
| Arjun Mehta | CTO | 10 | Database schema, authentication, and research |
| Priya Nair | Frontend Engineer | 5 | Setting up development environment starting January 7 |
| Kabir Sharma | Designer | 10 | Design system and initial wireframes |
| Ananya Iyer | Marketing | 10 | Waitlist collection and outreach |
| Shristi Sharmistha | Product Manager | 10 | Finalizing PRD and team coordination |

# Sprint Backlog

| Ticket ID | Title | Assignee | Story Points | Priority | Why This Sprint |
| --- | --- | --- | --- | --- | --- |
| TECH-001 | Database schema design | Arjun | 3 | P0 | Essential for data storage and retrieval. |
| TECH-003 | Authentication and user session management | Arjun | 5 | P0 | Critical for user security and access. |
| NUTR-TASK-003 | Date-stamped diary data model design | Arjun | 5 | P0 | Needed for tracking user entries over time. |
| GOAL-SPIKE-001 | Research EER formulas by age gender activity level | Arjun | 2 | P0 | To inform future calorie goal features. |
| GOAL-SPIKE-002 | Research RDA values for all micronutrients | Arjun | 2 | P1 | Supports nutritional tracking accuracy. |
| NUTR-EPIC-001 | Create Food Diary Core epic | Shristi | 1 | P0 | Foundation for future food diary features. |
| GOAL-EPIC-001 | Create Calorie Goal Setting epic | Shristi | 1 | P0 | Sets the groundwork for calorie tracking. |
| GOAL-EPIC-002 | Create Macro and Micro Goal Setting epic | Shristi | 1 | P0 | Essential for detailed nutritional goals. |

# Success Criteria

Supabase database schema designed with all necessary tables and RLS policies defined.

JWT authentication implemented and tested with two user accounts.

EER formula research completed and documented with sources.

RDA values for all tracked micronutrients researched and compiled.

Three epics created in Jira with associated child tickets.

Draft of technical specifications initiated by January 10.

# Dependencies

Supabase account must be created and configured before starting TECH-001.

Google Cloud project setup is necessary for future API integrations.

Priya's onboarding must be completed by January 7 to facilitate early schema review.

# Risks

Risk: Complexity in EER formula variants may delay the timeline for implementing calorie goals. Mitigation: Arjun will share findings from GOAL-SPIKE-001 with Shristi by January 7 to assess any impact.

Risk: Priya's mid-sprint start could hinder the first feature implementation in Sprint 2. Mitigation: Kabir will provide Priya with the design system on her first day to expedite her onboarding.

# Definition of Done

All tickets must be marked as Done in Jira.

Database schema must be reviewed and approved by Shristi.

Authentication must be tested with two distinct user accounts.

Both spike research documents must be shared in team Slack and acknowledged by Shristi.

Sections 1-4 of the technical spec must be completed by Arjun.